## BEL-148 MOT
1 |  |  |  |  | SPREADSHEET | 1) | SAVE THIS FILE TO THE PROPER FOLDER FOR YOUR PROJECT AS THE SAME NAME AS YOUR DGN (I.E. #####GS001.XLSX)
[5 empty] | INSTRUCTIONS: | 2) | ENTER ITEM CODE (FOR EXAMPLE: 201E11000) AND ADDITIONAL DESCRIPTION INTO THE BLUE CELLS
[6 empty] | 3) | ENTER ALL DATA REQUIRED, PAGE # AND SPLIT # MUST BE FILLED OUT.
[6 empty] | 4) | DO NOT REMOVE THE PROTECTION FROM THIS SPREADSHEET, LEAVE THE PROTECTION ON SO THAT YOU DO NOT DELETE NEEDED FORMULAS OR RESIZE SHEET
| Page # | 1 | [15 empty] | 1 | <--- ENTER STARTING SHEET NUMBER
| P.10 | ITEM_CODE | [6 empty] | 614E11630 | 614E12384 | 614E13312 | 614E13360 | 614E21200 | 614E22210 | 614E26400 | 615E20000 | 622E41100
ADDITIONAL_DESCRIPTION
| Split # | REF NO. | SHEET NO. | STATION TO STATION |  |  |  |  | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622
[9 empty] | INCREASED BARRIER DELINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (BI-DIRECTIONAL) | BARRIER REFLECTOR, TYPE 2 | OBJECT MARKER, TWO WAY | WORK ZONE CENTER LINE, CLASS I, 740.06, TYPE I | WORK ZONE EDGE LINE, CLASS I, 6", 740.06, TYPE I | WORK ZONE STOP LINE, CLASS I, 740.06, TYPE I | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED
[9 empty] | FT | EACH | EACH | EACH | MILE | MILE | FT | SY | FT
TO
| 1 |  |  | PRE-PHASE 1
1
| 1 | PV-1 | P.11, P.12 | 107616.5 | LT |  | 107825 | LT | [7 empty] | 239
| 1 | PV-2 | P.11, P.13 | 109200 | LT |  | 109437.5 | LT | [7 empty] | 240
1
| 1 |  |  | PHASE 1
1
| 1 | CL-1 | P.12, P.14 | 107043 |  |  | 107543 | [5 empty] | 0.09
| 1 | SL-1 | P.12, P.14 | 107543 | RT | [9 empty] | 12
| 1 | EL-1 | P.12-P.13 | 107543 | LT |  | 109493 | LT | [5 empty] | 0.32
| 1 | EL-2 | P.12-P.13 | 107543 | RT |  | 109493 | RT | [5 empty] | 0.32
1
1
| 1 | IA-1 | P.12 | 107711.5 | LT |  | 107736.5 | LT |  | 1
| 1 | PB-1 | P.12-P.13 | 107736.5 | LT |  | 109293.5 | LT |  |  | 26 | 26 |  |  |  |  | 1290
| 1 | IA-2 | P.13 | 109293.5 | LT |  | 109318.5 | LT |  | 1
1
1
| 1 | SL-2 | P.13, P.15 | 109493 | LT | [9 empty] | 12
| 1 | CL-2 | P.13, P.15 | 109493 |  |  | 109993 | [5 empty] | 0.09
1
| 1 | BD-1 | P.12 | 107791 | LT |  | 107816.5 | LT | 26
1
1
| 1 | BD-2 | P.13 | 109214 | LT |  | 109239 | LT | 25
1
| 1 | PV-3 | P.12 | 107825 | LT |  | 108249 | LT | [7 empty] | 349
| 1 | PV-4 | P.13 | 108584 | LT |  | 109200 | LT | [7 empty] | 306
1
| 1 | GD-1 | P.12-P.13 | 108208.5 | RT |  | 108618 | RT |  |  | 8 | 8
1
| 1 |  |  | PHASE 2
1
| 1 | EL-3 | P.14,P.15 | 107543 | LT |  | 109493 | LT | [5 empty] | 0.32
| 1 | EL-4 | P.14,P.15 | 107543 | RT |  | 109493 | RT | [5 empty] | 0.33
| 1 | IA-3 | P.14 | 107642 | RT |  | 107667 | RT |  | 1
| 1 | PB-2 | P.14,P.15 | 107667 | RT |  | 109386 | RT |  |  | 29 | 29 |  |  |  |  | 1450
1
| 1 | IA-4 | P.15 | 109386 | RT |  | 109411 | RT |  | 1
1
| 1 | BD-3 | P.14 | 107789 | LT |  | 107816 | LT | 27
| 1 | BD-4 | P.14 | 107992.33 | LT |  | 108272.49 | RT | 281
| 1 | BD-5 | P.15 | 108574.83 | RT |  | 108800.89 | LT | 226
| 1 | BD-6 | P.15 | 109217 | LT |  | 109242 | LT | 25
1
| 1 | GD-2 | P.14 | 107451 | LT |  | 107727.5 | LT |  |  | 6 | 6
1
1
1
1
1
1
1
1
1
1
1
1
1
| Total | TOTALS CARRIED TO GENERAL SUMMARY | [6 empty] | 610 | 4 | 69 | 69 | 0.18 | 1.29 | 24 | 1134 | 2740
| Page # | 2
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | REF NO. | SHEET NO. | STATION TO STATION
TO
| Total | TOTALS CARRIED TO GENERAL SUMMARY
| Page # | 3
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | REF NO. | SHEET NO. | STATION TO STATION
TO
| Total | TOTALS CARRIED TO GENERAL SUMMARY
| Page # | 4
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | REF NO. | SHEET NO. | STATION TO STATION
TO
| Total | TOTALS CARRIED TO GENERAL SUMMARY