## Holiday Table
DAY OF HOLIDAY OR SPECIAL EVENT | TIME ALL LANES MUST BE OPEN TO TRAFFIC
SUNDAY | 12:00N FRIDAY THROUGH 6:00 AM MONDAY
MONDAY | 12:00N FRIDAY THROUGH 6:00 AM TUESDAY
TUESDAY | 12:00N MONDAY THROUGH 6:00 AM WEDNESDAY
TUESDAY (GEN./REG. ELECTION) | 5:00 AM TUESDAY THROUGH 12:00 AM WEDNESDAY
WEDNESDAY | 12:00N TUESDAY THROUGH 6:00 AM THURSDAY
THURSDAY | 12:00N WEDNESDAY THROUGH 6:00 AM FRIDAY
THURSDAY (THANKSGIVING ONLY) | 6:00 AM WEDNESDAY THROUGH 6:00 AM MONDAY
FRIDAY | 12:00N THURSDAY THROUGH 6:00 AM MONDAY
SATURDAY | 12:00N FRIDAY THROUGH 6:00 AM MONDAY
NOT USED!

## Notification Time Table
NOTIFICATION OF TRAFFIC RESTRICTIONS TIME TABLE
ITEM | DURATION OF CLOSURE | NOTICE DUE TO PERMITS & PIO
RAMP & ROAD CLOSURES | >= 2 WEEKS | 21 CALENDAR DAYS PRIOR TO CLOSURE
| > 12 HOURS & <2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE
| <= 12 HOURS | 4 BUSINESS DAYS PRIOR TO CLOSURE
LANE CLOSURES & RESTRICTIONS | >= 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE
| < 2 WEEKS | 5 BUSINESS DAYS PRIOR TO CLOSURE
START OF CONSTRUCTION & TRAFFIC PATTERN CHANGES | N/A | 14 CALENDAR DAYS PRIOR TO IMPLEMENTATION

## Lane Value Contract Table
DESCRIPTIONS OF CRITICAL LANES TO BE MAINTAINED | RESTRICTED TIME PERIOD | TIME UNIT | DISINCENTIVE $ PER UNIT
2 LANES OF S.R. 148 | HOLIDAYS/SPECIAL EVENTS | HOUR | 300
NOT USED!

## Survey Data
PROJECT REFERENCE COORDINATES
LOCATION | NORTHING | EASTING
CONTROL POINTS
CONTROL POINT # 50 IRON PIN SET - 11.5' E. OF E. EOP, 33.5' SW OF SOUTH GATE POST | 709727.3625 | 2355043.79
CONTROL PIN # 51 IRON PIN SET - 6.5' W. OF W. EOP, 19' NW OF NW CORNER OF BRIDGE | 709356.7158 | 2355308.31
℄ CONST. S.R. 148
P.O.T. 459+00.00 | 708961.3402 | 2355284.0055
P.C. 459+93.99 | 709046.0304 | 2355324.7642
P.C.C. 462+06.27 | 709252.4376 | 2355361.6049
P.C.C. 463+15.39 | 709355.6944 | 2355328.8972
P.T. 464+65.41 | 709477.3386 | 2355241.5718
P.O.T. 465+68.47 | 709554.3457 | 2355173.0686
℄ EX. R/W S.R. 148
P.T. 457+79.53 | 708850.6078 | 2355226.3887
P.C. 459+79.59 | 709025.6629 | 2355323.2375
P.T. 464+27.51 | 709441.9284 | 2355273.0121
P.C. 472+19.79 | 710024.0626 | 2354735.5855
INTERSECTIONS
℄ CONST. 464+39.99= ℄ R/W/ 464+49.46 | 709458.0554 | 2355258.1237
BM #1 - ELEV. 1013.27
IRON PIN SET 9' EAST OF EDGE OF PAVEMENT
STA. 460+32.70, 19.92' RT.
BM #2 - ELEV. 1007.40
IRON PIN SET 6' WEST OF EDGE OF PAVEMENT
STA. 463+26.75, 17.24' LT.