## Sheet1
UTILITY CONFLICTS
PROJECT: CLE-132-1264 |  |  |  | PID: 113005 | DATE: 2/22/2024
Bridge No.: CLE-132-1264
Description: Rehab of single span bridge with Superplasticized Dense Concrete Overlay (1.75" Thick), replace backwalls and expansion joints, and repair deck edge under railing anchor with trowelable mortar. Replace approach guardrail, end terminal assemblies, and bridge terminal assemblies and DBR bridge railing APP. Traffic will be detoured.
LAT | LONG | Google
39.0866 | -84.1766 | LINK
CONFLICTS SUMMARY
STAGE 1 PLAN SHEET # | COMPANY | UTILITY TYPE | STATION & OFFSET | LOCATION | AERIAL OR UNDERGROUND | CONFLICT? | COMMENTS
27 | DUKE ELECTRIC | ELECTRIC | STA. 10+55.90 OFFSET 43.75 LT TO STA. 15+55.33 OFFSET 63.07 LT & STA. 8+67.31 OFFSET 37.04 LT TO STA. 11+20.14 OFFSET 20.53 LT TO STA. 12+90.73 OFFSET 19.71 LT TO STA. 15+21.36 OFFSET 42.97 LT | SR 132 | AERIAL | YES | Potential conflict with the aerial lines close to the bridge.
27 | MCI/VERIZON & CINCINNATI BELL TELEPHONE | TELECOM | STA. 10+55.90 OFFSET 43.75 LT TO STA. 15+55.33 OFFSET 63.07 LT & STA. 8+67.31 OFFSET 37.04 LT TO STA. 11+20.14 OFFSET 20.53 LT TO STA. 12+90.73 OFFSET 19.71 LT TO STA. 15+21.36 OFFSET 42.97 LT | SR 132 | AERIAL | YES | Potential conflict with the aerial lines close to the bridge.
27 | CLERMONT COUNTY WATER RESOURCES DEPARTMENT | SANITARY | STA. 11+57.09 OFFSET 46.02 LT TO STA. 14+99.09 OFFSET 46.64 LT TO STA. 15+03.08 OFFSET 22.66 LT | SR 132 | UNDERGROUND | NO | Will be out of the way of proposed guardrail and should not be affected by the minimal cuts or fills.
27 | CLERMONT COUNTY WATER RESOURCES DEPARTMENT | WATER | STA. 8+67.61 OFFSET 35.54 LT TO STA. 15+51.64 OFFSET 32.29 LT | SR 132 | UNDERGROUND | NO | Will be out of the way of proposed guardrail and should not be affected by the minimal cuts or fills.