## Utility Log
O.U.P.S 1-800-362-2764 |  | COMPANY ID: Euthenics, Inc. |  |  |  |  | PROJECT: CUY-71-18.48 |  | PID: 105793 | Last Updated By: BPS | 2022-10-05 | 9:00
PM: Brandon Sopko, P.E. |  | OUPS TICKET 12/09/2020 Design: A034402420-00A 12/09/2020 Design: A034402424-00A 12/09/2020 Design: A034402436-00A 12/09/2020 Design: A034402439-00A |  | OUPS TICKET XX/XX/2020 Markings: AXXXX |  |  | Location- Buhrer Avenue Pedestrian Bridge over IR-71 Cuyahoga County, OH |  |  | Additional Notes:
Utility Company | Utilty | Contact | Project Notification Notice (Emailed by ODOT or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Utility Location | Sent Feasibilty Study | Comments | Sent Stage 1 Plans | Received Comments | Sent Stage 2 Plans | Received Comments | Sent Stage 3 Plans | Received Comments | Remarks | UG or OH
Name and Address | Type | Name
Underground at bridge ends and under bridge beneath IR-71
City of Cleveland (Division of Water) (CWD) | Water | Rasheed Warith | Euthenics sent | Sent OUPS | Received |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email / hard copy by mail | 2021-01-04 | Sent Stage 2 Plans by email (not required per Plan Review manual but submitted | 2022-08-12 | Sent Stage 3 Plans via email (not required per Plan Review manual but submitted | Received approval letter from CWD after submission of Stage 1 plans. No additional correspondence
1201 Lakeside Ave. |  | rasheed_warith@ClevelandWater.com | Project Notification | Ticket on | Response by | [6 empty] | for CWD records) |  | for CWD records) | was required pe CWD Plan Review Manual, however continued to submit staged submittals
Cleveland, OH 44114 |  |  | by email on | 2020-12-09 | email on |  | 2021-03-16 | Submitted Feasibilty Study with a hard copy by mail | 2021-09-27 | Received approval letter from CWD. |  |  |  |  | for CWD records.
|  | Fred Roberts | 2021-03-11 |  | 2020-12-23
|  | fred_roberts@ClevelandWater.com |  |  |  |  | 2021-04-12 | CWD responded that they have no comment on the Feasibility Study as | 2021-09-29 | Sent response notifying CWD that we do not anticipate any casting adjustments
|  | 216-664-2444 x75590 | [5 empty] | presented. |  | as the letter states.
3 conduits carried on the crossframe of the bridge
The Illuminating Company (CEI) | Electric | John M. Zassick | Euthenics sent | Sent OUPS | Received |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email | CEI aerial facilities connect to ODOT utility pole which provides power service for ODOT ITS camera
6896 Miller Rd, Suite 101 |  | jmzassick@firstenergycorp.com | Project Notification | Ticket on | Response by | [9 empty] | along I-71. Through coordination with CEI, After contractor has set new pole and run the
Brecksville, OH 44141 |  | 440-546-8706 | by email on | 2020-12-09 | email on |  | 2021-03-12 | Received response that CEI will maintain the existing 3 - 4" diameter steel | 2021-08-30 | Received CEI UG Redline of existing facilities on Buhrer Avenue | 2022-01-04 | Received response noting availability for a field meeting | 2022-09-12 | Sent follow-up email to coordinate CEI setting service pole for project. | underground cable to it and up it, CEI will disconnect from the old pole and connect to the new one.
|  |  | 2021-03-11 |  | 2020-12-31 |  |  | conduits with rebuilding both failed (rusted out) conduit expansion joint at the |  | Includes multiple poles on the west end, two being CEI cable poles and one |  | Sheet 23 - abutment modifications do not touch the CEI conduit window |  |  | Contractor to call CEI customer service at 800-589-3101 to schedule work. Coordination with CEI
[8 empty] | abutment ends with both solid and split fiberglass conduit material. CEI may |  | being CPP street light pole. |  | If CEI can add conduits, this window will need to be enlarged. | 2022-09-12 | Received response with updated customer service number for contractor to call | plan note has been added to clarify CEI's role in project. AT&T has already removed utilities from \
[8 empty] | also pursue adding up to three additional 4" IPS fiberglass conduits. CEI |  | West end existing CEI UG pole P#650490 to padmount transformer K-49594 |  | It is likely end crossframe will etermine CEI's options |  | for coordination with CEI for power service. CEI will disconnect service at the | existing pole.
[8 empty] | requests special consideration for replacement end frame design to provide |  | at 1700 Buhrer Ave not depicted on Stage 1 sheet 10 but should be (buried |  |  |  | old pole and connect to new one.
[8 empty] | adequate space for additional conduits. |  | cable close to project). | 2022-01-05 | Euthenics reached out to ODOT requesting availability for a field meeting |  |  | CEI will not perform any work to conduits underneath bridge as part of this project.
East end large CEI manhole MH-9214-02 (7’-7” wide by 9’-2” long) with four
[7 empty] | 2021-03-15 | Received response that CEI has no issues with overhead facilities. Requested |  | duct systems (one west and three east). | 2022-01-06 | ODOT responded that they are discussing CEI's response internally and checking
[8 empty] | we stay clear of the cable poles at both ends of the bridge. |  |  |  | with Central Office on how to handle the utilities request. Directed Euthenics to hold
[10 empty] | Can possibly meet in September to field review the redlines |  | off on scheduling a field meeting until a response is received from Central Office.
May still pursue installing additional fiberglass conduits across the bridge
[11 empty] | 2022-01-21 | ODOT noted they are still working on the coordination with CEI and will pass any
[9 empty] | 2021-10-04 | Reached out to CEI to verify that power connected to utility pole called to be |  | info along as it comes up.
relocated was CEI's service connection.
[11 empty] | 2022-02-10 | ODOT informed CEI that adding more conduits to the bridge will not be allowed.
[9 empty] | 2021-10-04 | Received response confirming CEI's service connection and for relocation ODOT
would need to call CEI's customer service at 800-544-4877.
Dominion Energy Ohio (DEO) | Gas | Micah Risacher | Euthenics sent | Sent OUPS | Received | Underground, Station left of bridge | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email | DEO confirmed that there are no conflicts on project.
320 Springside Drive |  | micah.j.risacher@dominionenergy.com | Project Notification | Ticket on | Response by
Akron, OH 44333 |  | 330-664-2638 | by email on | 2020-12-09 | email on |  | 2021-04-21 | Received response that Dominion has no conflict within the project limits. | 2021-09-02 | Received DEO response letter confirming there are no conflicts with DEO | 2022-01-06 | Received response that Dominion has no additional comments
|  |  | 2021-03-11 |  | 2020-12-10 |  |  |  |  | facilities on the project. DEO requested our plans include note requiring
|  | Submit plans to: |  |  |  |  | 2021-04-22 | Requested Strip Map from Dominion and/or information on gas line locations |  | contractor to maintain clearances and supports of their pipelines. | 2022-02-04 | Received duplicate response that Dominion has no additional comments
relocation@dom.com
[7 empty] | 2021-04-22 | Received response that they have a 4" plastic gas main located 2' south of the
north property line of Buhrer Avenue that ends 131' east of the west wall of
1633 Buhrer Ave. This coincides with the large gas meter adjacent to bridge.
Underground fiber wire service at forward abutment of the bridge with nearby handholes
AT&T - Ohio (AT&T) | Communications | James Janis | Euthenics sent | Sent OUPS | Received |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email | AT&T has removed facilities that were attached to ODOT utility pole. Now that these facilities are
13630 Lorain Ave, 2nd Floor |  | pj8191@att.com | Project Notification | Ticket on | Response by | [9 empty] | removed, there are no conflicts with AT&T on this project.
Cleveland, OH 44111 |  | 216-476-6142 | by email on | 2020-12-09 | email on |  | 2021-07-23 | Followed up with AT&T to request they verify the accuracy of our information. | 2021-08-31 | Received email that AT&T does maintain facilities on the east side of the bridge. |  |  | 2022-08-15 | Received response from Eric Johnston that he accepted a new position with AT&T
|  |  | 2021-03-11 |  | 2021-01-18 |  |  |  |  | Facilities feed the ODOT traffic camera located southeast of the bridge. Per |  |  |  | and is no longer a point of contact on this project.
records, facilities dip down utility pole into conduit & handholes that belong to
[10 empty] | ODOT. Plans to make a field visit to further inspect facilities. |  |  | 2022-08-15 | Received phone call and correspondence from Rick Greenhill at AT&T. Rick wanted
to speak to ODOT regarding (1) confirmation in writing from ODOT that cicuit is no
[9 empty] | 2021-10-04 | ATT field visit determined that utility called out for relocation is not ATT's pole. It |  |  |  | longer needed and (1) coordinate access to the base of the camera pole to remove
[10 empty] | does have ATT communication lines and CEI power lins which currently provide |  |  |  | equipment.
service to the ODOT Traffic Camera lcoated along I-71. If relocation is necessary,
[10 empty] | it would be at the request of the pole owner and the relocation work would be |  |  | 2022-08-16 | Rick corresponded with Bryan Comer (ODOT's Statewide ITS Engineer). Bryan
[10 empty] | compensable to the project. |  |  |  | noted that ODOT won't need any ATT service for the foreseeable future. Bryan and
Rick also determined that AT&T & ODOT's records show the service is disconnected,
but AT&T's records also shows that it is still assigned to this location. AT&T is
verifying they have inventory within ODOT's cabinet that needs removed.
[13 empty] | 2022-09-28 | Rick notified Euthenics that AT&T facilities are now removed.
[13 empty] | 2022-09-30 | BPS forwarded notification to ODOT for records.
Aerial facilities west of bridge.
MCI - Verizon | Communications | Dan Arz MCI/XO OSP engineer | Euthenics sent | Sent OUPS | Received |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email | MCI confirmed that there are no conflicts on project.
12300 Ridge Road |  | daniel.arz@verizon.com | Project Notification | Ticket on | Response by
North Royalton, Ohio 44133 |  | 440-457-4832 | by email on | 2020-12-09 | email on |  | 2021-03-22 | Received response that MCI/Verizon has aerial facilities on the east side of
|  |  | 2021-03-11 |  | 2021-01-18 |  |  | W. 17th Street that then follow Buhrer Ave. to the west. There are no
buried facilities near the project limits. MCI does not foresee any conflicts.
Aerial facilities east and west of bridge.
Charter Communications | Cable | Daniel Mccafferty | Euthenics sent | Sent OUPS |  |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email (error message to Gary Naumann) | Charter confirmed that there are no conflicts on project.
8179 Dow Circle |  | daniel.mccafferty@charter.com | Project Notification | Ticket on
Strongsville, Ohio 44136 |  | 216-575-8016 x216-555-4262 | by email on | 2020-12-09 |  |  | 2021-03-11 | Received response that Charter has aerial facilities east and west of I-71 |  |  | 2022-01-05 | Received response that Charter should have no conflict here. | 2022-08-15 | Emailed Charter requesting an updated point of contact for project.
|  |  | 2021-03-11 |  |  |  |  | along Buhrer Avenue, but do not cross I-71. Therefore, they should not be
[8 empty] | in conflict with our project. |  |  |  |  | 2022-08-15 | Received response that Daniel Mccafferty is new supervisor
[13 empty] | 2022-08-15 | Sent Stage 3 Plans via email and requested full contact info
[13 empty] | 2022-08-16 | Received Dan's updated contact information and revised plans
[13 empty] | 2022-08-16 | Received response that Charter should have no conflict with this project.
Water Pollution Control (WPC) | Sewer | Elie Ramy | Euthenics sent | Sent OUPS | Received | Underground at the rear approach of bridge, not on or under structure | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email and requested verification of sewer termination | WPC provided response letter indicating that WPC has no objection to the proposed work on
12302 Kirby Avenue |  | eramy@clevelandwpc.com | Project Notification | Ticket on | Response by | [9 empty] | this project.
Cleveland, OH 44108 |  | 216-664-2756 | by email on | 2020-12-09 | email on |  | 2021-03-22 | Received response that there is an existing No. 2 brick main sewer on Buhrer | 2021-08-20 | Received response that there is an existing No. 2 brick main sewer on Buhrer | 2022-01-06 | Received response that there is an existing No. 2 brick main sewer on Buhrer | 2022-08-15 | Spoke to Elie - WPC can not locate manhole that would be in ODOT's R/W. Suggested
|  |  | 2021-03-11 |  | 2020-12-21 |  |  | Ave. and this should be shown in the plans. WPC does not foresee impact on |  | Ave. and this should be shown in the plans. WPC does not foresee impact on |  | Ave. and this should be shown in the plans. WPC does not foresee impact on |  | using survey data to verify termination. Requested WPC sewer to be labeled.
[8 empty] | the existing City sewers. |  | the existing City sewers. |  | the existing City sewers.
[13 empty] | 2022-08-15 | Resent Stage 3 plans with WPC sewer labeled. Also sent survey field book showing
no evidence of sewer extending past manhole in roadway.
[13 empty] | 2022-08-17 | Received response letter indicating that WPC has no objection to the proposed
work on this project.
City of Cleveland | Traffic | Andrew R. Cross, Traffic Engineer | Euthenics sent | Sent OUPS |  |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Drake Brauer Sent Stage 1 Plans by email | 2022-01-04 | Sent Stage 2 Plans by email | 2022-08-12 | Sent Stage 3 Plans via email | City of Cleveland Traffic provided comments on the pedestrian detour on 4/19/2022 and these
Division of Traffic Engineering |  | across@city.cleveland.oh.us | Project Notification | Ticket on | [10 empty] | comments have been addressed and incorporated into the final plans.
601 Lakeside Ave., Rm 25 |  | 216-664-3197 | by email on | 2020-12-09 |  |  | 2021-07-23 | ODOT forwarded pedestrian detour route request for approval |  |  | 2022-04-19 | Andy Cross provided comments and appoved the pedestrian detour.
Cleveland, Ohio 44114 |  |  | 2021-03-11
ODOT District 12 | Traffic | Keri Welch | ODOT Sent | Sent OUPS |  |  | 2021-03-11 | Submitted Feasibilty Study by email. | 2021-08-19 | Sent Stage 1 Plans by email | 2022-12-22 | Drake Brauer Sent Stage 2 Plans by email | 2022-08-08 | Sent Stage 3 Plans | D12 Traffic has been providing comments as part of ODOT's Stage Reivew Comments. Alll comments
Division of Traffic Engineering |  | keri.welch@dot.ohio.gov | Project Notification | Ticket on | [10 empty] | have been disposed of and addressed.
5500 Transportation Boulevard |  | 216-584-2166 | by email on | 2020-12-09 |  |  |  |  | 2021-09-20 | Received plan information on ITS camera installation from ODOT and direction
Garfield Heights, Ohio 44125 |  |  | 2021-03-09 | [6 empty] | to include relocation of pole and pull boxes in plan details.
ODOT Central Office ITS | Traffic |  | ODOT Sent | [7 empty] | 2022-12-22 | Drake Brauer Sent Stage 2 Plans by email | 2022-08-08 | Sent Stage 3 Plans | OTO has been providing comments as part of ODOT's Stage Reivew Comments. Alll comments
ODOT Office of Traffic Operations |  | cen.its.lab@dot.ohio.gov | Project Notification | [11 empty] | have been disposed of and addressed.
1606 W. Broad Street |  | 614-387-4113 | by email on
Columbus, Ohio 43223 |  |  | 2021-10-14