## DGN Clip
CUY-480 ROADWAY ESTIMATED QUANTITIES
ITEM | ITEM EXT. | QTY | UNIT | DESCRIPTION | ABUT. | PIERS | SUPER. | GENERAL | SHEET REF.
614 | 11000 | LS | LS | MAINTAINING TRAFFIC
619 | 16011 |  | MNTH | FIELD OFFICE, TYPE B, AS PER PLAN
623 | 10001 | LS | LS | CONSTRUCTION LAYOUT STAKES AND SURVEYING, AS PER PLAN
832 | 30000 |  | EACH | EROSION CONTROL

## 202E11201
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 202E11201
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-03 | PAGE NUMBER: | 1
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | PORTIONS OF STRUCTURE REMOVED, AS PER PLAN | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| VOLUME = | 10.1535 | CY |  | Use $900/CY
| LS COST = | 10000
0
TOTAL | [7 empty] | LUMP | LUMP

## 509E10001
QUANTITY |  |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 509E10001
CALCULATIONS |  |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 2
PID NO. |  | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME |  | EPOXY COATED REINFORCING STEEL, AS PER PLAN | [6 empty] | PAY UNIT | LB
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| BAR | LENGTH | WT. / FT. | TOTAL
| R401 | 787.6 | 0.668 | 526
| R601 | 2054.58 | 1.502 | 3086
| R602 | 3325.08 | 1.502 | 4994
|  |  |  | 8606 | = TOTAL |  |  |  | 8606
TOTAL | [8 empty] | 8606

## 509E20000
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 509E20000
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 3
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | REINFORCING STEEL, REPLACEMENT OF EXISTING REINFORCING STEEL | [6 empty] | PAY UNIT | LB
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  |  | ASSUME CONTINGENCY QUANTITY = | 500 | LB
TOTAL | [7 empty] | 500

## 510E10000
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 510E10000
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 4
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
1 DOWEL IN DECK & 1 DOWEL IN TOP OF PARAPET EVERY 12"
[5 empty] | Total | 1648 |  | 1648
TOTAL | [7 empty] | 1648 | 1648

## 511E34449
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 511E34449
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 5
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | CLASS QC2 CONCRETE, BRIDGE DECK (PARAPET), AS PER PLAN | [6 empty] | PAY UNIT | CY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  |  |  | AREA (SF) | LENGTH | VOLUME (CY)
| CONCRETE REFACING |  |  | 2.2 | 362.81 | 29.5623 | N. PARAPET
|  |  |  | 2.2 | 361.05 | 29.4189 | S. PARAPET
[5 empty] | Total | 59 |  | 59
TOTAL | [7 empty] | 59 | 59

## 512E10100
QUANTITY |  |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 512E10100
CALCULATIONS |  |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 6
PID NO. |  | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME |  | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
TOTAL FROM EX. PLANS (NEED TO REVISE FOR ST. 2) (ADDED 25 SY FOR SEALING REFACING)
[6 empty] | TOTAL: | 1550 | SY
[6 empty] | Total | 1550 |  | 1550
TOTAL | [8 empty] | 1550 | 1550

## 512E10600
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 512E10600
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 7
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | CONCRETE REPAIR BY EPOXY INJECTION | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  |  | TOTAL CRACK REPAIRS = | 11.5
[5 empty] | Total | 12 |  | 12
TOTAL | [7 empty] | 12 | 12

## 512E74000
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 512E74000
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 8
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | REMOVAL OF EXISTING COATINGS FROM CONCRETE SURFACES | [6 empty] | PAY UNIT | SY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  |  | TOTAL COATING REMOVALS = | 1240 | SY
[5 empty] | Total | 1240 |  | 1240
TOTAL | [7 empty] | 1240 | 1240

## 516E01300
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 516E01300
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 9
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | ELASTOMERIC STRIP SEAL WITHOUT STEEL EXTRUSIONS | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
LENGTH
[5 empty] | REAR ABUT = | 76.5 | FT
[5 empty] | FWD. ABUT = | 76.5 | FT
[5 empty] | Total | 153 |  | 153
TOTAL | [7 empty] | 153 | 153

## 516E47001
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 516E47001
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 10
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | JACKING AND TEMPORARY SUPPORT OF SUPERSTRUCTURE, AS PER PLAN | [6 empty] | PAY UNIT | LUMP
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
[5 empty] | Total | LUMP |  | LUMP
USE $5000
TOTAL | [7 empty] | LUMP | LUMP

## 519E11101
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 519E11101
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 11
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | PATCHING CONCRETE STRUCTURE, AS PER PLAN | [6 empty] | PAY UNIT | SF
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
[6 empty] | Measured | Estimated
[6 empty] | Quantity | Quantity
[5 empty] | REAR ABUTMENT = | 17.1 | 17.955
[5 empty] | FWD. ABUTMENT = | 192.6 | 202.23
[5 empty] | PIER #1 = | 118.9 | 124.845
[5 empty] | PIER #2 = | 217.8 | 228.69
[5 empty] | PIER #3 = | 85.2 | 89.46
[5 empty] | PIER #4 = | 162 | 170.1
[5 empty] | NORTH PARAPET = | 59.8 | 62.79
[5 empty] | SOUTH PARAPET = | 57.6 | 60.48
[5 empty] | Total |  | 957 | 957
TOTAL | [7 empty] | 957 | 957

## 519E12300
QUANTITY |  | MADE BY: | WER | DATE: | 2023-05-01 | ITEM NUMBER: | 519E12300
CALCULATIONS |  | CHECKED BY: | JSP | DATE: | 2023-05-02 | PAGE NUMBER: | 12
PID NO. | 117872 |  | PROJECT | CUY-480-1787L&R |  | STRUCTURE | CUY-480-1788L (SFN 1813102)
ITEM NAME | PATCHING CONCRETE BRIDGE DECK - TYPE B | [6 empty] | PAY UNIT | SY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
[5 empty] | Measured | Estimated
[5 empty] | Quantity | Quantity
|  |  |  | DECK PATCHING = | 1118.9 | 1174.845
[5 empty] | Total | 1175 |  | 1175
TOTAL | [7 empty] | 1175 | 1175

## VOID_Calc
BEAM |  | INTERMEDIATE CROSSFRAME (BOTTOM MEMBER) |  | END CROSSFRAME (BOTTOM MEMBER)
TYPE | WF 33x130 | TYPE | L 3x3x5/16 | TYPE | L 4x4x5/16
LENGTH (FT) | 125 | LENGTH (FT) | 9.5 | LENGTH (FT) | 9.5934
DEPTH (IN.) | 33.1 | LEG 1 LENGTH (IN.) | 3 | LEG 1 LENGTH (IN.) | 4
WEB THICKNESS (IN.) | 0.58 | LEG 2 LENGTH (IN.) | 3 | LEG 2 LENGTH (IN.) | 4
FLANGE WIDTH (IN.) | 11.51 | THICKNESS (IN.) | 0.3125 | THICKNESS (IN.) | 0.3125
FLANGE THICKNESS (IN.) | 0.855 | QUANTITY | 98 | QUANTITY | 14
QUANTITY | 9
|  | TOTAL SURFACE AREA (SQ FT) | 931 | TOTAL SURFACE AREA (SQ FT) | 179.0761
TOTAL SURFACE AREA (SQ FT) | 9174.375
|  | INTERMEDIATE CROSSFRAME (DIAGONAL MEMBERS) |  | END CROSSFRAME (DIAGONAL MEMBERS)
|  | TYPE | L 3x3x5/16 | TYPE | L 4x4x5/16
|  | LENGTH (FT) | 9.8106 | LENGTH (FT) | 6.9692
|  | LEG 1 LENGTH (IN.) | 3 | LEG 1 LENGTH (IN.) | 4
|  | LEG 2 LENGTH (IN.) | 3 | LEG 2 LENGTH (IN.) | 4
|  | THICKNESS (IN.) | 0.3125 | THICKNESS (IN.) | 0.3125
|  | QUANTITY | 120 | QUANTITY | 24
|  | TOTAL SURFACE AREA (SQ FT) | 1177.2753 | TOTAL SURFACE AREA (SQ FT) | 223.0146
|  | **INDICATED BY DOUBLE LINE ON FRAMING PLAN |  | SPECIAL END CROSSFRAME (DIAGONAL MEMBERS)
|  | INTERMEDIATE CROSSFRAME (CONDUIT BAY - L SHAPES) |  | TYPE | L 4x4x5/16
|  | TYPE | L 3x3x5/16 | LENGTH (FT) | 6.6228
|  | LENGTH (FT) | 1.1992 | LEG 1 LENGTH (IN.) | 4
|  | LEG 1 LENGTH (IN.) | 3 | LEG 2 LENGTH (IN.) | 4
|  | LEG 2 LENGTH (IN.) | 3 | THICKNESS (IN.) | 0.3125
|  | THICKNESS (IN.) | 0.3125 | QUANTITY | 4
|  | QUANTITY | 40
|  |  |  | TOTAL SURFACE AREA (SQ FT) | 35.3217
|  | TOTAL SURFACE AREA (SQ FT) | 35.975
END CROSSFRAME (PLATE MEMBERS)
|  | INTERMEDIATE CROSSFRAME (CONDUIT BAY - C SHAPE) |  | TYPE | PL. 1.25'X2'X3/8"
|  | TYPE | C 12x20.7 | LENGTH (FT) | 1.25
|  | LENGTH (FT) | 9.5 | WIDTH (FT) | 2
|  | DEPTH (IN.) | 12 | THICKNESS (IN.) | 0.375
|  | WEB THICKNESS (IN.) | 0.282 | QUANTITY | 40
|  | FLANGE WIDTH (IN.) | 2.942
|  | FLANGE THICKNESS (IN.) | 0.501 | TOTAL SURFACE AREA (SQ FT) | 199.2361
|  | QUANTITY | 10
SPECIAL END CROSSFRAME (PLATE MEMBERS AT CONDUITS)
|  | TOTAL SURFACE AREA (SQ FT) | 221.8717 | TYPE | PL. 1.25'X2'X3/8"
|  |  |  | LENGTH (FT) | 1.25
|  | BAY 4 - INTERMEDIATE CROSSFRAME (BOTTOM MEMBER) |  | WIDTH (FT) | 2
|  | TYPE | L 3x3x5/16 | THICKNESS (IN.) | 0.375
|  | LENGTH (FT) | 5.9167 | QUANTITY | 2
|  | LEG 1 LENGTH (IN.) | 3
|  | LEG 2 LENGTH (IN.) | 3 | TOTAL SURFACE AREA (SQ FT) | 9.7118
|  | THICKNESS (IN.) | 0.3125
|  | QUANTITY | 10
|  |  |  | GRAND TOTAL SURFACE AREA (SQ FT) | 12374.0948
|  | TOTAL SURFACE AREA (SQ FT) | 59.1667 | 5% CONTINGENCY | 618.7047
|  |  |  | GRAND TOTAL SURFACE AREA (SQ FT) | 13000
BAY 4 - INTERMEDIATE CROSSFRAME (DIAGONAL MEMBERS)
|  | TYPE | L 3x3x5/16
|  | LENGTH (FT) | 6.4035
|  | LEG 1 LENGTH (IN.) | 3
|  | LEG 2 LENGTH (IN.) | 3
|  | THICKNESS (IN.) | 0.3125
|  | QUANTITY | 20
|  | TOTAL SURFACE AREA (SQ FT) | 128.0709