## TITLE TABLES
STRUCTURE | NHS | FUNCTIONAL CLASSIFICATION
FRA-70-12.03 | YES | 01 - INTERSTATE (URBAN)
FRA-670-1028 | YES | 01 - INTERSTATE (URBAN)
FRA-104-8.16 | YES | 02 - ARTERIAL FREEWAY (URBAN)
MAR-23-5.85 | YES | 03 - PRINCIPAL ARTERIAL OTHER (RURAL)
MAR-95-22.63 | NO | 04 - MINOR ARTERIAL (RURAL)
MAR-423-15.21 | NO | 05 - MAJOR COLLECTOR (RURAL)

## MN001
NOTIFICATION TIME FRAME TABLE
| ITEM | DURATION OF CLOSURE | NOTIFICATION DUE TO DISTRICT 6 COMMUNICATIONS OFFICE | SIGN DISPLAYED TO PUBLIC
| RAMP & ROAD CLOSURES | >= 2 WEEKS | 21 CALENDAR DAYS PRIOR TO CLOSURE | 14 CALENDAR DAYS PRIOR TO CLOSURE
|  | > 12 HOURS & < 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE | 7 CALENDAR DAYS PRIOR TO CLOSURE
|  | <=12 HOURS | 4 BUSINESS DAYS PRIOR TO CLOSURE | 2 BUSINESS DAYS PRIOR TO CLOSURE
| LANE CLOSURES & RESTRICTIONS | >= 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE
|  | < 2 WEEKS | 5 BUSINESS DAYS PRIOR TO CLOSURE
| START OF CONSTRUCTION & TRAFFIC PATTERN CHANGES | N/A | 14 CALENDAR DAYS PRIOR TO IMPLEMENTATION
NOTICE OF CLOSURE SIGN TIME TABLE
| ITEM | DURATION OF CLOSURE | SIGN DISPLAY TO PUBLIC | NOTIFICATION DUE TO DISTRICT 6 COMMUNICATIONS OFFICE
| RAMP & ROAD CLOSURES | >= 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE | 21 CALENDAR DAYS PRIOR TO CLOSURE
|  | > 12 HOURS & < 2 WEEKS | 7 CALENDAR DAYS PRIOR TO CLOSURE | 14 CALENDAR DAYS PRIOR TO CLOSURE
|  | <= 12 HOURS | 2 BUSINESS DAYS PRIOR TO CLOSURE | 4 BUSINESS DAYS PRIOR TO CLOSURE
[7 empty] | DAY OF HOLIDAY OR SPECIAL EVENT | TIME ALL LANES MUST BE OPEN TO TRAFFIC
[7 empty] | SUNDAY | 12:00 NOON FRIDAY THROUGH 6:00 AM MONDAY
[7 empty] | MONDAY | 12:00 NOON FRIDAY THROUGH 6:00 AM TUESDAY
[7 empty] | MONDAY (TOTAL SOLAR ECLIPSE) | 12:00 NOON FRIDAY THROUGH 6:00 AM WEDNESDAY
[7 empty] | TUESDAY | 12:00 NOON MONDAY THROUGH 6:00 AM WEDNESDAY
[7 empty] | TUESDAY (GEN./REG. ELECTION) | 5:00 AM TUESDAY THROUGH 12:00 AM WEDNESDAY
[7 empty] | WEDNESDAY | 12:00 NOON TUESDAY THROUGH 6:00 AM THURSDAY
[7 empty] | THURSDAY | 12:00 NOON WEDNESDAY THROUGH 6:00 AM FRIDAY
[7 empty] | THANKSGIVING | 6:00 AM WEDNESDAY THROUGH 6:00 AM MONDAY
[7 empty] | FRIDAY | 12:00 NOON THURSDAY THROUGH 6:00 AM MONDAY
[7 empty] | SATURDAY | 12:00 NOON FRIDAY THROUGH 6:00 AM MONDAY
OVERHEAD DIGITAL MESSAGE SIGN (DMS) LOCATIONs
I-670 EB @ MM 5.2, ST. CLAIR AVE
I-670 EB @ MM 5.6, WEST OF JOYCE AVE
I-670 EB @ MM 6.0, EAST OF JOYCE AVE
I-670 EB @ MM 6.5, EAST OF LEONARD AVE
I-670 EB @ MM 7.0, WEST OF NELSON RD/US-62
I-670 EB @ MM 8.1, EAST OF 5TH AVE
I-670 EB @ MM 8.9, AIRPORTDR/ INTERNATIONAL GATEWAY
I-670 EB @ MM 9.4,WEST OF STELZER RD
RAMP CLOSURE RESTRICTIONS
INTERSTATE ROUTE 670 IN FRANKLIN COUNTY
SECONDARY ROUTE: INTERSTATE ROUTE 270 SLM ALONG 670: 10.43 (EAST SIDE)
[9 empty] | RAMP DESIGNATION | MOVEMENT | NO CLOSURES ALLOWED |  | DETOUR ROUTES
[11 empty] | MON-FRI | SAT-SUN | PRIMARY DETOUR ROUTE | SECONDARY DETOUR ROUTE
[9 empty] | D | I-670 EB TO I-270 NB | 5AM-1AM | 7AM-9PM | 670 E TO 270 S (RAMP E) TO OH-317 TO 270 N | 670 E TO 270 S (RAMP E) TO OH-317 TO US-62 W TO 270 N (RAMP A)
[9 empty] | E | I-670 EB TO I-270 EB | 5AM-12AM | 8AM-9PM | 670 E TO 270 N (RAMP D) TO MORSE RD. TO 270 S | 670 E TO OH-317 TO 270 S
[9 empty] | G | I-270 SB TO I-670 WB | 3AM-12AM | 6AM-10PM | 270 S TO OH-317 TO 270 N TO 670 W (RAMP I) | 270 S TO US062 E (RAMP F) TO OH-317 TO 270 N TO 670 W (RAMP I)
[9 empty] | I | I-270 WB TO I-670 WB | 5AM-11PM | 8AM-9PM | 270 N TO MORSE RD. TO 270 S TO 670 W (RAMP G) | NONE
[22 empty] | LANE VALUE CONTRACT TABLE | [6 empty] | LANE VALUE CONTRACT TABLE
[22 empty] | Section (SLM) | Existing Number of Lanes per Direction | Lane closures are NOT permitted: |  |  |  | Disincentive Amounts per minute per lane | FRA-670
[24 empty] | Lane Reduction | Mon to Fri | Sat | Sun |  | Section | Existing Number of Lanes per Direction | Lane closures are NOT permitted: |  |  |  | Disincentive Amounts per minute per lane
[22 empty] | FRA-104 | [8 empty] | Lane Reduction | Mon to Fri | Sat | Sun
[22 empty] | I-71 Ramps (8.02) to US-33 (22.98) | 2 | 2 to 1 | 5AM-9AM & 2PM-6PM | No Restriction | No Restriction | 170 | International Gateway (9.36) to I-270 (10.43) | 4 | 4 to 3 | 5AM-9AM & 12N-7PM | No Restriction | No Restriction | 245
[22 empty] | Short term shoulder closures are NOT permitted 5AM-9AM and 3PM-6PM Monday-Friday. | [8 empty] | 4 to 2 | 5AM-9AM & 12N-7PM | No Restriction | No Restriction | 245
[31 empty] | 4 to 1 | 5AM-11PM | 9AM-11PM | 9AM-11PM | 245
Short term shoulder closures are NOT permitted 5AM-9AM and 3PM-6PM Monday-Friday.
LANE VALUE CONTRACT TABLE
[15 empty] | Section (SLM) | Existing Number of Lanes per Direction | Lane closures are NOT permitted: |  |  |  | Disincentive Amounts per minute per lane
[17 empty] | Lane Reduction | Mon to Fri | Sat | Sun
FRA-70
[15 empty] | Broad Street (11.21) to Glenwood Avenue (12.41) | 3 | 3 to 2 | 5AM-9AM & 2PM-6PM | No Restriction | No Restriction | 230
[17 empty] | 3 to 1 | 5AM-10PM | 6AM-8PM | 6AM-8PM | 230
Short term shoulder closures are permitted any time except 5AM-9AM and 3PM-6PM Monday-Friday.
AGLER ROAD (34.87) TO GOSHEN LANE (35.90) NORTHBOUND | 3 | 3 TO 2 | 5AM-8PM | 7AM-9AM & 2PM-7PM | 7AM-9AM & 2PM-7PM | 445
|  | 3 TO 1 | 5AM-11PM | 6AM-10PM | 6AM-10PM | 445

## SG100
STRUCTURE REPAIR (FRA-270-1563 SFN: 2510154)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 36095
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 36095
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 36095
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 36095
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 44
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 23
STRUCTURE REPAIR (FRA-70-1017R SFN: 2504529)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 9580
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 9580
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 9580
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 9580
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 15
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 8
STRUCTURE REPAIR (FRA-70-1121 SFN: 2504588)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 31075
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 31075
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 31075
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 31075
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 25
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 13
STRUCTURE REPAIR (FRA-270-3551 SFN: 2511746)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 26820
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 26820
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 26820
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 26820
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 98
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 12
STRUCTURE REPAIR (FAY-35-1666L SFN: 2400553)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 19110
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 19110
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 19110
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 19110
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 23
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 11
STRUCTURE REPAIR (FAY-35-1666R SFN: 2400561)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 19110
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 19110
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 19110
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 19110
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 23
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 11
STRUCTURE REPAIR (MAD-70-1217L SFN: 4902610)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 16575
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 16575
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 16575
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 16575
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 24
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 12
STRUCTURE REPAIR (MAD-70-1217R SFN: 4902645)
ITEM | EXT. | DESCRIPTION | UNIT | TOTAL
514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 16575
514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 16575
514 | 00060 | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 16575
514 | 00066 | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 16575
514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MAN HOUR | 24
514 | 10000 | FINAL INSPECTION REPAIR | EACH | 12