## Cover
Notes:
1. Project summary of utility correspondence through the above referenced date.

## Utility Contacts
Utility | Contact | Contact | Notes
| (Main) | (Alternate)
Electric
The Illuminating Co.
6896 Miller Rd. Suite 101
Brecksville, OH 44141
John Zassick
440-546-8706
jmzassick@firstenergrycorp.com
Telecommunications
G4S Secure Integration
4 Walker Way, Suite 1
Albany, NY 12205
Dragan Kordich
O: 518-869-5053
C: 814-450-3396
dragan.kordich@adestagroupcom
Cable/Internet
Zito Media
PO Box 45
Rock Creek, OH 44084
Mike Piccoli
304-224-3956
mike.piccoli@zitomedia.com
Cable/Internet
Windstream
560 Ternes Ave.
Elyria, OH 44035
Geoffrey Hamm
O: 440-329-4245
C: 330-256-6133
geoffrey.p.hamm@windstream.com
Gas
Dominion Energy Ohio
320 Springdale Dr. Suite 320
Akron, OH 44333
330-664-2409
relocation@dominionenergy.com

## Tickets
Request Date | Carpenter Marty | Ticket Number | Reason
(Requester)
2021-08-03 | Andy Nixon | B121500755 | OUPS - Design request for utility plans within the project limits for PID 107300
2021-08-10 | Andy Nixon | B122201230 | OUPS - Locate request for utility plans within the project limits for PID 107300

## Illuminating Co.
Utility Company (Contact) | Consultant (Personnel) | Date | Description and Comments
First Energy | Andy Nixon | 2021-08-03 | Received mapping from OUPS Ticket.
John Zassick | Greg Sprungle | 2021-10-25 | Submitted Stage 1 Plans Via E-mail
John Zassick | Neal Underwood | 2021-11-16 | Received no conflict letter.
John Zassick | Neal Underwood | 2021-12-20 | Sent e-mail to confirm that power to new signal controller can be provided as shown in the plans.
John Zassick | Neal Underwood | 2021-12-28 | Received e-mail that power connection is acceptable as shown.
John Zassick | Neal Underwood | 2022-02-07 | Submitted Stage 2 Plans Via E-mail
John Zassick | Neal Underwood | 2022-02-08 | Received letter stating there is no conflict.

## G4S
Utility Company (Contact) | Consultant (Personnel) | Date | Description and Comments
Dragan Kordich | Andy Nixon | 2021-08-05 | Received mapping from OUPS Ticket.
Dragan Kordich | Greg Sprungle | 2021-10-25 | Submitted Stage 1 Plans Via E-mail.
Dragan Kordich | Neal Underwood | 2021-12-20 | Sent follow-up e-mail.
Dragan Kordich | Neal Underwood | 2022-01-05 | Sent follow-up e-mail. Notified of possible relocation of facilities.
Dragan Kordich | Neal Underwood | 2022-02-07 | Submitted Stage 2 Plans Via E-mail.
Dragan Kordich | Neal Underwood | 2022-02-10 | Received repeated notifications that the e-mail was not delivered to "dragan.kordich@adestagroup.com". Resent plans to "dkordich@adestagroup.com".
Dragan Kordich | Neal Underwood | 2022-02-16 | Received repeated notifications that the e-mail was delayed in sending to "dkordich@adestagroup.com" and not delivered. Attempted to call contact. No voicemail system was available.
Dragan Kordich | Neal Underwood | 2022-03-09 | Sent follow-up e-mail.
Dragan Kordich | Neal Underwood | 2022-05-18 | Submitted Stage 3 Plans Via E-mail.

## Zito
Utility Company (Contact) | Consultant (Personnel) | Date | Description and Comments
Mike Piccoli | Greg Sprungle | 2021-10-25 | Submitted Stage 1 Plans Via E-mail
Mike Piccoli | Neal Underwood | 2021-12-20 | Sent follow-up e-mail.
Mike Piccoli | Neal Underwood | 2022-01-05 | Sent follow-up e-mail. Notified of possible relocation of facilities.
Mike Piccoli | Neal Underwood | 2022-01-11 | Project discussed with Mike via phone conversation. Mike said height of lines will be measured to determine options for raising lines. He will send information to CM and ODOT.
Mike Piccoli | Neal Underwood | 2022-02-07 | Submitted Stage 2 Plans Via E-mail
Mike Piccoli | Neal Underwood | 2022-03-09 | Sent follow-up e-mail.
Mike Piccoli | Neal Underwood | 2022-05-18 | Submitted Stage 3 Plans Via E-mail
Mike Piccoli | Neal Underwood | 2022-05-19 | Received e-mail stating Zito's overhead lines run east-west on the north side of the intersection and north-south on the west side of the intersection. This will avoid any conflict with overhead lines blocking visibility of the southbound signal heads.

## Windstream
Utility Company (Contact) | Consultant (Personnel) | Date | Description and Comments
Lisa Zingula | Andy Nixon | 2021-08-03 | Received mapping from OUPS Ticket.
Geoffrey Hamm | Greg Sprungle | 2021-10-25 | Submitted Stage 1 Plans Via E-mail.
Geoffrey Hamm | Greg Sprungle | 2021-10-26 | Geoff Hamm forwarded plans to Ray French.
Geoffrey Hamm | Neal Underwood | 2021-12-20 | Sent follow-up e-mail.
Geoffrey Hamm | Neal Underwood | 2022-01-05 | Sent follow-up e-mail. Notified of possible relocation of facilities.
Geoffrey Hamm | Neal Underwood | 2022-02-07 | Submitted Stage 2 Plans Via E-mail.
Geoffrey Hamm | Neal Underwood | 2022-03-09 | Sent follow-up e-mail.
Geoffrey Hamm | Neal Underwood | 2022-03-09 | Geoff Hamm forwarded plans to Ray French and Jon Hobby for their review.
Jon Hobby | Neal Underwood | 2022-04-06 | Sent e-mail to bring attention to the potential conflict on the south side of the intersection with the overhead fiber/commuication lines obstructing the view of the signal heads. Ask Windstream about what the options would be for this.
Jon Hobby | Neal Underwood | 2022-04-19 | Sent follow-up e-mail on the visiblity conflict.
Jon Hobby | Neal Underwood | 2022-05-18 | Submitted Stage 3 Plans Via E-mail.

## Dominion
Utility Company (Contact) | Consultant (Personnel) | Date | Description and Comments
Evan Dempsey | Andy Nixon | 2021-08-04 | Received mapping from OUPS Ticket.
General Inbox | Greg Sprungle | 2021-10-25 | Submitted Stage 1 Plans Via E-mail
Adam Kearns | Greg Sprungle | 2021-11-01 | Received e-mail stating that there is a conflict with the controller and the gas lines are not shown in the correct locations. Sent a mark up of their locations but recommended test holes.
Adam Kearns | Neal Underwood | 2021-12-20 | Sent e-mail to confirm routing of gas line in the northwest corner since his markups did not meet the surveyed gas valves.
Adam Kearns | Neal Underwood | 2021-12-20 | Received e-mail that his markups are not 100% accurate. Provide location of test boxes on the south side, however, these were not found in the field by CM. Offsets were provided from property lines.
General Inbox | Neal Underwood | 2022-02-07 | Submitted Stage 2 Plans Via E-mail
Adam Kearns | Neal Underwood | 2022-02-14 | Plans were reviewed, but since SUL's information was not provided yet a full review was not completed. Requested plans be updated and sent back for review.
Adam Kearns | Neal Underwood | 2022-03-09 | CM sent Domnion information from the SULs locate of their gas facilities. CM asked them to update the new gas line routing and if Domnion owned the unkown blue plastic pipe found in the SE corner during SULs excavation.
Adam Kearns | Neal Underwood | 2022-03-28 | Sent follow-up e-mail.
Adam Kearns | Neal Underwood | 2022-03-29 | Dominion confirmed the unknown blue plastic pipe is not theirs. Adam provided more dimensions for the gas line routing in the SW corner.
Adam Kearns | Neal Underwood | 2022-05-18 | Submitted Stage 2 Plans Via E-mail
Adam Kearns | Neal Underwood | 2022-05-19 | Sent e-mail confirming there are no conflicts and provided no conflict letter.