## Sheet1
O.U.P.S 1-800-362-2764 |  | COMPANY ID: |  |  |  | PID NO. 111657 |  | Last Updated By: MNG
PM: |  | OUPS TICKET A027501798-00A CALL ON 10/1/20 |  |  |  | GRE-68-13.56
Utility Company | Telephone | Contact | Project Notification Notice (Emailed by City or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Sent LG&T Plans | Received Comments | Stage 2 Plans Sent | Received Comments | UTILITY NOTE SUBMITED TO CITY UTILITY COORDINATOR | Remarks
Name and Address | No. | Name
|  |  |  | Date | Date |  |  | Date |  | Date
ATT Ohio | 937-708-1026 | Alan Stutes (current) | A027501798-00A | 2020-10-01 | 2020-10-13 | 2021-08-11 | 2021-09-10 | 2022-01-13 | 2022-03-01 |  | On deployment on West Coast.
7201 Far Hills Avenue |  | as1634@att.com |  |  | 2020-10-20 | [5 empty] | Replied with a screenshot of utilities in the area.
Dayton, OH 45459 |  |  |  |  | 2020-10-20 | [5 empty] | 9/10/2021 - no easements in area, buried facilities that may be in conflict.
| 937-296-3588 (O) | Howard Laudermilk
| 937-286-7218 (C) | hl1596@att.com | [8 empty] | 3/1/2022 - Aerial cables depicted on the west side of 68 and going north on 235. Are the buried cables depicted coming out the MH and on the east side of 68?
ATT Metro/LNS | (O) 614-379-6419 | Christopher McCloskey (old) | A027501798-00A | 2020-10-01 |  | 2021-08-11 | 2022-01-05 | N/A | N/A |  | Arcadis emailed on 10/6/20 and 10/19/20 to follow up. No response was received. Phone call placed on 10/30/20. Message was left for Christopher McCloskey.
Thayer Power and Communication, LLC | (M) 614-321-2226 | chrismccloskey@thayerpc.com |  | 2020-10-06
12345 Worthington Road NW |  |  |  | 2020-10-19
Pataskala, Ohio 43062 |  | Tim LaPointe |  | 2020-10-30
|  | tl0695@att.com | [8 empty] | 1/5/2022 - No facilities in project area.
ATT Transmission - Long Distance | 216-750-0135 | Chad Harkness | A027501798-00A | 2020-10-01 | 2020-10-10 | 2021-08-11 | 2021-08-11 | N/A | N/A |  | 8/11/2022 - No facilities in project area.
7555 E. Pleasant Valley Road Suite 140 |  | chad.harkness@mcgfiber.com
Independence, OH 44131
md4145@att.com
Charter Communications (Spectrum) | 937-203-7046 | Kenneth Amato | A027501798-00A | 2020-10-01 | 2020-10-07 | 2021-08-11 | 2021-08-12 | 2022-01-13 | No comments received, responded with a question. |  | Jeff Gammon is the updated contact as of 8/11/21.
10920 Kenwood Road |  | kenneth.amato@charter.com |  |  |  |  | 2021-08-25 |  |  |  | Spectrum plant in the project area runs aerial along the east side of Rte 68.
Blue Ash, OH 45242
dl-southern-ohio-outside-plant@charter.com | (O) 937-396-7290 | Jeff Gammon
Spectrum | (M) 937-999-7597 | jeffrey.gammon@charter.com | [8 empty] | Whatever changes need to be made to accommodate for the new roundabout, Spectrum (Charter Communications) will want to continue to follow the path of DP&L.
3691 Turner Rd | (O) 937-528-5613 | James Pope
Dayton, OH 45415 | (M) 937-999-8656 | james.pope@charter.com
Dayton Power and Light | 937-554-9063 | William Ward | A027501798-00A | 2020-10-01 | 2020-10-06 | 2021-08-11 | 2021-08-11 | 2022-01-13 | 2022-02-28 |  | No underground facilties in the project area.
1900 Dryden Road |  | william.ward@aes.com |  |  | 2020-10-16 | [5 empty] | AES overhead electric along east side of US 68
Dayton, OH 45439 | [10 empty] | No AES Ohio easements
2/28/2022 - proposed relocation plan received
Greene County Water and Sewer | 937-562-7463 | Vicki Bawidamann | A027501798-00A | 2020-10-01 | 2020-10-05 | 2021-08-11 | 2021-08-12 | 2022-01-13 | 2022-01-25 |  | Water line located in project limits.
Greene County Sanitary Engineering Department |  | vbawidamann@co.greene.oh.us | [8 empty] | Possible conflict under roundabout.
Attn: Project Management
667 Dayton Xenia Road | 937-562-7461 | Marissa Raglin
Xenia, OH 45385 |  | marissa.raglin@greenecountyohio.gov
SED_PM@co.greene.oh.us
| 937-562-7448 | Tristian Mull
tristan.mull@greenecountyohio.gov
City Xenia | 937-376-7265 | Christopher Berger | A027501798-00A | 2020-10-01 | 2020-10-07 | 2021-08-11 | 2021-08-11 | 2022-01-13 | 2022-04-25 |  | One possible conflict is a 16-inch steel-encased conduit for electric service and the other is an 8-inch concrete-encased conduit for a 2.5” Force Main and additional electric conduits.
10 North Detroit Street |  | cberger@ci.xenia.oh.us
Xenia, OH 45385
4/25/2022 - No comments from the City. Email forwarded to Joe Bates at the Xenia WTP to see if he has any comments.

## Sheet2
What utilities are within the project area?
Who is the contact for each?
What conflicts exist (easements, design elements, etc.)?
Where do they need to go?
Do they require additional R/W?
What is the utility clear date (usually answered by the client or ODOT if an LPA project)?
What is the utility’s schedule to get the relocation done prior to the utility clear date?
Please send a copy of the plans when we are closer to completion, ok to put mail box in driveway if maintained during winter

## Coordination
Utility | Contact | Date | Type | Notes
ATT | Alan Stutes | 2022-02-28 | Phone | Alan is going to send over schematic layouts, he thinks the only aerial is on the west side of 235 where the road splits. He's going to start looking into the relocation plan.
Greene Co. | Tristian Mull | 2022-06-21 | Phone | Fairly certain it'd be on our end to do design work. Greene Co normally only design things as part of the CIP project plan, etc. Greene Co will approve them and offer comments.
Greene Co. | Tristian Mull | 2022-06-22 | Phone | 4.5' of cover from WL, from top of WL. Ex. cover line they assume 4.5' cover Standard Trench detail - specified amount of gravel cover when outside of roadway, and under roadway.
Greene Co. | Tristian Mull | 2022-06-22 | Phone | Flexibility with waterline clearance? 4' is okay
Looks like ours is 3' cover. Issue is __
Sanitary engineer would really like to avoid lowering it, freezing problem, 20' wouldn't be an issue since it's so short of a section.
12" of undercut stone would help the strength. Pavement depth = 15" + 12" stone
Greene Co. agrees that we do not need to lower 20" waterline.
Fire hydrant: watch valve can not move, "adj to grade heavy duty valve box". Can come straight off, required to be anchor pipe, can put a bend in it. Require anchor pipe between valve & hydrant, one pipe can be non-anchor pipe. Add hydrant relocate detail to plans.
Standard 15099
ATT | Alan Stutes | 2022-11-23 | Email | Received placing plan.