SCOPE NARRATIVE

Project HAM SR 126 VAR

PID 112991

General Information

This Narrative Document contains different Scope areas for the above project.  These topics include:

MOT, Structures, and a General Information section.  The General Information section contains:  The statement that certified traffic was requested, the list of existing plans listed on ODOT’s FTP site, and a project map.

Structure Scope

HAM-126-1406 (SFN 3104923) which carries EB SR 126 over Mill Creek.

- Zone paint structural steel with per 514 OZEU specifications. Color shall be light green, federal color FS-595C-14277 for a distance of 10 feet from the east expansion joint.

- Replace east abutment bearings with elastomeric bearings.

- Replace expansion joint seal at both abutments. (armor shall remain).

- Patch deteriorated portions of concrete wearing surface on the deck, abutment backwall, and approach slab per Proposal Note 512, Type B. Request Structures Planning Department to provide locations for repair during plan development.

- Remove birds nest attached to bridge that interfere with work prior to restricted nesting season.

- Clear and grub with in 20 feet of the structure.

- Restrict painting/scaffolding for this structure to summer months as floodwater reaches beams regularly.

- Remove smashed portion of 6” CMP bridge drainage that outlets through the slope protection leaving a coped end. Attach an animal guard just within the remaining full section of the CMP pipe.

PIP Photos: \\D08FS100\archives\structures\bridges\23 photos\HAM\SR126\1406\PIP 05-16-23

HAM-126-1530 (SFN 3104990) which carries Galbraith Rd and sidewalk over SR 126

- Paint structural steel with per 514 OZEU specifications. Color shall be light green, federal color FS-595C-14277.

- Replace abutment bearings with elastomeric bearings.

- Patch deteriorated portions of concrete substructure and concrete barrier with 519 patching. For areas larger than 5 sq feet, include anode per SS 844. On deteriorated pier columns areas, wrap the circumference of the pier column to 2 feet above the repair area (unless surface is obstructed by barrier, cap, etc.) with fiber reinforced polymer (FRP). Additionally, wrap the top 2 feet of all single pier columns. Request Structures Planning Department to repair locations for repair during plan development.

- Seal concrete surfaces on the superstructure and abutments with Epoxy Urethane Sealer.

- Clear and grub with in 20 feet of the structure.

- There are utilities on this structure. They appear to be in PVC conduits. Coordinate as necessary.

PIP Photos: \\D08FS100\archives\structures\bridges\23 photos\HAM\SR126\1530\PIP 05-16-23

HAM-126-1543 (SFN 3105008) which carries a ramp from westbound SR 126 to Galbraith Rd over SR 126

- Paint structural steel with per 514 OZEU specifications. Color shall be light green, federal color FS-595C-14277.

- Replace abutment bearings with elastomeric bearings.

- Patch deteriorated portions of concrete substructure with 519 patching. For areas larger than 5 sq feet, include anode per SS 844. On deteriorated pier columns areas, wrap the circumference of the pier column to 2 feet above the repair area (unless surface is obstructed by barrier, cap, etc.) with fiber reinforced polymer (FRP).  Request Structures Planning Department to repair locations for repair during plan development.

- Seal concrete surfaces on the superstructure and abutments with Epoxy Urethane Sealer.

- Clear and grub with in 20 feet of the structure. Include an as per plan note to include the removal of vines from the structure.

PIP Photos: \\D08FS100\archives\structures\bridges\23 photos\HAM\SR126\1543\PIP 05-16-23

HAM-126-1555 (SFN 3105024) which carries Knollcrest Drive over SR 126

- Paint structural steel with per 514 OZEU specifications. Color shall be light green, federal color FS-595C-14277.

- Replace abutment bearings with elastomeric bearings.

- Patch deteriorated portions of concrete substructure with 519 patching. For areas larger than 5 sq feet, include anode per SS 844. On deteriorated pier columns areas, wrap the circumference of the pier column to 2 feet above the repair area (unless surface is obstructed by barrier, cap, etc.) with fiber reinforced polymer (FRP).  Request Structures Planning Department to repair locations for repair during plan development.

- Seal concrete surfaces on the superstructure and abutments with Epoxy Urethane Sealer.

- Clear and grub with in 20 feet of the structure.

- Plug open utility conduits with grout.

PIP Photos: \\D08FS100\archives\structures\bridges\23 photos\HAM\SR126\1555\PIP 05-16-23

HAM-126-1818 (SFN 3105083) which carries Plainfield Rd over SR 126

- Paint structural steel with per 514 OZEU specifications. Color shall be light green, federal color FS-595C-14277. Light blue, federal color FS-595C-15526 at the request of the City of Blue Ash (Gordon Perry, 6-26-23).

- Replace portions of the barrier that are deteriorated on both sides with full thickness concrete. Patch deteriorated areas of the concrete barrier that are only deteriorated on one side, and deteriorated portions of the substructure with 519 patching. For areas larger than 5 sq feet, include anode per SS 844. On deteriorated pier columns areas, wrap the circumference of the pier column to 2 feet above the repair area (unless surface is obstructed by barrier, cap, etc.) with fiber reinforced polymer (FRP). Request Structures Planning Department to repair locations for repair during plan development.

- Protect pier columns below with concrete barrier if columns are within 5 feet of the curb.

- Seal concrete surfaces on the superstructure and abutments with Epoxy Urethane Sealer.

- Replace the damage sidewalk around the north east wingwall.

- Replace sections of damaged aluminum railing on the east side of the bridge. Replace missing bolts and washers for the anchor bolts for the railing on the northeast wingwall.

- Clear and grub within 20 feet of the structure, except that the mulched/landscaped areas shall not be disturbed.

PIP Photos: \\D08FS100\archives\structures\bridges\23 photos\HAM\SR126\1818\PIP 05-16-23

Maintenance of Traffic

TBD- Scott Kraus to provide.

- Include the following note in the plans:

“Any work (falsework, traffic protection, containment, etc.) over live traffic by the contractor that reduces the existing vertical clearance is prohibited unless 30 days advanced notice is provided with new proposed vertical clearances AND the contractor verifies and documents the actual vertical clearance before allowing traffic underneath. The existing vertical clearance are provided in the table below. The vertical clearance over live traffic cannot be lowered to less than 15’-0” under any circumstances. Lowering the vertical clearance during construction is considered the Contractor's Means and Methods of accomplishing the work, and therefore the State is not responsible for any damage from vehicular impacts that may result as per 107.10.”

Design Designations

|  |  | HAM-126-1406 |  | HAM-126-1530 |  | HAM-126-1543 |
| --- | --- | --- | --- | --- | --- | --- |
| Functional Classification |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |
| Design Functional Classification |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |
| Opening Year ADT (2026) |  | 13,500 |  | 39,500 |  | 39,500 |
| Design Year ADT (2038) |  | 15,000 |  | 43,500 |  | 43,500 |
| Design Hourly Volume |  | 2,000 |  | 4,400 |  | 4,400 |
| Direction Distribution |  | 0.56 |  | 0.53 |  | 0.53 |
| Trucks (24 Hour B&C) |  | 2% |  | 4% |  | 4% |
| Posted Speed (mph) |  | 60 |  | 60 |  | 55 |
| Design Speed (mph) |  | 65 |  | 65 |  | 60 |

|  |  | HAM-126-1555 |  | HAM-126-1818 |
| --- | --- | --- | --- | --- |
| Functional Classification |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |
| Design Functional Classification |  | 02 Other Freeway (Urban) |  | 02 Other Freeway (Urban) |
| Opening Year ADT (2026) |  | 45,500 |  | 46,500 |
| Design Year ADT (2038) |  | 50,500 |  | 48,500 |
| Design Hourly Volume |  | 7,100 |  | 5,800 |
| Direction Distribution |  | 0.56 |  | 0.57 |
| Trucks (24 Hour B&C) |  | 4% |  | 5% |
| Posted Speed (mph) |  | 55 |  | 55 |
| Design Speed (mph) |  | 60 |  | 60 |

General Information

Misc.:

- Existing plans

- No plan splits needed, 80% 4PF7/ 20% 4PS7, district preservation funds (NHS).

|  | Arch No | Name | Year | PID | Description |
| --- | --- | --- | --- | --- | --- |
| 1 | 08C1532 | HAM-126-13.00 | 1985 |  | Grade Separation of 126 into a limited access highway |
| 2 | 08C4534 | HAM-126-13.73/14.06/14.34 | 2018 | 98533 | Bridge painting w/ minor maintenance |
| 3 | 08C1083 | HAM-126-23.17 | 1999 | 7977 | 126 improvements, including plainfield rd bridge, 1818 |
| 4 | 08C1960 | HAM CR 453B | 1963 |  | Cross county grade separation, including plainfield rd bridge, 1818 |
| 5 | 08C2439 | Plainfield Rd Improvements | 1991 |  | Plainfield Rd bridge improvements, 1818 |
| 6 | 08C3075 | D08-BM-FY2012 | 2012 | 77789 | Bridge maintenance of several bridges, including plainfield Rd bridge, 1818 |

Photos are available at:

1406 inspection: \\D08FS100\archives\structures\bridges\21 photos\HAM\SR126\1406

1530 inspection: \\D08FS100\archives\structures\bridges\21 photos\HAM\SR126\1530

1543 inspection: \\D08FS100\archives\structures\bridges\21 photos\HAM\SR126\1543

1555 inspection: \\D08FS100\archives\structures\bridges\21 photos\HAM\SR126\1555

1818 inspection: \\D08FS100\archives\structures\bridges\21 photos\HAM\SR126\1818

Project Map

HAM-126-1406

HAM-126-1530/1543/1555

HAM-126-1818