## Sheet1
Seat Wall | Station to Station |  |  | Utility | Depth of Cover | Identified Issues | Conflict | Solution /Notes
UTILITIES COORDINATED WITH SEAT WALLS
L1 | 557+57.14 | TO | 557+78.47 | 4"x10" CBT FIBER CONC. ENCASED | 3.69 | Under proposed work | None | Facilities not affected by the proposed work.
| 557+74.11 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
L2 | 560+70.34 | TO | 560+96.34 | 12" RCP STORM LINE | 3.9 | Under proposed work | None | Facilities not affected by the proposed work.
| 560+71.09 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
L3 | 562+18.14 | TO | 562+26.80 | 24" RCP STORM LINE | 6.41 | Under proposed work | None | Facilities not affected by the proposed work.
| 562+20.55 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
L4 | 562+64.00 | TO | 562+86.00 | 24" RCP STORM LINE | 7.19 | Under proposed work | None | Facilities not affected by the proposed work.
| 562+72.73 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
| 562+68.95 |  |  | ALTA POWER POLE | N/A | Pole near work | None | Facilities not affected by the proposed work.
L5 | 563+83.33 | TO | 563+99.00 | 24" RCP STORM LINE | 8.09 | Under proposed work | None | Facilities not affected by the proposed work.
| 563+83.33 | TO | 563+99.00 | 4"x10" CBT FIBER CONC. ENCASED | 2.83 | Under proposed work | None | Facilities not affected by the proposed work.
| 563+90.84 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
| 563+80.12 |  |  | ALTA POWER POLE | N/A | Pole near work | None | Facilities not affected by the proposed work.
L6 | 564+15.33 | TO | 564+31.00 | 24" RCP STORM LINE | 8.08 | Under proposed work | None | Facilities not affected by the proposed work.
| 564+15.33 | TO | 564+31.00 | 4"x10" CBT FIBER CONC. ENCASED | 3.03 | Near proposed work | None | Facilities not affected by the proposed work.
L7 | 564+44.50 | TO | 564+53.70 | 4"x10" CBT FIBER CONC. ENCASED | 0.93 | Near proposed work | None | Facilities not affected by the proposed work.
| 564+55.81 |  |  | DUKE POWER POLE | n/a | Pole near work | Nond | Duke will replace pole with a deeper pole.
L8 | n/a |  | n/a | n/a | n/a | n/a | n/a | No utilities in area of work.
L9 | 565+40.21 |  |  | MCI TELECOM | 3 | Near proposed work | None | MCI approved sleeving utility under wall.
L10 | n/a |  | n/a | n/a | n/a | n/a | n/a | No utilities in area of work.
L11 | 567+50.69 | TO | 567+62.69 | 24" RCP STORM LINE | 8.66 | Under proposed work | None | Facilities not affected by the proposed work.
| 567+50.53 |  |  | GAS LATERAL | 3 | Under proposed work | None | Facilities not affected by the proposed work.
L12 | 568+00.28 | TO | 567+10.28 | 24" RCP STORM LINE | 7.87 | Under proposed work | None | Facilities not affected by the proposed work.
| 568+12.85 |  |  | WATER LATERAL | 3 | Under proposed work | None | Facilities not affected by the proposed work.
| 568+14.40 |  |  | DUKE POWER POLE | N/A | Pole near work | Duke Special Note | Protect Pole to Remain - See utility notes.
L13 | 568+38.04 | TO | 568+46.71 | 24" RCP STORM LINE | 7.27 | Under proposed work | None | Facilities not affected by the proposed work.
| 568+47.18 |  |  | GAS LATERAL | 3 | Under proposed work | None | Facilities not affected by the proposed work.
L14 | 568+52.74 | TO | 568+61.41 | 24" RCP STORM LINE | 6.99 | Under proposed work | None | Facilities not affected by the proposed work.
| 568+63.31 |  |  | WATER LATERAL | 3 | Under proposed work | None | Facilities not affected by the proposed work.
R1 | 558+14.57 | TO | 558+30.80 | 2" VERIZON FIBER OPTIC CABLE | 5.99 | Under proposed work | None | Facilities not affected by the proposed work.
| 558+19.99 |  |  | DUKE POWER POLE | N/A | Near proposed work | Pole Near Wall | Duke will replace pole with a deeper pole.
R2 | 558+51.68 | TO | 558+74.35 | 2" VERIZON FIBER OPTIC CABLE | 6.05 | Under proposed work | None | Facilities not affected by the proposed work.
| 558+50.10 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
| 558+52.37 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
R3 | 560+01.85 | TO | 560+29.85 | 2" VERIZON FIBER OPTIC CABLE | 3.64 | Under proposed work | None | Facilities not affected by the proposed work.
| 560+25.74 |  |  | SANITARY LATERAL | 7 | Under proposed work | None | Facilities not affected by the proposed work.
R4 | 560+56.45 | TO | 560+84.45 | 2" VERIZON FIBER OPTIC CABLE | 3.01 | Under proposed work | None | Facilities not affected by the proposed work.
| 560+60.81 |  |  | GAS LATERAL | 3 | Under proposed work | Depth | Duke approved sleeving utility under wall.
| 560+73.83 |  |  | EXISTING 1" COPPER WATER SERVICE LINE | 3 | Under proposed work | Depth | GWCC approved relocation of this line. see below.
| 560+75.83 |  |  | NEW 1" COPPER SERVICE LINE | 4 | Under proposed work | None | GWCC approved new service line in this location.
| 560+79.08 |  |  | DUKE POWER POLE | N/A | Pole near work | Pole Near Wall | Duke will replace pole with a deeper pole.
R5 | 561+55.59 |  |  | GAS LATERAL | 3 | Under proposed work | Depth | Duke approved sleeving utility under wall.
R6 | 562+03.49 |  |  | NEW 1" COPPER SERVICE LINE | 3 | Under proposed work | None | GWCC approved new service line in this location.
| 562+13.49 |  |  | EXISTING 1" COPPER WATER SERVICE LINE | 3 | Under proposed work | Depth | GWCC approved relocation of this line. see above.
| 562+21.62 |  |  | DUKE POWER POLE | N/A | Pole near work | Pole Near Wall | Duke will replace pole with a deeper pole.
R7 | n/a |  | n/a | n/a | n/a | n/a | n/a | No utilities in area of work.
R8 | n/a |  | n/a | n/a | n/a | n/a | n/a | No utilities in area of work.
R9 | 571+71.71 | TO | 571+91.71 | 2" VERIZON FIBER OPTIC CABLE | 3 | Under proposed work | None | Facilities not affected by the proposed work.
R10 | 572+12.08 | TO | 572+30.45 | 2" VERIZON FIBER OPTIC CABLE | 3 | Under proposed work | None | Facilities not affected by the proposed work.
R11 | 572+18.17 |  |  | DUKE POWER POLE | N/A | Pole near work | Pole Near Wall | Duke will replace pole with a deeper pole.
UTILITY COORDINATION - approved by respective utility
Callout | Station to Station |  |  | Utility | Depth | Improvement | Conflict | Solution /Notes
R1 | 55720.74 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R2 | 55747.36 | TO | 55751.91 | GCWW | 0 | New Pavement | None | VALVE BOX AND SERVICE BOX ADJUSTED TO GRADE
R3 | 55795.89 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R4 | 55798.7 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R33 | 55807.23 |  |  | GCWW | 0 | New Pavement | None | MH ADJ TO GRADE
R46 | 55819.99 |  |  | Duke Electric | 0 | New Pavement | None | REPLACE WOOD POLE
R5 | 55831.38 |  |  | GCWW | 0 | New Pavement | None | FIRE HYDRANT ADJ TO GRADE
R6 | 55853.95 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R7 | 56009.02 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R8 | 56051.99 |  |  | Duke Gas | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R9 | 56058.91 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R34 | 56071.39 |  |  | Duke Electric | 0 | New Pavement | None | PULL BOX ADJ TO GRADE
R47 | 56079.08 |  |  | Duke Electric | 0 | New Pavement | None | REPLACE WOOD POLE
R10 | 56099.47 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R11 | 56150.41 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R12 | 56208.97 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R35 | 56215.71 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX REMOVED
R13 | 56219.89 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R14 | 56227.7 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R15 | 56249.58 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R48 | 56221.92 |  |  | Duke Electric | 0 | New Pavement | None | REPLACE WOOD POLE
R16 | 56332.7 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R17 | 563+39.02 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R18 | 56448.54 |  |  | Cincinnati Bell | 0 | New Pavement | None | MH ADJ TO GRADE
R49 | 56455.81 |  |  | Duke Electric | 0 | New Pavement | None | REPLACE WOOD POLE
R19 | 56534.88 |  |  | GCWW | 0 | New Pavement | None | FIRE HYDRANT ADJ TO GRADE
R20 | 56609.93 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R21 | 56645.86 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R22 | 56779.33 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R36 | 56809.57 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R37 | 56820.71 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R23 | 568+47.60 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R24 | 56928.08 |  |  | GCWW | 0 | New Pavement | None | FIRE HYDRANT ADJ TO GRADE
R25 | 56930.63 |  |  | Duke Valve | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R26 | 56965.54 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
D1 | 57099.94 |  |  | SMU | 0 | New CB Required | Frame/Grate | REPLACE CURB INLET WITH DRIVEWAY FRAME/GRATE
R28 | 57133.13 |  |  | GCWW | 0 | New Pavement | None | VALVE BOX ADJUSTED TO GRADE
R29 | 57149.41 |  |  | MSDGC | 0 | New Pavement | None | MH ADJ TO GRADE
R30 | 57156.25 |  |  | Duke Electric | 0 | New Pavement | None | SERVICE BOX ADJ TO GRADE
R50 | 57218.17 |  |  | Duke Electric | 0 | New Pavement | None | REPLACE WOOD POLE
R31 | 57259.88 |  |  | Duke Electric | 0 | New Pavement | None | SERVICE BOX ADJ TO GRADE
R32 | 57261.28 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R38 | 56966.51 |  |  | Duke Electric | 0 | New Pavement | None | PULL BOX ADJ TO GRADE
R39 | 56986.55 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R40 | 57000.25 |  |  | Duke Gas | 0 | New Pavement | None | GAS VALVE BOX ADJ TO GRADE
R41 | 57019.33 |  |  | MSDGC | 0 | New Pavement | None | MH ADJ TO GRADE
R42 | 57091.43 |  |  | MSDGC | 0 | New Pavement | None | MH ADJ TO GRADE
R43 | 57097.56 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R44 | 57205.41 |  |  | SMU | 0 | New Pavement | None | MH ADJ TO GRADE
R45 | 57221.84 |  |  | Duke Electric | 0 | New Pavement | None | PULL BOX ADJ TO GRADE