## Phase 2
JOB | Quantity | 114497 LMST-Columbia Township |  | Date | [5 empty] | Survey | Field Surv | 8 HR | TOTAL | 40 HR | FEE GUIDE
TASK# |  | TASK DESCRIPTION | NARRATIVE | Need | DURHAM | RADER | KLEINER | ATCHLEY | McNeely | Manager | M-HRS | C-DAY | HOURS | WEEK
0
2.3.A.a.1 |  | Type "A" Project Control and Benchmarks | Establish Type "A" Project Control based on Static GPS methods and establish benchmarks using differential leveling by holding one of the GPS elevations as the controlling benchmark | [7 empty] | 0 | 0 |  | 0 | 40 / MON
2.3.A.a.2 |  | Type "B" Project Control and Benchmarks | Check ODOT provided control points, densify control network using VRS GPS methods and conventional survey traverses. Establish benchmarks as needed by differential leveling. Assume 1500 LF of survey traverse |  | 1 | 5 | 3 |  |  |  | 20 | 1.25 | 29 | 0.125 | 20 / MON
2.3.A.b.1 |  | Monumentation Recovery - Ex. C/L & R/W | Research- HAM-50 RW plans, adjacent subdivision and condominium plats. Make a thorough search of monuments, analyze evidence of right-of-way lines |  | 1 | 6 |  |  | 7 |  | 16 | 1 | 30 | 0.15 | 50 / MILE
2.3.A.b.2 |  | Monumentation Recovery - Property Lines | Research- deeds, existing surveys, and easements. Make a thorough search of monuments, analyze evidence of property lines |  | 1 | 5 |  |  | 5 |  | 24 | 1.5 | 35 | 0.125 | 20 / OWNER
2.3.A.c.1 |  | Base Mapping - No R/W Project | Two (2) check sections and two (2) white stripe profiles at 10 foot intervals (300 feet). Four (4) additional check sections through the wooded area along the north side of US 50. Locate all visible utilities and drainage features, get invert elevations and make structure sketches. Develop traffic protection plan - assume using a 3 person crew for this task |  | 3 | 4 | 12 | 4 |  |  | 78 | 3.25 | 101 | 0.1 | 22 / 0.1 MILE
2.3.A.c.2 |  | Base Mapping - R/W Project | Survey planimetric and terrain topographic features within the following limits _______ Additionally, any topographic features needed to prepare RW Plans. DTM, and base map deliverables. Geotech boring locations entered in a spreadsheet identifying the horizontal and vertical position | [7 empty] | 0 | 0 |  | 0 | 26 / 0.1 MILE
2.3.A.d |  | Drainage Survey (stream sections) | Stream sections made for hydraulic analysis, including DTM files | [7 empty] | 0 | 0 |  | 0 | 16 / 0.1 MILE
2.3.A.e.1 |  | Bridge Survey for Complete Bridge Replacement | Planimetric location of the basic bridge features. Separate DTM to define roadway surface. | [7 empty] | 0 | 0 |  | 0 | 30 / BRIDGE
2.3.A.e.2 |  | Bridge Survey for Rehabilitation over road | Locate basic planimetric features and separate DTM to define roadway surface. Locate detailed bridge features including beam seats, beam size, beam profile, piers. ID key elevations for bridge rehab. | [7 empty] | 0 | 0 |  | 0 | 40 / BRIDGE
2.3.A.e.3 |  | Bridge Survey for Rehabilitation over water course | Locate basic planimetric features and separate DTM to define roadway surface. Locate detailed bridge features including beam seats, beam size, beam profile, piers, and bridge rail. ID key elevations for bridge rehab. | [7 empty] | 0 | 0 |  | 0 | 48 / BRIDGE
2.3.A.f |  | Establish Property Lines, tax id & ownerships on base map | Boundary line resolution |  |  | 16 |  |  | 5 |  | * | * | 21 | 0.4 | 5 / OWNER
2.3.A.g | 10 | Property Owner Notification | Research tax records, spreadsheet of owner mailing information, prepare & mail letter. Assume 10 owners |  |  | 1 | 4 | 4 |  |  | * | * | 9 | 0.025 | 2 / OWNER
2.3.G.a |  | Utility coordination and documentation | OUPS request, and documentation |  |  | 1 |  |  | 3 |  | * | * | 4
0
|  | TOTAL FIELD SURVEY | [8 empty] | 138 | 7 | 229 | 0
[11 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
2.3.H.e |  | Identify potential Total Takes | [8 empty] | * | * |  | 0
2.3.H.f |  | Railroad Coordination | [8 empty] | * | *
2.4.B |  | Right of Way Cost | assume 7 parcels, property line locations to be supplemented with CAGIS property lines |  |  | 2 | 8 |  |  |  | * | * | 10 | 0.05
2.6.A |  | Public Involvement Meeting | [8 empty] | * | * |  | 0
3.1.K |  | Determine RW Encroachments | [8 empty] | * | * |  | 0
3.1.L |  | Determine potential RW from R.R. | [8 empty] | * | * |  | 0
3.3.J.a |  | Utility base map | [8 empty] | * | *
[11 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
3.4.A |  | Conceptual RW Plan Review | [8 empty] | * | * |  | 0 | 4 / SHT
3.4.B.a |  | Legend Sheet | [8 empty] | * | * |  | 0 | 10 / SHT
3.4.B.b |  | Centerline Survey Plat | [8 empty] | * | * |  | 0 | 20 / SHT
3.4.B.c |  | Property Map | [8 empty] | * | * |  | 0 | 26 / SHT
3.4.B.d |  | Summary of Additional RW | [8 empty] | * | * |  | 0 | 3 / OWNER
3.4.B.e |  | R/W Detail Sheets | [8 empty] | * | * |  | 0 | 32 / SHT
3.4.B.g |  | Legal Descriptions & Closure Calculations | [8 empty] | * | * |  | 0 | 3.0 / LEGAL
|  | Legal Exhibits | including County Approval | [7 empty] | * | * |  | 0
3.4.B.h |  | Right-of-Way Acquisition Estimate | [8 empty] | * | * |  | 0
3.4.B.i |  | Field Review - Preliminary Submittal | [8 empty] | * | * |  | 0 | 3 / SHT
|  | Final RW Plan | [8 empty] | * | * |  | 0
3.4.C.a |  | Final Plan - address comments | [8 empty] | * | * |  | 0 | 2.5 / SHT
3.4.C.b |  | Field Review & Verify Ownership | [8 empty] | * | * |  | 0 | 1.5 / SHT
3.4.C.c |  | Record Centerline Plat and all appropriate docum. | Consultant required to do this | [7 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
3.4.C.d |  | Set Lath during acquistion (if authorized) | [8 empty] | 0 | 0 |  | 0
3.4.C.d |  | Set R/W Pins after acquistion(when authorized) | [8 empty] | 0 | 0 |  | 0 | 0.33 / PIN
4.4.A |  | Final Plan Package (R/W Portion) | [8 empty] | * | * |  | 0
TOTALS |  | Submitted 7/21/2021 |  |  | 6 | 40 | 27 | 8 | 20 |  | 138 | 7 | 239 | 0.975
Direct Cost
2.3.A.c.1 |  | Milage - 7 trip @ 30 miles @ 0.45 = | 95
|  | Survey Stakes | 20