## Phase 2
JOB | Quantity | 114496 LMST-Spring Hill |  | Date | [5 empty] | Survey | Field Surv | HR | TOTAL | 40 HR | FEE GUIDE
TASK# |  | TASK DESCRIPTION | NARRATIVE | Need | DURHAM | RADER | KLEINER | ATCHLEY | McNeely | Manager | M-HRS | C-DAY | HOURS | WEEK
0
2.3.A.a.1 |  | Type "A" Project Control and Benchmarks | Establish Type "A" Project Control based on Static GPS methods and establish benchmarks using differential leveling by holding one of the GPS elevations as the controlling benchmark | [7 empty] | 0 | 0 |  | 0 | 40 / MON
2.3.A.a.2 |  | Type "B" Project Control and Benchmarks | Check ODOT provided control points, densify control network using VRS GPS methods and conventional survey traverses. Establish benchmarks as needed by differential leveling. Assume 4000 LF of survey traverse, of which 2000 LF is through wooded area, including the labor to cut lines. |  | 1 | 4 | 3 |  |  |  | 40 | 2.5 | 48 | 0.1 | 20 / MON
2.3.A.b.1 |  | Monumentation Recovery - Ex. C/L & R/W | Research- HAM-50 RW plans, and Newton Road plans, and old PCC & STL Railroad Valuation Map. Make a thorough search of monuments, analyze evidence of right-of-way lines |  | 1 | 5 | 6 |  | 8 |  | 12 | 0.75 | 32 | 0.125 | 50 / MILE
2.3.A.b.2 |  | Monumentation Recovery - Property Lines | Research- deeds, plats, existing surveys, and easements. Make a thorough search of monuments, analyze evidence of property lines |  | 1 | 7 |  |  | 8 |  | 28 | 1.75 | 44 | 0.175 | 20 / OWNER
2.3.A.c.1 |  | Base Mapping - No R/W Project | Two (2) check sections at tie in area near the intersection of US 50 and Srping Hill Road and two (2) check sections at tie in area at the western terminus of the LMST. Locate all visible utilities and drainage features, get invert elevations and make structure sketches. We assume 2000 LF to be in the wooded area, requiring conventional cross sections. Hours have been included to locate the Ordinary High Water mark along the Little Miami River. |  | 4 | 4 | 8 | 4 |  |  | 128 | 8 | 148 | 0.1 | 22 / 0.1 MILE
2.3.A.c.2 |  | Base Mapping - R/W Project | Survey planimetric and terrain topographic features within the following limits _______ Additionally, any topographic features needed to prepare RW Plans. DTM, and base map deliverables. Geotech boring locations entered in a spreadsheet identifying the horizontal and vertical position | [7 empty] | 0 | 0 |  | 0 | 26 / 0.1 MILE
2.3.A.d |  | Drainage Survey (stream sections) | Stream sections made for hydraulic analysis, including DTM files | [7 empty] | 0 | 0 |  | 0 | 16 / 0.1 MILE
2.3.A.e.1 |  | Bridge Survey for Complete Bridge Replacement | Planimetric location of the basic bridge features. Separate DTM to define roadway surface. | [7 empty] | 0 | 0 |  | 0 | 30 / BRIDGE
2.3.A.e.2 |  | Bridge Survey for Rehabilitation over road | Locate basic planimetric features and separate DTM to define roadway surface. Locate detailed bridge features including beam seats, beam size, beam profile, piers. ID key elevations for bridge rehab. | [7 empty] | 0 | 0 |  | 0 | 40 / BRIDGE
2.3.A.e.3 |  | Bridge Survey for Rehabilitation over water course | Locate basic planimetric features and separate DTM to define roadway surface. Locate detailed bridge features including beam seats, beam size, beam profile, piers, and bridge rail. ID key elevations for bridge rehab. | [7 empty] | 0 | 0 |  | 0 | 48 / BRIDGE
2.3.A.f |  | Establish Property Lines, tax id & ownerships on base map | Boundary line resolution along Hamilton County Park lands. Preliminary research shows a possible ownership gap south of Auditor Parcel 520-0112-0169 |  | 1 | 23 |  | 4 |  |  | * | * | 28 | 0.575 | 5 / OWNER
2.3.A.g | 12 | Property Owner Notification | Research tax records, spreadsheet of owner mailing information, prepare & mail letter. Assume 12 owners |  |  | 3 | 6 | 2 |  |  | * | * | 11 | 0.075 | 2 / OWNER
2.3.G.a |  | Utility coordination and documentation | OUPS request, and documentation |  |  | 3 | 3 |  |  |  | * | * | 6
0
|  | TOTAL FIELD SURVEY | [8 empty] | 208 | 13 | 317 | 0
[11 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
2.3.H.e |  | Identify potential Total Takes | [8 empty] | * | * |  | 0
2.3.H.f |  | Railroad Coordination | [8 empty] | * | *
2.4.B |  | Right of Way Cost | assume 3 parcels, property line locations to be supplemented with CAGIS property lines |  |  | 2 | 3 |  |  |  | * | * | 5 | 0.05
2.6.A |  | Public Involvement Meeting | [8 empty] | * | * |  | 0
3.1.K |  | Determine RW Encroachments | [8 empty] | * | * |  | 0
3.1.L |  | Determine potential RW from R.R. | [8 empty] | * | * |  | 0
3.3.J.a |  | Utility base map | [8 empty] | * | *
[11 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
3.4.A |  | Conceptual RW Plan Review | [8 empty] | * | * |  | 0 | 4 / SHT
3.4.B.a |  | Legend Sheet | [8 empty] | * | * |  | 0 | 10 / SHT
3.4.B.b |  | Centerline Survey Plat | [8 empty] | * | * |  | 0 | 20 / SHT
3.4.B.c |  | Property Map | [8 empty] | * | * |  | 0 | 26 / SHT
3.4.B.d |  | Summary of Additional RW | [8 empty] | * | * |  | 0 | 3 / OWNER
3.4.B.e |  | R/W Detail Sheets | [8 empty] | * | * |  | 0 | 32 / SHT
3.4.B.g |  | Legal Descriptions & Closure Calculations | [8 empty] | * | * |  | 0 | 3.0 / LEGAL
|  | Legal Exhibits | including County Approval | [7 empty] | * | * |  | 0
3.4.B.h |  | Right-of-Way Acquisition Estimate | [8 empty] | * | * |  | 0
3.4.B.i |  | Field Review - Preliminary Submittal | [8 empty] | * | * |  | 0 | 3 / SHT
|  | Final RW Plan | [8 empty] | * | * |  | 0
3.4.C.a |  | Final Plan - address comments | [8 empty] | * | * |  | 0 | 2.5 / SHT
3.4.C.b |  | Field Review & Verify Ownership | [8 empty] | * | * |  | 0 | 1.5 / SHT
3.4.C.c |  | Record Centerline Plat and all appropriate docum. | Consultant required to do this | [7 empty] | * | * |  | 0
[11 empty] | * | * |  | 0
3.4.C.d |  | Set Lath during acquistion (if authorized) | [8 empty] | 0 | 0 |  | 0
3.4.C.d |  | Set R/W Pins after acquistion(when authorized) | [8 empty] | 0 | 0 |  | 0 | 0.33 / PIN
4.4.A |  | Final Plan Package (R/W Portion) | [8 empty] | * | * |  | 0
TOTALS |  | Submitted 7/21/2021 |  |  | 8 | 51 | 29 | 10 | 16 |  | 208 | 13 | 322 | 1.2
Direct Cost
2.3.A.c.1 |  | Milage - 13 trips @ 30 miles @ 0.45 = | 175
|  | Survey Stakes | 25