## Utility Log
O.U.P.S 1-800-362-2764 |  | COMPANY ID: |  |  |  | PROJECT: HAM-COLUMBIA CONNECTOR |  | PID: 114496 |  |  |  | Last Updated By: | Last Updated Date:
Project Managers: |  | TICKETS 4/22/2022 : A211201429-00A, A211201438-00A, A211201451-00A |  |  |  | Project files: 114496_BU001 | [5 empty] | Qiaochu Chen | 2025-07-17 | Project Limits:
Utility Company | Telephone | Contact | Project Notification Notice (Emailed by ODOT or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Sent Stage 1 Plans | Received Comments | Sent Stage 2 Plans | Received Comments | Sent Stage 3 Plans | Received Comments | FINAL TRACINGS SENT | Received Comments | Remarks | UG or OH
Name and Address | No. | Name
Duke Energy | (513) 508-9609 | Shane Erhart |  | 2022-04-22 |  | 2024-01-19 |  | 2024-06-28 |  | 2025-03-17 | 2025-03-27 |  |  | 3/27/2025 - Shane responded stating concern with the utility poles on the south side of US 50. The utility poles being in the middle of our proposed path. Requested current DGN files to plan relocation. 5/23/2025 - Shane responded requesting the design files for the path and the wall on segment B. | OH
Electric Distribution | [10 empty] | 2025-05-23
2010 Dana Avenue
Cincinnati, Oh 45207
Duke Energy | (513) 659-3513 | Tim Meyer |  | 2022-04-22 |  | 2024-01-19 |  | 2024-06-28 |  | 2025-03-17 | 2025-03-17 |  |  | 9/12/2024 - Tim responded with a screenshot providing the location of their 69kV OH transmission line and poles which falls into the project area, which matches what we have in current plan 3/17/2025 - Tim responded stating he does not anticipate any impacts. | OH
Electric Transmission | [7 empty] | 2024-08-26 | 2024-09-12
139 East Fourth St, 4th Floor Annex
Cincinnati, Oh 45202
Duke Energy | (513) 384-4731 | Andy McNichols |  | 2022-04-22 |  | 2024-01-19 |  | 2024-06-28 |  | 2025-03-17 | 2025-04-28 |  |  | 9/9/2024 - Received an 'External Map Request Form' which Stantec needs to fill out and submit to obtain their UG gasline location maps (2 locations of lateral crossing, 1 gas valve on surface of SUP). 10/22/2024 - Brian responded with no concerns about the 3 potential concerns Stantec identified, and brought up another concern about a 4'' gas line laterally crossing the prop. SUP at STA.44+00 to STA.45+00 range (at a prop. drive). 11/25/2024 - Brian provided the accurate location of the 4" gas from their field survey. Stantec has updated the plan to reflect it, and will send out the plan to Duke in stage 3. 4/28/2025 - Brian responded with some concern of the gas line crossing the path at sta. 48+00. Wants CAD files for test hole locations. | UG
Gas | [7 empty] | 2024-09-03 | 2024-09-09
139 East Fouth St, Room 460A |  | Brian Hollmann | [6 empty] | 2024-10-22
Cincinnati, Oh 45202 | [8 empty] | 2024-11-25
MSD | (513) 557-7188 | Rob Franklin |  | 2022-04-22 |  | 2024-01-19 | 2024-01-23 | 2024-06-28 |  | 2025-03-17 | 2025-03-18 |  |  | 1/23/2024 - Rob responded with some markups and additional sanitary plan sheets. 8/26/2024 - Rob responded with a request of adding an existing line north of the project from sta. 10 to sta.13 (approx.), which is outside constr. Limit. Stantec has added that to the plan and will be reflected in stage 3 3/18/2025 - Rob responded with a letter of acceptance. | UG
Santiary | [7 empty] | 2024-08-23 | 2024-08-26
1600 Gest Street
Cincinnati, Oh 45204
Charter Communications | (513) 386-5499 | Kent Rieger |  | 2022-04-22 |  | 2024-01-19 |  | 2024-06-28 |  | 2025-03-17 |  |  |  | Never got response back. Stantec needs to send emails to confirm the locations, depth and size of the telecom utilities that belongs to Charter Communication.
Cable
11252 Cornell Park Drive
Cincinnati, Oh 45242
AltaFiber | (513) 565-7187 | Breck Cowan |  | 2022-04-22 | 2022-04-25 |  |  | 2024-06-28 |  | 2025-03-17 | 2025-04-04 |  |  | 9/4/2024 - Breck responded with some markups showing the existing UG facilities belongs to CBT/Altafiber and some corrections to the locations shown in the plan. Stantec has made the correction in the plan and the change will be reflected in stage 3. 3/17/2025 - Called Breck to discuss the concern with the steps. He will call me back when he gets to his review. (Approx. 1-2 weeks). 4/4/2025 - Breck responded stating utilities are shown in the plans correctly just missing 1 duckbank at sta. 18+50 LT. Does not forsee any issues. | UG
Telecom | [8 empty] | 2024-09-04
221 East Fouth St, BLDG 121-900
Cincinnati, Oh 45202
Greater Cincinnati Water Works | (513) 591-6533 | Earl Bratfish |  | 2022-04-22 |  | 2024-01-19 | 2024-01-29 | 2024-06-28 |  | 2025-03-17 | 2025-03-27 |  |  | 1/29/2024 - Earl responded with some markups and additional water plan sheets. 8/29/2024 - Earl responded with concerns about the 3 fire service facilities ( stand pipe, valve indicator post and valving) at sta. 40+80 on the surface of the prop. SUP, need to contact another person to discuss about relocation options. (Phil Young <phillip.young@gcww.cincinnati-oh.gov>) 3/27/2025 - Earl responded stating concern with the 2 water lines that cross US 50 and our path at sta. 46+60 and 47+90. Concern with the cut for the stabilization. . | UG
Water | [7 empty] | 2024-08-23 | 2024-08-29
1600 Gest St
Cincinnati, Ohio 45204
Verizon Communications | (330) 253-8267 | Allan Guest |  | 2022-04-22 | 2022-04-22 |  |  | 2024-06-28 |  | 2025-03-17 |  |  |  | 4/22/2022 - Received a screenshot of the telecome line location that belongs to Verizon. Stantec to confirm with them about the accurate location, size, and depth. 3/17/2025 - Cynthia responded that she was able to download the plans. | UG
Telecom
120 Ravine St. |  | Cynthia Martinex | [8 empty] | 2025-03-17
Akron, Ohio 44303

## Impacts & Potential Conflicts
PID # 114496
HAM-Columbia Connector
Utility Crossing / Conflict Locations
Assumed Utility Depths (if less than 18" of separation or utility required clearance violation MUST verify with utility or relocation must occur!
Depths are based upon project experience within D6. | [8 empty] | UTILITY TYPE KEY: | Utility
Water |  |  | 4' |  |  |  | 2025-07-17 |  | T | Telephone
Sanitary Sewer |  |  | N/A -Actual | [5 empty] | C | Cable
Storm Sewer |  |  | N/A-Actual | [5 empty] | FO | Fiber Optic
Telephone, Cable |  |  | 3' | [5 empty] | FODB | Fiber Optic Duct Bank
Fiber Optic, Electrical |  |  | 3' | [5 empty] | E | Electric
GAS |  |  | 3' | [5 empty] | EDB | Electric Duct Bank
GAS PIPELINE |  |  | 4' | [5 empty] | ST | Storm
[9 empty] | SAN | Sanitary
[9 empty] | W | Water
[9 empty] | G | Gas
[9 empty] | GHP | Gas High Pressure
[9 empty] | GPL | Gas Pipeline
[9 empty] | L OR ITS | ODOT OWNED
Ref. No. | Sheet No. | Starting Station | Offset & (RT or LT) | Ending Station | Offset & (RT or LT) | Length | Conflict Location Description | Possible Conflict with what? | # of inches of separation between Existing Utility and proposed work | Is the utility within their own easement? (Y OR N) | Utility Type- (See Key Above for Reference) | If Electric - What is Voltage of line? | Utility Owner | Conflict Resolution | Resolved by what date | Utility Clear Date (sale - 60)
Water
| 14 | 40+74 |  | 40+80 |  |  | Fire service facilities (stand pipe and valve indivator post) on the surface of the prop. SUP which need to be relocated out of the path. | the prop. SUP |  | N | W |  | GCWW | Not determined yet, need to reach out to Phil Young <phillip.young@gcww.cincinnati-oh.gov>
Telecom
Electric
| 12 | 12+64 |  |  |  |  | UG electric distribution line laterally crosses the prop. Curb ramp |  |  |  | E
| 13 | 15+03 |  |  |  |  | Electric Distribution Pole near the constr. Limit |  |  |  | E
| 15-16 | 44+75 |  | 46+69 |  |  | UG electric line along the prop. Sup |  |  |  | E
| 16 | 46+69 |  |  |  |  | Electric Distribution Pole on the surface of SUP, needs to be relocated
| 16 | 49+15 |  |  |  |  | Electric Distribution Pole on the surface of SUP, needs to be relocated
Gas
| 14 | 18+38 |  |  |  |  | gas line laterally cross the prop. shared use path | prop. SUP |  |  | G |  | Duke Energy | Received comments of no conflicts. | 2024-10-22
| 16 | 47+97 |  |  |  |  | gas line laterally cross the prop. shared use path | prop. SUP |  |  | G |  | Duke Energy | Adjust to ground | 2024-10-22
| 14 | 18+38 |  |  |  |  | surface of the prop. shared use path | prop. SUP |  |  | G |  | Duke Energy | Received comments of no conflicts. | 2024-10-22
| 15 | 44+00 |  | 45+00 |  |  | gas line laterally cross the prop. shared use path at a prop. Drive | prop. SUP |  |  | G |  | Duke Energy | Wait for Duke Energy to provide accurate location and depth