## 961A
STATION | OFFSET | SIDE | DESCRIPTION OF CONFLICT |  | UTILITY INVOLVED | Include in FS Discussion?
BEGIN |  |  |  | Signal Pole on Northwest corner of Miami Run and US 50/Wooster Pike Intersection. | Signal Pole | Yes
64.84 | 1.07 | RIGHT |  | Old light pole/sign foundation, not in use, in path footprint. | Light Pole Foundation | No
69.87 | 7.882 | RIGHT |  | Catch Basin at drive of Kroger Gas in path footrpint. | Catch Basin | No
186.84 | 6.28 | RIGHT |  | Catch Basin at Miami Run intersection/turnout. | Catch Basin | No
187.13 | 8.802 | RIGHT |  | Catch Basin at Miami Run intersection/turnout. | Catch Basin | No
208.93 | 10.436 | RIGHT |  | Catch Basin at Miami Run intersection/turnout. | Catch Basin | No
209.69 | 8.082 | RIGHT |  | Catch Basin at Miami Run intersection/turnout. | Catch Basin | No
605.31 | 5.078 | LEFT |  | Catch Basin located in proposed path footprint. | Catch Basin | No
663.3 | 7.442 | LEFT |  | Manhole in the proposed path footprint. | Manhole | No

## 962A
STATION | OFFSET | SIDE | DESCRIPTION OF CONFLICT |  | UTILITY INVOLVED | Include in FS Discussion? | Project Cost?
2017.31 | 3.6367 | RIGHT |  | Street sign in path footprint. | Street Sign | No
2017.46 | 3.92 | LEFT |  | Street sign in path footprint. | Street Sign | No
2337.44 | 12.938 | RIGHT |  | Electric power pole within grading limits. | Electric Power Pole | No
2385.85 | 10.8786 | RIGHT |  | Street sign in path footprint. | Street Sign | No
2472.6223 | 7.5634 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2475.2248 | 7.4827 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2593.0792 | 7.373 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2595.5549 | 7.3656 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2604.528 | 19.407 | LEFT |  | Fire Hydrant located on the edge of the footrpint of the retaining wall. | Fire Hydrant | Yes
2655.1291 | 21.1401 | LEFT |  | Street sign in retaining wall footprint. | Street Sign | No
2687.5193 | 22.1297 | LEFT |  | Electric power pole within grading limits. | Electric Power Pole | No
2814.3338 | 18.0266 | LEFT |  | Signal/Power Pole located in proposed path footprint. | Signal/Power Pole | Yes
2821.5893 | 9.0187 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | No
2824.3978 | 8.9491 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2939.4933 | 17.1857 | LEFT |  | Electric Power pole located in the proposed path footprint. | Electric Power Pole | Yes
2966.823 | 8.7551 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2969.4916 | 8.4853 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
2988.8419 | 17.3146 | LEFT |  | Street sign in path footprint. | Street Sign | No
2990.8206 | 23.319 | LEFT |  | Catch Basin on edge of Kroger parking lot located in limits of grading. | Catch Basin | No
2994.4903 | 23.264 | LEFT |  | Catch Basin on edge of Kroger parking lot located in limits of grading. | Catch Basin | No
3032.5778 | 13.8855 | LEFT |  | Fire Hydrant located in the proposed path footprint. | Fire Hydrant | Yes
3086.8241 | 16.688 | LEFT |  | Electric Power pole located in the proposed path footprint. | Electric Power Pole | Yes
3142.504 | 7.465 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
3145.3284 | 7.4334 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
3157.0514 | 16.8724 | LEFT |  | Street sign in path footprint. | Street Sign | No
3164.1605 | 21.1652 | LEFT |  | Catch Basin on edge of Kroger parking lot located in limits of grading. | Catch Basin | No
3206.4898 | 8.6335 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
3209.6409 | 8.6493 | LEFT |  | Catch Basin located in existing curb line is in proposed path footprint, curb line is being reset. | Catch Basin | Yes
3230.8518 | 17.0031 | LEFT |  | Electric Power pole located in the proposed path footprint. | Electric Power Pole | Yes
3311.6575 | 16.8244 | LEFT |  | Street sign in path footprint. | Street Sign | No
3354.4621 | 15.3513 | LEFT |  | Electric Power pole located in the proposed path footprint. | Electric Power Pole | Yes
3382.7215 | 17.1829 | LEFT |  | Concrete paved gutter from Kroger parking lot located in proposed path's footprint. | Paved Gutter | Yes
3501.7658 | 2.0692 | LEFT |  | Electric Power pole located in the buffer of the proposed aligment. | Electric Power Pole | No
3519.0147 | 15.992 | LEFT |  | McDonalds sign within the proposed path and wall footprint. | Private Sign | Yes
3553.5954 | 12.466 | LEFT |  | Light pole of McDonald's parking lot located in the proposed path's footprint. | Light Pole | Yes
3562.2926 | 10.2665 | LEFT |  | Street sign in path footprint. | Street Sign | No
3618.7562 | 10.4048 | LEFT |  | Street sign in path footprint. | Street Sign | No
3678.0259 | 13.5343 | LEFT |  | Light pole of McDonald's parking lot located in the proposed path's footprint. | Light Pole | Yes
3726.2667 | 15.7397 | LEFT |  | Sreet sign in path footprint. | Street Sign | No
3731.0421 | 23.587 | LEFT |  | Signal pole located in the proposed grading. | Signal Pole | No
3795.91 | 13.033 | LEFT |  | Signal pole located in the proposed path's footprint. | Signal Pole | Yes

## 971B
STATION | OFFSET | SIDE | DESCRIPTION OF CONFLICT |  | UTILITY INVOLVED | Include in FS Discussion?
1006.33 | 11.724 | RIGHT |  | Street sign in path footprint. | Street Sign | No
1008.66 | 21.547 | RIGHT |  | Mariemont Promenade sign within grading for bike path. | Private Sign | No
1013.88 | 11.865 | RIGHT |  | Signal pole located in path footprint (new location based on Googel Earth, but still within the path footprint). | Signal Pole | Yes
1085.99 | 7.845 | RIGHT |  | Street sign in path footprint. | Street Sign | No
1088.67 | 25.124 | RIGHT |  |  |  | No
1089.36 | 21.082 | RIGHT |  | Signal control box/cabinet. | Signal Cabinet | Yes
1089.56 | 16.873 | RIGHT |  | Signal pole located in path footprint (new location based on Googel Earth and may not be within the path footprint, but will still be within grading limits). | Signal Pole | Yes
1313.72 | 24.228 | RIGHT |  | Light pole within limits of grading. | Light Pole | Yes
1590.47 | 44.173 | RIGHT |  | Sanitary Manhole within grading limits. | Sanitary Manhole | Yes
1688.34 | 8.686 | RIGHT |  | Electric Power Pole in path footprint. | Electric Power Pole | No
1888.86 | 16.062 | RIGHT |  | Old concrete sign foundation not in use in path footprint. | Sign Foundation | No
1895.13 | 22.36 | RIGHT |  | Kroger Fuel Station sign conflicts with proposed retaining wall. | Private Sign | Yes
1934.85 | 11.469 | RIGHT |  | Electric Power Pole in path footprint. | Electric Power Pole | Yes

## 972B
STATION | OFFSET | SIDE | DESCRIPTION OF CONFLICT |  | UTILITY INVOLVED | Include in FS Discussion?
3015.22 | 0.979 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3016.6 | 5.98 | RIGHT |  | Manhole located within the proposed path's footprint. | Manhole | No
3018.17 | 0.864 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3083.49 | 10.861 | RIGHT |  | Fire hydrant located in the proposed path's footprint. | Fire Hydrant | No
3184.02 | 0.708 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3185.25 | 6.156 | RIGHT |  | Manhole located within the proposed path's footprint. | Manhole | No
3186.77 | 0.45 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3377.23 | 1.309 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3379.67 | 7.03 | RIGHT |  | Manhole located within the proposed path's footprint. | Manhole | No
3380.47 | 1.602 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3410.75 | 6.764 | RIGHT |  | Manhole located within the proposed path's footprint. | Manhole | No
3471.23 | 12.987 | RIGHT |  | Fire hydrant located in the proposed path's footprint. | Fire Hydrant | Yes
3571.19 | 1.048 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No
3574.52 | 5.105 | RIGHT |  | Manhole located within the proposed path's footprint. | Manhole | No
3574.79 | 0.806 | RIGHT |  | Catch Basin located on the existing curb line. | Catch Basin | No