Ohio Department of Transportation

District 5, 9600 Jacksontown Road S.E., P.O. Box 306, Jacksontown, Ohio 43030 (740) 323-4400

TO: *Please comment, pass on and return to Planning and Engineering

FROM: Chris Shonk, P.E.

DATE:	 Tuesday, January 24, 2023

SUBJECT: Lic-70-10.77 PID: 104637

Anticipated Award date: February 16, 2024

* Steve Miller, P.E., Area Construction Engineer

* Jeff Hill, County Manager

*	Julie Gwinn, P.E., Capitol Program Administrator

* Jason Sturgeon, P.E.  District Deputy Director

* Cody Gierhart, District GIS Coordinator

* Doug Morgan, P.E. District Design Engineer

* Joe Broschart, Project Coordinator

The subject project is in Licking County on Interstate 70 at the 10.77 mile marker.  It involves the replacement of the existing bridge superstructure: beams, deck, parapet, & approach slabs and the rebuilding of the abutments from the top of footer up. The vertical profile of Twp. Rd. 144 will be raised approximately 9" to increase to vertical clearance of I.R. 70 from 15.8'  to 16.6'.  The raising of the Twp. Rd. 144 vertical profile will require full depth pavement, embankment work, and guardrail installation at the location.

The replacement of the superstructure under part-width construction was considered, however, the disadvantages associated with this option exceeded the advantages.  The existing bridge deck is 24’-0” wide measured from the curb faces and has 4 beam lines. To construct the bridge with part width construction, the driving lane must have at least 3 beam lines under the bridge deck to maintain traffic during construction. Widening the bridge to left, right, or symmetrically would require the full replacement of the superstructure and substructures. Widening the bridge is this manner would also require additional right of way.  The existing roadway, Twp. Rd. 144, width is 16’, the ADT consists of 140 cars and 20 B/C trucks. The added length of the local detour will be 3.0 miles.  In summary it was determined from the information provided above (additional costs, additional right of way, short local detour, low ADT/user costs) that it will be far more cost effective and practical to implement a full closure of Township Rd. 144 during construction.

As of this date, no other state projects are anticipated to be constructed on the potential detour routes.

If there are any questions, please contact me at 740-323-5110.

Proposed Detour Survey

Lic-70-10.77

| Project ID#: 104637 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Type and Description: | It involves the replacement of the existing bridge superstructure with related roadway work, embankment work, and guardrail installation at the location. |  |  |  |  |
| Potential Detour Route: | LOCAL DETOUR NORTHBOUND: Palmer Rd. West to S.R. 158 North to U.S. 40 East. SOUTHBOUND: Reverse of Northbound. STATE DETOUR: N/A |  |  |  |  |
| Adequacy of above Routes: 1) Pavement Width 2) Bridge Capacity 3) Safeness | STATE DETOUR LOCAL DETOUR 1) N/A 1) 16’-24’ asphalt chip seal/asphalt 2) N/A 2) All are adequate 3) N/A 3) All routes are adequate |  |  |  |  |
| Volume & Character of Traffic | PASSENGER & A: 140 B & C: 20 TOTAL: 160 |  |  |  |  |
| Local Traffic Needs | Local traffic will use: Local Detour as stated above. |  |  |  |  |
| Directive Distribution |  |  |  |  |  |
| Detour Distance | STATE: LOCAL: LENGTH OF DETOUR: N/A miles 4.5 miles LENGTH OF NORMAL ROUTING: N/A miles 1.5 miles ADDED LENGTH: N/A miles 3.0 miles |  |  |  |  |
| General Comments & Recommendations | Expected Duration of Work: 90 days (including time to order materials, etc.) T.R. 144 closed 90 days |  |  |  |  |
| Length of Work | 0.13 miles |  |  |  |  |
| Proposed Roadway Width | Pavement width – 2 - 11’ lanes & 2.75’ shoulders |  |  |  |  |
| PERSONNEL SURVEY Please initial box (only one) for your approval and circulate to next on the list. |  |  |  |  |  |
| TITLE |  | if attachment | RUN AROUND | HALF WIDTH DETOUR | CLOSURE DURATION CONSTRUCTION DURATION |
| AREA CONSTRUCTION ENGINEER |  |  |  |  |  |
| COUNTY MANAGER |  |  |  |  |  |
| PLANNING AND ENGINEERING ADMINISTRATOR |  |  |  |  |  |
| DISTRICT DEPUTY DIRECTOR |  |  |  |  |  |
| DISTRICT GIS COORDINATOR |  |  |  |  |  |
| DISTRICT PROJECTS COORDINATOR |  |  |  |  |  |

Comments: Lane Value Contract, as per proposal note 127, “Lane Value Contract” for use on I.R. 70