Ohio Department of Transportation

District 5, 9600 Jacksontown Road S.E., P.O. Box 306, Jacksontown, Ohio 43030 (740) 323-4400

TO: *Please comment, pass on and return to Planning and Engineering

FROM: Heather Gilbert, P.E.

DATE:	 Thursday, July 1, 2021

SUBJECT: Lic-37-25.05 PID: 114392

Anticipated Award date: April 25, 2022

* Steve Miller, P.E., Area Construction Engineer

* Jeff Hill, County Manager

*	Julie Gwinn, P.E., Capitol Program Administrator

* Jason Sturgeon, P.E.  District Deputy Director

* Cody Gierhart, District GIS Coordinator

* Doug Morgan, P.E. District Design Engineer

* Joe Broschart, Project Coordinator

The subject project is in Licking County on State Route 37 at the 25.05 mile marker.  It involves the replacement of the existing bridge superstructure with related roadway work, embankment work, and guardrail installation at the location.

The replacement of the structure under part-width construction was considered, however, the disadvantages associated with this option exceeded the advantages.  The phase to construct the west side of the structure would require a full closure due to the proximity of the drives and expected truck movements.  The taper for the barrier on the north end of the bridge would not allow for access to the affected property if traffic were to be maintained part-width.  With at least one phase needing to be a full closure, the decision was made that the project could be expedited if all of the work was performed under a full closure.  The availability of a relatively close state detour route (SR 204->SR 158) was also a consideration for implementing a full closure.

As of this date, no other state projects are anticipated to be constructed on the potential detour routes.

If there are any questions please contact me at 740-323-5113.

Proposed Detour Survey

Lic-37-25.05

| Project ID#: 114392 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Type and Description: | It involves the replacement of the existing bridge superstructure with related roadway work, embankment work, and guardrail installation at the location. |  |  |  |  |
| Potential Detour Route: | LOCAL DETOUR: I.R. 70 to S.R. 158 to Palmer Road STATE DETOUR: I.R. 70 to S.R. 158 to S.R. 204 |  |  |  |  |
| Adequacy of above Routes: 1) Pavement Width 2) Bridge Capacity 3) Safeness | STATE DETOUR LOCAL DETOUR 1) 24’ 1) 10’ – 14’ asphalt/asphalt chip seal 2) All are adequate 2) All are adequate 3) All routes are adequate 3) All routes are adequate |  |  |  |  |
| Volume & Character of Traffic | PASSENGER & A: 10,230 B & C: 770 TOTAL: 11,000 |  |  |  |  |
| Local Traffic Needs | Local traffic will use: N/A |  |  |  |  |
| Directive Distribution |  |  |  |  |  |
| Detour Distance | STATE: LOCAL: LENGTH OF DETOUR: 8.7 miles 7.4 miles LENGTH OF NORMAL ROUTING: 3.4 miles 0.6 miles ADDED LENGTH: 5.3 miles 6.8 miles |  |  |  |  |
| General Comments & Recommendations | Expected Duration of Work: 150 days (including time to order materials, etc.) S.R. 37 closed 45 days $5,000/day with a maximum incentive $45,000 |  |  |  |  |
| Length of Work | 0.02 miles |  |  |  |  |
| Proposed Roadway Width | Pavement width – 2 12’ lanes & 4’ shoulders |  |  |  |  |
| PERSONNEL SURVEY Please initial box (only one) for your approval and circulate to next on the list. |  |  |  |  |  |
| TITLE |  | if attachment | RUN AROUND | HALF WIDTH DETOUR | CLOSURE DURATION CONSTRUCTION DURATION |
| AREA CONSTRUCTION ENGINEER |  |  |  |  |  |
| COUNTY MANAGER |  |  |  |  |  |
| PLANNING AND ENGINEERING ADMINISTRATOR |  |  |  |  |  |
| DISTRICT DEPUTY DIRECTOR |  |  |  |  |  |
| DISTRICT GIS COORDINATOR |  |  |  |  |  |
| DISTRICT PROJECTS COORDINATOR |  |  |  |  |  |

Comments:  A+B Bidding, as per proposal note 124, “A+B bidding”