## PRE-PHASE 1
SHEET NO. | PHASE | 411 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622 | 622 | 622
|  | STABILIZED CRUSHED AGGREGATE | INCREASED BARRIER DENLINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (UNIDIRECTIONAL) | WORK ZONE RAISED PAVEMENT MARKER (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY YELLOW) | BARRIER REFLECTOR, TYPE 1 ( ONE WAY) | OBJECT MARKER, ONE WAY | OBJECT MARKER, TWO WAT | WORK ZONE LANE LINE, CLASS I, 6", 807 PAINT | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (WHITE) | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (YELLOW) | WORK ZONE CHANNELIZING LINE, CLASS I, 8", 807 PAINT | WORK ZONE CHANNELIZING LINE, CLASS I, 12", 807 PAINT | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED | PORTABLE BARRIER, ANCHORED | GLARE SCREEN
|  | CY | FT | EACH | EACH | EACH | EACH | EACH | EACH | EACH | MILE | MILE | MILE | FT | FT | SY | FT | FT | FT
26 | PRE-PHASE 1 | 1.7 | 100 | 1 |  | 36 | 18 | 8 | 7 |  | 0.07 | 0.14 | 0.14 | 350 |  | 4 | 100
27 | PRE-PHASE 1 | 26.7 |  |  |  | 50 | 25 | 30 | 9 | 6 | 0.1 | 0.19 | 0.19 | 500 |  | 787.6 | 800 |  | 300
27 | PRE-PHASE 1 | 3.8 |  |  |  | 6 | 1 | 30 | 10 | 10 | 0.19 | 0.19 | 0.19 |  |  | 103.7 | 1000 |  | 500
28 | PRE-PHASE 1 |  | 42 |  |  | 4 |  | 27 | 9 | 9 | 0.19 | 0.19 | 0.19 |  |  |  | 958 | 42 | 500
28 | PRE-PHASE 1 |  | 500 |  | 1 | 3 |  | 30 | 10 | 10 | 0.19 | 0.19 | 0.19 |  |  |  | 500 | 500 | 500
29 | PRE-PHASE 1 |  | 142 |  |  | 5 |  | 27 | 9 | 9 | 0.19 | 0.19 | 0.19 |  |  |  | 858 | 142 | 500
29 | PRE-PHASE 1 |  |  |  |  | 4 |  | 30 | 10 | 10 | 0.19 | 0.19 | 0.19 |  |  |  | 1000 |  | 500
30 | PRE-PHASE 1 |  | 92 |  |  | 2 |  | 12 | 4 | 4 | 0.08 | 0.08 | 0.08 |  |  |  | 508 | 92 | 300
| SUB-TOTAL PLAN SPLIT 01/NHS/14 | 32.2 | 876 | 1 | 1 | 110 | 44 | 194 | 68 | 58 | 1.2 | 1.36 | 1.36 | 850 |  | 895.3 | 5724 | 776 | 3100
30 | PRE-PHASE 1 |  | 292 |  | 1 | 1 |  | 15 | 5 | 5 | 0.12 | 0.12 | 0.12 |  |  |  | 408 | 292 | 500
30 | PRE-PHASE 1 |  | 342 |  | 1 | 3 |  | 27 | 9 | 9 | 0.19 | 0.19 | 0.19 |  |  |  | 658 | 342 | 500
31 | PRE-PHASE 1 |  |  |  |  | 4 |  | 30 | 10 | 10 | 0.19 | 0.19 | 0.19 |  |  |  | 1000 |  | 500
31 | PRE-PHASE 1 |  |  |  |  | 4 |  | 27 | 9 | 9 | 0.19 | 0.19 | 0.191 |  |  |  | 1000 |  | 500
32 | PRE-PHASE 1 |  |  |  |  | 5 |  | 30 | 10 | 10 | 0.19 | 0.19 | 0.19 |  |  |  | 1000 |  | 500
32 | PRE-PHASE 1 | 5.6 |  |  |  | 4 |  | 27 | 9 | 9 | 0.19 | 0.19 | 0.19 |  |  | 161.8 | 1000 |  | 500
33 | PRE-PHASE 1 | 24.9 | 144 | 2 |  | 4 |  | 26 | 10 | 5 | 0.19 | 0.19 | 0.19 |  |  | 695.9 | 906 |  | 406
33 | PRE-PHASE 1 |  |  |  |  | 39 | 19 | 2 | 1 |  | 0.1 | 0.17 | 0.17 | 374 |  |  | 62
34 | PRE-PHASE 1 |  |  |  |  | 50 | 25 |  |  |  | 0.09 | 0.09 | 0.09 | 500
34 | PRE-PHASE 1 |  |  |  |  | 26 | 13 | [6 empty] | 250
| SUB-TOTAL PLAN SPLIT 02/NHS/11 | 30.5 | 778 | 2 | 2 | 140 | 57 | 184 | 63 | 57 | 1.45 | 1.52 | 1.521 | 1124 |  | 857.7 | 6034 | 634 | 3406
SUB-TOTALS CARRIED TO SHEET 23
PRE-PHASE 1 TOTALS (INFO ONLY) |  | 63 | 1654 | 3 | 3 | 250 | 101 | 378 | 131 | 115 | 3 | 3 | 3 | 1974 |  | 1753 | 11758 | 1410 | 6506

## PHASE 1
SHEET NO. | PHASE | 411 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622 | 622 | 622
|  | STABILIZED CRUSHED AGGREGATE | INCREASED BARRIER DENLINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (UNIDIRECTIONAL) | WORK ZONE RAISED PAVEMENT MARKER (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY YELLOW) | BARRIER REFLECTOR, TYPE 1 ( ONE WAY) | OBJECT MARKER, ONE WAY | OBJECT MARKER, TWO WAT | WORK ZONE LANE LINE, CLASS I, 6", 807 PAINT | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (WHITE) | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (YELLOW) | WORK ZONE CHANNELIZING LINE, CLASS I, 8", 807 PAINT | WORK ZONE CHANNELIZING LINE, CLASS I, 12", 807 PAINT | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED | PORTABLE BARRIER, ANCHORED | GLARE SCREEN
|  | CY | FT | EACH | EACH | EACH | EACH | EACH | EACH | EACH | MILE | MILE | MILE | FT | FT | SY | FT | FT | FT
35 | PHASE 1 |  |  |  |  | 37 | 18 |  |  |  |  | 0.07 | 0.07 | 250 | 200
36 | PHASE 1 |  |  |  |  | 27 | 25 |  |  |  |  | 0.28 | 0.1 | 30
36 | PHASE 1 |  |  |  |  | 16 | 16 |  |  |  |  | 0.29 | 0.1
37 | PHASE 1 |  | 42 | 1 |  |  |  | 2 | 2 |  |  | 0.29 | 0.1 |  |  |  | 12 | 42
37 | PHASE 1 |  | 150 |  |  |  |  | 8 | 8 |  |  | 0.29 | 0.1 |  |  |  |  | 450
38 | PHASE 1 | [10 empty] | 0.29 | 0.1
38 | PHASE 1 | [10 empty] | 0.29 | 0.1
39 | PHASE 1 |  | 104 | 1 |  |  |  | 3 | 3 |  |  | 0.17 | 0.06 |  |  |  | 12 | 92
| SUB-TOTAL PLAN SPLIT 01/NHS/14 |  | 296 | 2 |  | 80 | 59 | 13 | 13 |  |  | 1.97 | 0.73 | 280 | 200 |  | 24 | 584
39 | PHASE 1 |  | 88 |  |  |  |  | 3 | 3 |  |  | 0.12 | 0.04 |  |  |  |  | 100
39 | PHASE 1 | [6 empty] | 5 | 5 |  |  | 0.29 | 0.1 |  |  |  |  | 262
40 | PHASE 1 | [10 empty] | 0.29 | 0.1
40 | PHASE 1 | [10 empty] | 0.29 | 0.1
41 | PHASE 1 | [10 empty] | 0.29 | 0.1
41 | PHASE 1 |  |  |  |  | 8 | 8 |  |  |  |  | 0.29 | 0.1
42 | PHASE 1 |  |  |  |  | 41 | 25 |  |  |  |  | 0.18 | 0.1 | 370
42 | PHASE 1 |  |  |  |  | 26 | 13 | [5 empty] | 0.02 | 40 | 200
| SUB-TOTAL PLAN SPLIT 02/NHS/11 |  | 88 |  |  | 75 | 46 | 8 | 8 |  |  | 1.75 | 0.66 | 410 | 200 |  |  | 362
SUB-TOTALS CARRIED TO SHEET 23
PHASE 1 TOTALS (INFO ONLY) |  |  | 384 | 2 |  | 155 | 105 | 21 | 21 |  |  | 3.72 | 1.39 | 690 | 400 |  | 24 | 946

## PHASE 2
SHEET NO. | PHASE | 411 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622 | 622 | 622
|  | STABILIZED CRUSHED AGGREGATE | INCREASED BARRIER DENLINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (UNIDIRECTIONAL) | WORK ZONE RAISED PAVEMENT MARKER (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY YELLOW) | BARRIER REFLECTOR, TYPE 1 ( ONE WAY) | OBJECT MARKER, ONE WAY | OBJECT MARKER, TWO WAT | WORK ZONE LANE LINE, CLASS I, 6", 807 PAINT | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (WHITE) | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (YELLOW) | WORK ZONE CHANNELIZING LINE, CLASS I, 8", 807 PAINT | WORK ZONE CHANNELIZING LINE, CLASS I, 12", 807 PAINT | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED | PORTABLE BARRIER, ANCHORED | GLARE SCREEN
|  | CY | FT | EACH | EACH | EACH | EACH | EACH | EACH | EACH | MILE | MILE | MILE | FT | FT | SY | FT | FT | FT
45 | PHASE 2 | [10 empty] | 0.14
45 | PHASE 2 | [10 empty] | 0.19
46 | PHASE 2 |  | 42 | 1 |  |  |  | 2 | 2 |  |  | 0.19 |  |  |  |  | 12 | 42
46 | PHASE 2 |  | 450 |  |  |  |  | 9 | 9 |  |  | 0.19 | [5 empty] | 450
47 | PHASE 2 | [10 empty] | 0.19
47 | PHASE 2 | [10 empty] | 0.19
48 | PHASE 2 |  | 92 | 1 |  |  |  | 2 | 2 |  |  | 0.12 |  |  |  |  | 12 | 92
| SUB-TOTAL PLAN SPLIT 01/NHS/14 |  | 584 | 2 |  |  |  | 13 | 13 |  |  | 1.21 |  |  |  |  | 24 | 584
48 | PHASE 2 |  | 100 |  |  |  |  | 4 | 4 |  |  | 0.08 | [5 empty] | 200
48 | PHASE 2 | [6 empty] | 6 | 6 |  |  | 0.19 | [5 empty] | 260
49 | PHASE 2 | [10 empty] | 0.19
49 | PHASE 2 | [10 empty] | 0.19
50 | PHASE 2 | [10 empty] | 0.19
50 | PHASE 2 | [10 empty] | 0.19
51 | PHASE 2 | [10 empty] | 0.08
| SUB-TOTAL PLAN SPLIT 02/NHS/11 |  | 100 |  |  |  |  | 10 | 10 |  |  | 1.11 | [5 empty] | 460
SUB-TOTALS CARRIED TO SHEET 23
PHASE 2 TOTALS (INFO ONLY) |  |  | 684 | 2 |  |  |  | 23 | 23 |  |  | 2.32 |  |  |  |  | 24 | 1044

## PHASE 3
SHEET NO. | PHASE | 411 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622 | 622 | 622
|  | STABILIZED CRUSHED AGGREGATE | INCREASED BARRIER DENLINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (UNIDIRECTIONAL) | WORK ZONE RAISED PAVEMENT MARKER (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY YELLOW) | BARRIER REFLECTOR, TYPE 1 ( ONE WAY) | OBJECT MARKER, ONE WAY | OBJECT MARKER, TWO WAT | WORK ZONE LANE LINE, CLASS I, 6", 807 PAINT | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (WHITE) | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (YELLOW) | WORK ZONE CHANNELIZING LINE, CLASS I, 8", 807 PAINT | WORK ZONE CHANNELIZING LINE, CLASS I, 12", 807 PAINT | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED | PORTABLE BARRIER, ANCHORED | GLARE SCREEN
|  | CY | FT | EACH | EACH | EACH | EACH | EACH | EACH | EACH | MILE | MILE | MILE | FT | FT | SY | FT | FT | FT
N/A | PRE-PHASE 3 (CROSSOVER 3 CONST.) |  |  | 1 |  |  |  | 10 | 10 | [7 empty] | 500
55 | PHASE 3 |  |  |  |  | 10 | 5 | [6 empty] | 100
56 | PHASE 3 |  |  |  |  | 50 | 25 |  |  |  |  | 0.06 | 0.06 | 500
56 | PHASE 3 | 1.9 |  |  |  | 82 | 41 |  |  |  | 0.01 | 0.16 | 0.16 | 700 | 200 | 5.5
57 | PHASE 3 | 20.4 | 144 | 1 |  | 52 | 28 | 20 |  | 8 | 0.09 | 0.32 | 0.19 | 350 |  | 788.6 | 256 |  | 256
57 | PHASE 3 | 3.8 |  |  |  | 4 |  | 18 |  | 10 | 0.1 | 0.38 | 0.19 |  |  | 97.9 | 500 |  | 500
58 | PHASE 3 |  | 42 |  |  | 4 |  | 20 |  | 8 | 0.1 | 0.38 | 0.19 |  |  |  | 458 | 42 | 500
58 | PHASE 3 |  | 200 |  | 1 | 4 |  | 25 | 7 | 10 | 0.1 | 0.38 | 0.19 |  |  |  |  | 850 | 500
59 | PHASE 3 |  | 284 | 1 |  | 4 |  | 23 | 3 | 8 | 0.1 | 0.38 | 0.19 |  |  |  | 370 | 284 | 500
59 | PHASE 3 |  |  |  |  | 4 |  | 18 |  | 10 | 0.1 | 0.38 | 0.19 |  |  |  | 500
60 | PHASE 3 |  |  |  |  | 2 |  | 12 |  | 6 | 0.06 | 0.23 | 0.12 |  |  |  | 300 |  | 300
| SUB-TOTAL PLAN SPLIT 01/NHS/14 | 26.1 | 670 | 3 | 1 | 216 | 99 | 146 | 20 | 60 | 0.66 | 2.67 | 1.48 | 1650 | 200 | 892 | 2884 | 1176 | 2556
N/A | PRE-PHASE 3 (CROSSOVER 4 CONST.) |  |  | 1 |  |  |  | 10 | 10 | [7 empty] | 500
60 | PHASE 3 |  |  |  |  | 2 |  | 8 | 5 | 2 | 0.04 | 0.16 | 0.08 |  |  |  | 200 | 200 | 200
60 | PHASE 3 |  | 200 | 1 |  | 4 |  | 27 | 7 | 10 | 0.1 | 0.38 | 0.19 |  |  |  | 512 | 390 | 500
61 | PHASE 3 |  | 192 |  |  | 4 |  | 18 |  | 8 | 0.1 | 0.38 | 0.19 |  |  |  | 500 |  | 500
61 | PHASE 3 |  |  |  |  | 5 |  | 20 |  | 10 | 0.1 | 0.38 | 0.19 |  |  |  | 500 |  | 500
62 | PHASE 3 |  |  |  |  | 4 |  | 18 |  | 8 | 0.1 | 0.38 | 0.19 |  |  |  | 500 |  | 500
62 | PHASE 3 |  |  |  |  | 4 |  | 20 |  | 10 | 0.1 | 0.38 | 0.19 |  |  |  | 500 |  | 500
63 | PHASE 3 | 7.1 |  |  |  | 42 | 31 | 18 |  | 8 | 0.07 | 0.38 | 0.19 | 150 |  | 216.7 | 500 |  | 500
63 | PHASE 3 | 21.3 |  |  |  | 98 | 50 | 6 |  | 3 |  | 0.27 | 0.19 | 1000 | 50 | 543.7 | 134 |  | 134
64 | PHASE 3 |  |  |  |  | 24 | 12 |  |  |  | 0.06 | 0.1 | 0.1 | 75 | 150
| SUB-TOTAL PLAN SPLIT 02/NHS/11 | 28.4 | 392 | 2 |  | 187 | 93 | 145 | 22 | 59 | 0.67 | 2.81 | 1.51 | 1225 | 200 | 760.4 | 3846 | 590 | 3334
SUB-TOTALS CARRIED TO SHEET 23
PHASE 2 TOTALS (INFO ONLY) |  | 54.5 | 1062 | 5 | 1 | 403 | 192 | 291 | 42 | 119 | 1.33 | 5.48 | 2.99 | 2875 | 400 | 1652.4 | 6730 | 1766 | 5890

## PHASE 4
SHEET NO. | PHASE | 411 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 615 | 622 | 622 | 622
|  | STABILIZED CRUSHED AGGREGATE | INCREASED BARRIER DENLINEATION | WORK ZONE IMPACT ATTENUATOR, 24" WIDE HAZARDS, (UNIDIRECTIONAL) | WORK ZONE RAISED PAVEMENT MARKER (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY WHITE) | WORK ZONE RAISED PAVEMENT MARKER, AS PER PLAN (ONE WAY YELLOW) | BARRIER REFLECTOR, TYPE 1 ( ONE WAY) | OBJECT MARKER, ONE WAY | OBJECT MARKER, TWO WAT | WORK ZONE LANE LINE, CLASS I, 6", 807 PAINT | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (WHITE) | WORK ZONE EDGE LINE, CLASS I, 6", 807 PAINT (YELLOW) | WORK ZONE CHANNELIZING LINE, CLASS I, 8", 807 PAINT | WORK ZONE CHANNELIZING LINE, CLASS I, 12", 807 PAINT | PAVEMENT FOR MAINTAINING TRAFFIC, CLASS A | PORTABLE BARRIER, UNANCHORED | PORTABLE BARRIER, ANCHORED | GLARE SCREEN
|  | CY | FT | EACH | EACH | EACH | EACH | EACH | EACH | EACH | MILE | MILE | MILE | FT | FT | SY | FT | FT | FT
67 | PHASE 4 | [10 empty] | 0.16
68 | PHASE 4 | [10 empty] | 0.19
68 | PHASE 4 |  | 50 |  |  |  |  | 7 | 7 |  |  | 0.19 | [5 empty] | 350
69 | PHASE 4 |  | 142 | 1 |  |  |  | 3 | 3 |  |  | 0.19 |  |  |  |  | 12 | 142
69 | PHASE 4 | [10 empty] | 0.19
70 | PHASE 4 | [10 empty] | 0.12
| SUB-TOTAL PLAN SPLIT 01/NHS/14 |  | 192 | 1 |  |  |  | 10 | 10 |  |  | 1.04 |  |  |  |  | 12 | 492
70 | PHASE 4 | [6 empty] | 4 | 4 |  |  | 0.07 | [5 empty] | 200
70 | PHASE 4 |  | 192 | 1 |  |  |  | 8 | 8 |  |  | 0.19 |  |  |  |  | 12 | 400
71 | PHASE 4 | [10 empty] | 0.19
71 | PHASE 4 | [10 empty] | 0.19
72 | PHASE 4 | [10 empty] | 0.19
72 | PHASE 4 | [10 empty] | 0.19
73 | PHASE 4 | [10 empty] | 0.19
73 | PHASE 4 | [10 empty] | 0.08
| SUB-TOTAL PLAN SPLIT 02/NHS/11 |  | 192 | 1 |  |  |  | 12 | 12 |  |  | 1.29 |  |  |  |  | 12 | 600
| PHASE 4 TOTALS (INFO ONLY) |  | 384 | 2 |  |  |  | 22 | 22 |  |  | 2.33 |  |  |  |  | 24 | 1092
PLAN SPLIT 01/NHS/14
19 | PRE-PHASE 1 | 32.2 | 876 | 1 | 1 | 110 | 44 | 194 | 68 | 58 | 1.2 | 1.36 | 1.36 | 850 | 0 | 895.3 | 5724 | 776 | 3100
20 | PHASE 1 | 0 | 296 | 2 | 0 | 80 | 59 | 13 | 13 | 0 | 0 | 1.97 | 0.73 | 280 | 200 | 0 | 24 | 584 | 0
21 | PHASE 2 | 0 | 584 | 2 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 1.21 | 0 | 0 | 0 | 0 | 24 | 584 | 0
22 | PHASE 3 | 26.1 | 670 | 3 | 1 | 216 | 99 | 146 | 20 | 60 | 0.66 | 2.67 | 1.48 | 1650 | 200 | 892 | 2884 | 1176 | 2556
23 | PHASE 4 | 0 | 192 | 1 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 1.04 | 0 | 0 | 0 | 0 | 12 | 492 | 0
| TOTALS PLAN SPLIT 01/NHS/14 | 59 | 2618 | 9 | 2 | 608 |  | 376 | 124 | 118 | 1.9 | 11.82 |  | 2780 | 400 | 1788 | 8668 | 3612 | 5656
PLAN SPLIT 02/NHS/11
19 | PRE-PHASE 1 | 30.5 | 778 | 2 | 2 | 140 | 57 | 184 | 63 | 57 | 1.45 | 1.52 | 1.521 | 1124 | 0 | 857.7 | 6034 | 634 | 3406
20 | PHASE 1 | 0 | 88 | 0 | 0 | 75 | 46 | 8 | 8 | 0 | 0 | 1.75 | 0.66 | 410 | 200 | 0 | 0 | 362 | 0
21 | PHASE 2 | 0 | 100 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | 0 | 460 | 0
22 | PHASE 3 | 28.4 | 392 | 2 | 0 | 187 | 93 | 145 | 22 | 59 | 0.67 | 2.81 | 1.51 | 1225 | 200 | 760.4 | 3846 | 590 | 3334
23 | PHASE 4 | 0 | 192 | 1 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 12 | 600 | 0
| TOTALS PLAN SPLIT 02/NHS/11 | 59 | 1550 | 5 | 2 | 598 |  | 359 | 115 | 116 | 2.2 | 12.18 |  | 2759 | 400 | 1619 | 9892 | 2646 | 6740
TOTALS CARRIRED TO GENERAL SUMMARY
ALL PHASES TOTAL (INFO ONLY) |  | 118 | 4168 | 14 | 4 | 1206 |  | 735 | 239 | 234 | 4.1 | 24 |  | 5539 | 800 | 3407 | 18560 | 6258 | 12396