## Sheet1
ALLOWABLE CLOSURE TABLE
LOCATION | MOT PHASE | DURATION | DAMAGES
SHORT TERM CLOSURES OF US-23 FOR MONROE STREET BRIDGE WORK AS PER MT-99.60 | PHASES 1 - 5B | 15 MINUTES BETWEEN HOURS OF MIDNIGHT AND 5 AM | -
OVERNIGHT RAMP CLOSURES | PHASE CHANGES | 9PM FRI - 5AM MON | $1000/15 MIN
US-23 SB INSIDE LANE CLOSURE FOR TEMPORARY PAVEMENT INSTALLATION | PREPHASE | NIGHTLY 8 PM - 6 AM | $1000/15 MIN
ALEXIS ROAD U-TURN AT ELLIOTT DRIVE RIGHT LANE CLOSURE | PHASE 1 | 10 DAYS | $1000/DAY
US-23 SB INSIDE LANE CLOSURE FOR TEMPORARY PAVEMENT REMOVAL | PHASE 2 | NIGHTLY 8 PM - 6 AM | $1000/15 MIN
MONROE STREET & ALEXIS ROAD BETWEEN GLASGOW ROAD AND ACRES ROAD | PHASES 3 - 5B | A+B DURATION | A+B INCENTIVE/ DISINCENTIVE
ACRES ROAD NORTH OF ALEXIS ROAD | PHASE 3 | 14 DAYS | $1000/DAY
WEEKEND RAMP CLOSURES US-23 NB | PHASE 5A | 14 DAYS | $1000/15 MIN
EAST CEMETARY DRIVE NORTH OF MONROE STREET | PHASE 4 | 14 DAYS | $1000/DAY
GLASGOW ROAD ONE LANE TWO WAY | PHASE 4A | 10 DAYS | $3000/DAY
LANE CLOSURES ON MONROE/ ALEXIS | PHASE 1-2 AND POST PHASE | 8 PM TO 6 AM | $1000/15 MIN