## Sheet1
Project: | MAH-STAVICH TRAIL (PHASE 1) | PID # 112604 | Date: 3/29/2023
Plan Sheet # | Company | Utility Type | Station & Offset | Location | Aerial or Underground | Conflict? | Test Hole Required (Level A) | Comments
11 | Ohio Edison | Electric Guy Wires | 83+14, 10' | Right | Aerial | Yes | No | Relocate guy wires or may need horizontal bar for vertical clearance to trail
12 | Village of Lowellville | Sanitary MH | 89+38, 9' | Left | Underground | Yes | No | Adjust to grade
13 | Village of Lowellville | Sanitary MH | 91+36, 9.5' | Left | Underground | Yes | No | Adjust to grade
13 | Village of Lowellville | Sanitary MH | 94+02, 1.5' | Right | Underground | Yes | No | Adjust to grade
13 | Ohio Edison | Electric Guy Wires | 93+66, 4' | Left | Aerial | Yes | No | Relocate guy wires or may need horizontal bar for vertical clearance to trail
14 | Village of Lowellville | Sanitary MH | 97+36, 0.5' | Right | Underground | Yes | No | Adjust to grade
15 | Village of Lowellville | Sanitary MH | 100+38, 2.5' | Right | Underground | Yes | No | Adjust to grade
15 | Village of Lowellville | Sanitary MH | 102+28, 6.5' | Left | Underground | Yes | No | Adjust to grade
15 | Village of Lowellville | Sanitary MH | 103+40, 7' | Right | Underground | Yes | No | Adjust to grade
16 | Village of Lowellville | Sanitary MH | 106+40, 7' | Right | Underground | Yes | No | Adjust to grade
16 | Dominion East Ohio | Gas Line | 106+54, 11.5' | Left | Underground | No | No | Dominion to relocate gas line around CB