## Stage 3
PID 119047 MAR-746-3.641 | DATE SENT | CORRESPONDENCE | Last Updated: | 2023-12-20 | RESPONSES
|  |  | RESPONSE DATE | CONFLICT? (YES or NO)
ELECTRIC
Mid Ohio Energy | 2023-09-06 | Called for email address in order to send plan set, left a voicemail. | 2023-09-07 |  | Gary Vanderhoff called back to give email address.
2589 Marion-Upper Sandusky Rd. | 2023-09-07 | Email sent; Cover Letter and Plan set provided.
Marion, OH 43302
Attn.: Gary Vanderhoff
Phone: 740-382-1234
Email: gvanderhoff@midohioenergy.com
CABLE
Brightspeed | 2023-09-06 | Called number on file; number disconnected/can't be reached. | 2023-09-06 |  | Chad Smith called back to give information on a Company Contact; Tim Bowser
175 Ashland Rd. | 2023-09-06 | Called additional number to figure out Company Contact; spoke with Chad Smith. | 2023-10-17 |  | Ref attached field locations for Brightspeed utilities. Please let me know what will need relocated. I can abandon all the buried facilities thru the proposed construction limits, by placing all the facilities in the air on the existing pole lines. What is the estimated relocation date for this project?
Mansfield, OH 44902 | 2023-09-06 | Email sent; Cover Letter and Plan set provided. | 2023-12-07 | NO | Brightspeed has given this project to Terra Tech to perform the engineering review. Please find Brightspeed’s existing facilities attached for MAR-746-3.64. The 24 fiber that runs South out of the handhole was located at depths several feet below what is shown in the cross sections and appears to be out of the excavation needed to construct the proposed manhole.
Attn.: Casper Schmidt Tim Bowser | 2023-12-14 | Sent an email to Andrew Huff in response to email received from him with detailed facility depth information, email requeste confirmation that a telephone line picked up by survey was not Brightspeed's. | 2023-12-20 |  | Mr. Huff responded to my email by asking about the origin of the telephone line that is depicted, is it from plans provided or based on anything else. He also informed us of his efforts in doing the investigation used in generating the information provided on 12/7/23.
Phone: 740-393-6864 | 2023-12-20 | A response was sent to Mr. Huff informing him that the basis for location of the questioned telephone line was field gathered locations picked up by the surveyor. Also informing him that we will continue to list that facility as one to be relocated by others since currently we do not know who owns it or what depth it is located at, just it's alignment.
Email: casper.c.schmidt@centurylink.com
Email: tim.bowser@brightspeed.com
WATER
DEL-CO-Water | 2023-09-06 | Called number on file; extension number disconnected/can't be reached. | 2023-09-06 |  | Dave Wolf called back to confirm htat he is the Company Contact.
6773 Olentangy River Rd. | 2023-09-06 | Called additional number to figure out Company Contact, spoke with Dave Wolf. | 2023-09-07 | NO | Del-Co looked at the proposed project and do not believe they will have any conflicts with your proposed improvements. With that being said, I error on the side of caution and I am proposing that Del-Co spot our facilities in two locations shown on the marked up plans attached to confirm our exact location and elevation
Delaware, OH 43015 | 2023-09-06 | Email sent; Cover Letter and Plan set provided. | 2023-09-07 | NO | I will probably have our facilities spotted late this fall once I receive feedback from your team and get this project loaded into our system. We will be able to confirm if a relocation is necessary based off of the results of those potholes.
Attn.: Bill Hamilton Dave Wolf
Phone: 740-548-7746 ext: 2248 740-201-0130
Email: bhamilton@delcowater.com dwolf@delcowater.com
ODOT
ODOT Traffic (DIST. 6) | 2023-09-06 | Email sent; Cover Letter and Plan set provided.
400 East William St.
Delaware, OH 43015
Attn.: Dave Carlin
Phone: 740-833-8267
Email: david.carlin@dot.ohio.gov
GAS