## MOT-70-0603 Brookville
O.U.P.S 1-800-362-2764 |  |  |  |  | PROJECT NO. MOT-70-6.03 |  |  | Last Updated By: CCJ
PM: Chris Jackman, P.E. |  |  |  |  | Location- MOT-70-0603 (BROOKVILLE) |  |  | ON 1/2/18
Utility Company | Telephone | Contact | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Stage 1 Plans Sent | Comments Received | Stage 3 Plans Sent | Comments Received | Remarks
Name and Address | No. | Name
UTILITY COORDINATION LOG
OK
Dayton Power and Light (DPL)
1900 Dryden Rd.
Dayton, OH 45439 | 937-331-4521 | William Gourley | 2015-06-09 |  | 2015-10-09 | 2015-10-14 | 2017-12-21 | 2017-12-22
No conflict -see email 12/22/17
william.gourley@aes.com
OK
Dayton Power & Light
Transmission
P.O. Box 1247 | 937.331.4647 | Gregory Tokar | 2015-06-09 |  | 2015-10-09 | 2015-10-13 | 2017-12-21 |  | No Conflict
Dayton, OH 45401
Gregory.tokar@aes.com
OK
Montgomery Co. Water/Sanitary
1850 Spaulding Rd.
Dayton, OH 45432-3732 | 937.781.2632 | Edward Schlaack | 2015-06-09 |  | 2015-10-09 | 2015-11-23 | 2017-12-21 | 2018-01-02 | No Conflict. See email 1/2/18.
schlaacke@mcohio.org
Ohio DOT Distirct 7 Traffic
1001 Saint Marys Avenue
Sidney, Ohio 45365 | 937-497-6838 | Mary Hoy, PE | 2015-06-09 |  | 2015-10-09 |  | 2017-12-21

## MOT-70-0708-Kimmel
O.U.P.S 1-800-362-2764 |  |  |  |  | PROJECT NO. MOT-70-7.08 |  |  | Last Updated By: CCJ
PM: Chris Jackman, P.E. |  |  |  |  | MOT-70-0708 (KIMMEL ROAD) |  |  | ON 6/05/18
Utility Company | Telephone | Contact | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Stage 1 Plans Sent | Comments Received | Stage 3 Plans Sent | Comments Received | Remarks
Name and Address | No. | Name
UTILITY COORDINATION LOG
[9 empty] | OH lines at both ends of the bridge. Per email 12-7-17, lines should be flagged and signs placed below the flagging. Note added to plans. | Flag Lines-note added to P&P Sheet
Dayton Power and Light (DPL)
1900 Dryden Rd.
Dayton, OH 45439 | 937-331-4521 | William Gourley | 2015-06-09 |  | 2015-10-09 | 2017-12-07 | 2017-12-21
william.gourley@aes.com
OK
Dayton Power & Light
Transmission
P.O. Box 1247 | 937.331.4647 | Gregory Tokar | 2015-06-09 |  | 2015-10-09 | 2015-10-13 | 2017-12-21 | 2017-12-22 | No conflict -see email 10/13/15
Dayton, OH 45401
Gregory.tokar@aes.com
[9 empty] | Possible Conflict with fiber optic and GR at Cell Tower Drive. Note added to plans. They have 2 parallel lines. See phone memos 10-13-15, 8-15-16, emails 10-13-15, 8-22-16. Line north of bridge is 16.5' above roadway (measured on 2/13/18). Line needs to be flagged during construction. See phone memo 12-12-17. This line was field measured by CCJ/AMT on 2-13-18 and found to be 16.5'. Frontier is okay with the existing and proposed VC and will not need to relocate. See Phone Memo 2-26-18. | Flag Lines-note added to P&P Sheet
Frontier Communications | [10 empty] | Chuck would like a hard copy of plans
6464 Westbrook Rd.
Clayton, OH 45315 | 937.833.1468 | Charles Bernacchi | 2015-06-09 |  | 2015-10-09 | 2015-10-13 | 2017-12-21 | 2018-02-26
Cell 541-390-3910
Charles.Bernacchi@ftr.com
OK
Charter Communications
3691 Turner Rd. | [8 empty] | No Conflict
Dayton, OH 45415 | 937.425.8850 | Tim Kuss | 2015-06-09 |  | 2015-10-09 | 2015-10-12 | 2017-12-21
Tim.kuss@charter.com
OK
Montgomery Co. Water/Sanitary
1850 Spaulding Rd. | [8 empty] | No Conflict. See email 11/23/15 and drawings.
Dayton, OH 45432-3732 | 937.781.2632 | Edward Schlaack | 2015-06-09 |  | 2015-10-09 | 2015-11-23 | 2017-12-21 | 2018-01-02 | No Conflict. See email 1-2-18
schlaacke@mcohio.org
[9 empty] | No conflict with Gas Transmission or distribution. See email 1-2-18 and 2-27-18. | OK
Vectren Energy Delivery
6500 Clyo Rd.
Centerville, OH 45459 | 937.312.2533 | Don Specht | 2015-06-09 |  | 2015-10-09 | 2015-10-13 | 2017-12-21 | 2018-01-02
2018-02-27
dspecht@vectren.com
[9 empty] | Pole will need to be relocated. They will need 3 weeks' notice email to relocate their pole. We have added a note to the plans. See email 3-7-18. | Relocation Required. Note added to P&P sheet.
Miami Valley Lighting | 937-259-7192 | Robyn Livesay
1065 Woodman Drive | Cell: 937-475-8627 | robyn.livesay@aes.com
Dayton, OH 45432 | [5 empty] | 2016-08-22 | 2017-12-21 | 2018-03-06
| (937) 259-7191 | Abe Francis
robyn.livesay@dplinc.com |  | abe.francis@aes.com

## Sheet1 (2)
O.U.P.S 1-800-362-2764 |  | OUPS TICKET A427401100-00A CALL ON 10/1/2014 |  |  |  | PROJECT NO. xxxxxx |  | Last Updated By: CIS
PM: xxxx | [5 empty] | Location- Newell St. Painesville, OH |  | ON 12/17/14
Utility Company | Telephone | Contact | Project Notification Notice (Emailed by City or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Sent LG&T Plans | Received Comments | F&OC PLANS SENT | Received Comments | UTILITY NOTE SUBMITED TO CITY UTILITY COORDINATOR | Remarks
Name and Address | No. | Name
UTILITY COORDINATION LOG - Add Additional Rows As Necessary
UTIITY COMPANY NAME |  | Name | Date | Date | Date | Date |  | Date |  | Date
920 xxxxx | 614.365.3406 (O)
Columbus, Oh 43212
Attn: Mr. xxxxxx
Lake County Department of Utilities | 440.350.2652 | Sarah Cerovski |  | 2014-10-01 | No Response
105 Main St.
Painesville, OH 44077