## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | MOT-BRO-2210 | [5 empty] | Last Updated By: | RRB
PM: | AJH |  | OUPS Ticket: | 317300169 | [5 empty] | On: | 2023-10-12
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
Centerpoint | 937-291-7116 | Kelly Spurlock |  |  | 2023-07-26 | 2023-08-17 |  |  |  |  | Gas locates marked, and attached pdf of existings service/main locations.
| 765-648-3246 | Nick Dearing | Gas Transmission |  | 2023-07-26 | [5 empty] | No gras tranmission facilites in the area.
2023-10-05
Frontier Communications | 541-390-3910 | Charles Bernacchi |  |  | 2023-07-26 | 2023-07-31 |  |  |  |  | All phone facilities are aerial and on poles.
2023-10-05
AES | 937-554-9063 | Bill Ward |  |  | 2023-07-26 | 2023-07-28 |  |  |  |  | No underground electric lines crossing the project area, and no work planned in the area.
[9 empty] | 2023-10-05 | 2023-10-09 | Guying at Sta. 38+51 and Sta. 40+90 may be affected if open cut is used. Will specify in pre-con and on pans to DND ex. guying.
MCES | 937-781-2632 | Ed Schlaack |  |  | 2023-07-26 |  |  |  | 2023-10-05 | 2023-10-06 | No utilities in this area.
2023-07-26
2023-07-26

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary