## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | PID 116871 | [5 empty] | Last Updated By: | BAW
PM: | MJT |  | OUPS Ticket: | [6 empty] | On: | 2023-11-30
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
Crown Castle |  | Craig Snell |  |  | 2022-12-13 | Crown Castle is clear of work zone per Craig Snell (12/13/22) | 2023-02-08 | 2/13/23: Craig Snell identified a potential conflict on sheet 11 of the stage 2 plans. We should not be in conflict as we are only replacing curb and repaving in that location. | 2023-08-11 | 11/7/23: Update Email Sent 11/29/23: Craig Snell with Crown Castle provided information on the Fiber that is was underground and appeared to be displayed as cable in the plans. We updated the plans to display as FO, still no conflicts.
10188 International Blvd. Cincinnati, OH 45246
Centerpoint |  | Jeff Pike |  |  | 2022-12-13 | Centerpoint Energy does not anticipate any conflicts per Jeff Pike (01/06/23) | 2023-02-08 | 2/27/23: James Wooten was planning to mark lines not shown on the plan, but has not notified us of that work at this time | 2023-08-11 | 8/15/23 Jeff Pike of CenterPoint contacted James Wooten of CenterPoint to get the missing gas mains marked, still does not forsee any conflicts 11/7/23: Update Email Sent (Received Out of Office response) Forwarded to Kelly Spurlock and Greg Fishman) - No conflicts and gas is shown accurately per Kelly Spurlock
Dayton West Operations Center 4283 N James H McGee Blvd, Dayton, OH 45417
ATT Transmission |  | Dan Gardner |  |  | 2022-12-13 | AT&T Transmission / Long Lines does not have facilities in the project area per Dan Gardner on behalf of Bill Taggart (01/09/23) | 2023-02-08 | Did not receive stage 2 response from them and will be confirming no conflicts when we send out stage 3 | 2023-08-11 | 8/15/23: no conflicts with AT&T local per Howard Laudermilk II 8/11/23: AT&T Transmission does not have facilities in the project area. Per Adam Schneider of MCG Engineering on Behalf of Bill Taggart of AT&T Transmission/Lon Lines
450 W. Willson Bridge Rd. Suite 180 Worthington, Ohio 43085
AES |  | Bill Ward |  |  | 2022-12-13 | No underground electric per Bill Ward (12/15/22) Some concern about pole in conflict w/ curb. Should not be an issue, curb will be replaced in the same location it is today. | 2023-02-08 | 2/22/23: Poles in conflict will be outside of proposed curb and have been labled as "DND" (do not disturb) in the plans. | 2023-08-11 | 8/11/23: No new conflicts per Bill Ward with AES
Charter Communication |  | Jacob Houdeshell |  |  | 2022-12-13 | No Response | 2023-02-08 | We will be coordinating with Chris Graves and Erik Ganger going forward. | 2023-08-11 | 11/7/23: Update Email Sent No conflicts confirmed by Justin Tegtmeyer
Erik Ganger
Chris Graves
Montgomery County Water and Sanitary |  | Edward Schlaack |  |  | 2022-12-13 | No Response | 2023-02-08 | 2/13/23: Received existing plans from Ed Schlaak to confim and update waterline information, but don’t anticipate any conflicts | 2023-08-11 | 9/28/23: Edward Schlaack, P.E from MCES reviewed the plans and included additional as-builts to ensure existing water is shown accurately
Level 3 Communication |  | Terry Spaw |  |  | 2022-12-13 | No Response | 2023-02-08 | We still have not recieved anything from them. Does ODOT have a better contact for this company? | 2023-08-11 | 8/18/23: Luman responded no facilities in the construction area Centery Link and Level 3 combined to become Luman
Now Luman |  | Leslie Dingman
Miami Valley Lighting |  | Robyn Livesay |  |  | 2022-12-13 | No Response | 2023-02-08 | We will be contacting Steven Galyo to and others from AES about any lighting in the area to confirm, but they do not apear to be in conflict. We have not yet received any response from Miami Valley Lighting. | 2023-08-11 | 11/7/23: Update Email Sent Still have not received response, Austin Forwarded email on to Robyn Livesay

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary