## Ramp Closures-Detours
RAMP CLOSURE AND DETOUR TABLE
Interchange | Ramp | Closure Duration Allowed | Detour Route
SR-2 & SR-163 Spur | Ramp A - SR-2 EB to SR-163 Spur | Overnight Closures from 9PM to 6AM allowed Monday through Thursday | SR-2 EB to SR-53 NB to SR-163
| Ramp B - SR-163 Spur to SR-2 EB |  | SR-163 EB to SR-53 SB to SR-2 EB
| Ramp C - SR-2 WB to SR-163 Spur |  | SR-2 WB to SR-53 NB to SR-53
| Ramp D - SR-163 Spur to SR-2 WB |  | SR-163 EB to SR-53 SB to SR-2 WB
SR-2 & SR-53 | Ramp A - SR-53 SB to SR-2 EB |  | SR-2 WB to SR-53 Interchagne to SR-53 S Interchange to SR-2 EB
| Ramp B - SR-2 EB to SR-53 NB |  | SR-2 EB to SR-269 NB to SR-163 WB
| Ramp C - SR-53 SB to SR-2 WB |  | SR-2 EB to SR-269 S Interchange to SR-2 WB
| Ramp D - SR-2 WB to SR-53 NB |  | SR-2 WB to SR-163 Spur to SR-163 EB
SR-2 & SR-269 | Ramp A - SR-2 EB to SR-269 NB |  | SR-2 EB to SR-269 S Interchange to SR-2 WB
| Ramp B - SR-269 SB to SR-2 EB |  | SR-163 WB to SR-53 SB to SR-2 EB
| Ramp C - SR-269 SB to SR-2 WB |  | SR-2 EB to SR-269 S Interchange to SR-2 WB
| Ramp D - SR-2 WB to SR-269 NB |  | SR-2 WB to SR-53 NB to SR-163 EB
The contractor shall be responsible for all overnight closure detour signing

## Lane Value Contract
LANE VALUE CONTRACT TABLE
LANES/RAMPS TO BE OPENED TO TRAFFIC | RESTRICTED TIME PERIOD | TIME UNIT | DISINCENTIVE $ PER TIME PERIOD
ALL RAMPS AND INTERSECTIONS | HOLIDAYS PER HOLIDAY NOTE ON THESE PLANS | PER MINUTE | 100
ALL RAMPS AND INTERSECTIONS | 6am to 9pm Monday thru Thursday and all-day Fridays, Saturdays, and Sundays | PER 15 MINUTES | 500
2 lanes each direction on EB & WB SR-2 from SR 269 interchange (approximate station 1415+00) to east project limits | *Contract Start Date to Mon July 31, 2023: 6am to 9pm Monday thru Thursday and 24 hrs./day, Fridays, Saturdays, and Sundays | PER 15 MINUTES | 500
2 lanes each direction on EB & WB SR-2 from SR 269 interchange (approximate station 1415+00) to east project limits | May 15, 2024, to September 3, 2024: 6am to 9pm Monday thru Thursday and 24 hrs./day, Fridays, Saturdays, and Sundays | PER 15 MINUTES | 500