## Disposition of Comments
|  | WAY-23-6.63; PID 119931 | [5 empty] | Status Code = "Open" = Open, Remains Unresolved, Undrafted, and or Unverified | [6 empty] | Open | MarkedUp
[8 empty] | Status Code ="Closed" =Closed, Comment Resolved-Drafted and Verified | [6 empty] | Closed
|  | Disposition of Comments | [5 empty] | Status Code = "Resolve" =Comment remains unresolved and needs additional coordination for resolution | [6 empty] | Resolve
Ref. | Subject | Comment No. | Reference | Reviewer | Agency | Sheet # | Review Comment | Status Code | Response | Responsible Party | Sub. Responsible Party | Responsible Party Confirm | New Plan Sheet # | ADDRESSED BY | CHECKED BY
|  | 1 |  | Mark Mueller | ODOT | 1 | Per L&D 1302.3 this should be: 03 PRINCIPAL ARTERIAL (RURAL) | open |  | SDC
|  | 2 |  | Mark Mueller | ODOT | 1 | PITT TOWNSHIP | open |  | SDC
|  | 3 |  | Mark Mueller | ODOT | 1 | The plans will need to be signed and sealed digitally. | open
|  | 4 |  | Mark Mueller | ODOT | 1 | These should have areas. Refer to L&D 1302.11.2. | open |  | SDC
|  | 5 |  | Mark Mueller | ODOT | 1 | (NOI NOT REQUIRED) | open |  | SDC
|  | 6 |  | Mark Mueller | ODOT | 1 | Even though we are not using OHDOT standards, can these be added as cells per OHDOT cadd standards? | open |  | SDC
|  | 7 |  | Mark Mueller | ODOT | 1 | NONE REQUIRED | open | added NONE REQUIRED | SDC
|  | 8 |  | Mark Mueller | ODOT | 1 | Add: ADA DESIGN WAIVERS NONE REQUIRED | open | added ADA DESIGN WAIVERS NONE REQUIRED | SDC
|  | 9 |  | Mark Mueller | ODOT | 1 | Picture included of correct labeling for TH 62 | open | n/a
|  | 10 |  | mmueller | ODOT | 1 | TH 62 | open | revised text to TH 62 | SDC
|  | 11 |  | mmueller | ODOT | 1 | 0.63 | open | revised sht text to .63 | SDC
|  | 12 |  | mmueller | ODOT | 1 | .63 (Typ. to all sheets.) | open | revised all sht text to .63 | SDC
|  | 13 |  | Mark Mueller | ODOT | 2 | Remove Intersection 7 Label | open | label will be removed | SDC
|  | 14 |  | Mark Mueller | ODOT | 2 | Add "Begin Work" and Federal Project # flag | open |  | SDC
|  | 15 |  | SaraM | ODOT | 2 | Add Station/offset. Note which centerline this offset is from (RW or Const). | open |  | SDC
|  | 16 |  | SaraM | ODOT | 2 | add descriptions of the concrete monuments (what is in the top? "x" or brass mon in top? what is stamped on top if it is a marker? size (6" 12"?), condition, depth, found or set) and for the BM's (full description...ie: pony spike set in west face of Pole #...., chiseled x in NW corner of SE wingwall..... | open | Provided updated excel file. | surveyor?
|  | 17 |  | SaraM | ODOT | 2 | is this also CL of Construction? | open |  | SDC
|  | 18 |  | SaraM | ODOT | 2 | Also CL of Construction? | open |  | SDC
|  | 19 |  | SaraM | ODOT | 2 | are these at Grid? or in Project datum? Looks like Survey Parameters show a 1.000032 scale factor has been applied? | open | The coordinates listed are based on ODOT Wyandot LDP. | surveyor?
|  | 20 |  | SaraM | ODOT | 2 | carry elevation to hundredths(2 places) . Carry N&E to thousandths (3 places) | open | Okay. | surveyor?
|  | 21 |  | mmueller | ODOT | 2 | Per L&D 1303.6, show both stationing and SLM. The Begin Project SLM should be 6.63 based on the intersection point being at 6.691. | open |  | SDC
|  | 22 |  | mmueller | ODOT | 2 | Per L&D 1303.6, show both stationing and SLM. The End Project SLM should be 6.75 based on the intersection point being at 6.691. | open |  | SDC
|  | 23 |  | Mark Mueller | ODOT | 3 | Delete guardrail and move break point to the edge of the 10' dimension | open |  | SDC
|  | 24 |  | Mark Mueller | ODOT | 3 | Remove label "B Guardrail at CR 113" | open |  | SDC
|  | 25 |  | Mark Mueller | ODOT | 3 | Should this be changed to CL of pavement? Or, should the dimension be change? Based on the Grading Plan the left dimension is 3.76' and the right dimension is 10.23'. | open |  | SDC
|  | 26 |  | Mark Mueller | ODOT | 3 | TH 62 | open |  | SDC
|  | 27 |  | Mark Mueller | ODOT | 3 | Remove label "± 10' East of US 23" | open |  | SDC
|  | 28 |  | mmueller | ODOT | 3 | TH 62 | open |  | SDC
|  | 29 |  | mmueller | ODOT | 3 | CH 62 | open |  | SDC
|  | 30 |  | Mark Mueller | ODOT | 4 | 14' | open |  | SDC
|  | 31 |  | Mark Mueller | ODOT | 4 | ODOT's direction to follow the Stage 2 plans developed under PID 109362 should be disregarded for the proposed pavement buildup. The buildup shown is more appropriate for the RCUT that was part of PID 109362 but excessive for a cul-de-sac. We recommend using ODOT's Simplified Pavement Designs for Short Projects which would be 1.25" of Item 441 surface on 4" of Item 301 base. | open |  | SDC
|  | 32 |  | Mark Mueller | ODOT | 4 | Picture of pay item for surface course to be used | open | n/a
|  | 33 |  | Mark Mueller | ODOT | 4 | Picture of pay item for concrete base to be used | open | n/a
|  | 34 |  | Mark Mueller | ODOT | 4 | Replace surface course item with pictured pay item. See comment 31 for thickness | open |  | SDC
|  | 35 |  | Mark Mueller | ODOT | 4 | Remove intermediate course label from typical sections/legend | open |  | SDC
|  | 36 |  | Mark Mueller | ODOT | 4 | Replace concrete base item with pictured pay item. See comment 31 for thickness | open |  | SDC
|  | 37 |  | Mark Mueller | ODOT | 4 | Rounding? | open |  | SDC
|  | 38 |  | mbrunet | ODOT | 4 | I concur with this suggested pavement design from the simplified pavement design. This design is adequate buildup for this route. | open |  | SDC
|  | 39 |  | TZURA | ODOT | 4 | Not sure what the 0.10 Min. is? | open |  | SDC
|  | 40 |  | Mark Mueller | ODOT | 5 | TH? | open |  | SDC
|  | 41 |  | Mark Mueller | ODOT | 5 | Picture of PPE note that is to be included. SEE COMMENT 42 | open | n/a
|  | 42 |  | Mark Mueller | ODOT | 5 | Please include the District's PPE note. I will provide the Word document for your use. | open |  | SDC
|  | 43 |  | SaraM | ODOT | 5 | use survey parameters WORD document that was provided. The G105 note has two versions now: one for State Plane projects, one for OCCS (akaLDP) project. This is a OCCS(LDP) project, the word doc provided is in the G105 note format for OCCS. See Survey Specs Appendix I and L& D manual. | open |  | SDC
|  | 44 |  | SaraM | ODOT | 5 | Picture of survey parameters note that should be included | open | n/a
|  | 45 |  | SaraM | ODOT | 5 | should only read Type B | open |  | SDC
|  | 46 |  | SaraM | ODOT | 5 | see correct format on WORD doc provided | open |  | SDC
|  | 47 |  | TZURA | ODOT | 5 | Topsoil should for use as directed by the Engineer. Is it even needed at this location? | open |  | mike?
|  | 48 |  | TZURA | ODOT | 5 | Any Geotextile Fabric for the undercut? | open |  | SDC
|  | 49 |  | Mark Mueller | ODOT | 6 | If there are lane closures couldn't the drop off be as much as 24" since the horizontal distance "X" would be greater than 12'? Maybe just note that the contractor is responsible for maintaining drop off depths in accordance with MT-101.90. | open
|  | 50 |  | Mark Mueller | ODOT | 6 | Add the Portable Changeable Message Sign, As Per Plan note and include a quantity for 1 PCMS in each direction. | open
|  | 51 |  | Mark Mueller | ODOT | 6 | Add the Law Enforcement Office (With Patrol Car) for Assistance During Construction Operations note and include a quantity. | open
|  | 52 |  | Mark Mueller | ODOT | 7 | picture of pay items that should be included. See comment 53 | open | n/a
|  | 53 |  | Mark Mueller | ODOT | 7 | Please add these pay items under the roadway section: | open |  | SDC
|  | 54 |  | Mark Mueller | ODOT | 7 | These items should be modified per comments on sheet 4. | open |  | SDC
|  | 55 |  | Mark Mueller | ODOT | 7 | This item should be deleted per comments on sheet 4. | open |  | SDC
|  | 56 |  | Mark Mueller | ODOT | 7 | The lump sum MOT pay item should be under the Incidental heading. | open |  | SDC
|  | 57 |  | mmueller | ODOT | 7 | 01/SAF/21 | open |  | SDC
|  | 58 |  | Mark Mueller | ODOT | 8 | TH | open |  | SDC
|  | 59 |  | Mark Mueller | ODOT | 8 | TH | open |  | SDC
|  | 60 |  | Mark Mueller | ODOT | 8 | 49? | open |  | SDC
|  | 61 |  | Mark Mueller | ODOT | 8 | Where is this quantity coming from? | open | EX 8" PIPE-labeled | SDC
|  | 62 |  | Mark Mueller | ODOT | 8 | The width at the tie in location is 14' | open | length plus edges | SDC
|  | 63 |  | Mark Mueller | ODOT | 8 | Based on the station to station lengths, each length appears to be +8' | open | length plus edges | SDC
|  | 64 |  | Mark Mueller | ODOT | 8 | Change to 301 | open |  | SDC
|  | 65 |  | Mark Mueller | ODOT | 8 | Update based on comment on sheet 4 | open |  | SDC
|  | 66 |  | Mark Mueller | ODOT | 8 | The quantity will need to be updated for 1 application of tack coat. | open |  | SDC
|  | 67 |  | Mark Mueller | ODOT | 9 | Label and designate the paved gutter for removal? Provide width dimension since it is being paid for in length? | open |  | SDC
|  | 68 |  | Mark Mueller | ODOT | 9 | Overlapping text | open |  | SDC
|  | 69 |  | Mark Mueller | ODOT | 9 | TH | open |  | SDC
|  | 70 |  | Mark Mueller | ODOT | 9 | Pipes labeled twice | open |  | SDC
|  | 71 |  | Mark Mueller | ODOT | 9 | Overlapping text | open |  | SDC
|  | 72 |  | Mark Mueller | ODOT | 9 | Add "Begin Work" and Federal Project # flag | open |  | SDC
|  | 73 |  | Mark Mueller | ODOT | 9 | Pipe labeled twice | open |  | SDC
|  | 74 |  | Mark Mueller | ODOT | 9 | In my opinion you can turn off the COP (crown) line and the pavement markings for this sheet. | open |  | SDC
|  | 75 |  | SaraM | ODOT | 9 | Are there any C/L concrete monuments that might be disturbed with construction? If so, add a table with coordinates (could be incorporated with the control table on Sheet 2) and a quantity added to the Gen Summary. See Project Control example to left. To save space, columns that do not pertain to the project can be omitted. We have a template of the table in Excel that can be provided. | open | See comment provided on pdf markup. | surveyor?
|  | 76 |  | SaraM | ODOT | 9 | Picture that comment 75 is referencing | open |  | surveyor?
|  | 77 |  | SaraM | ODOT | 9 | Typ.: Is this also C/L of Construction? | open |  | SDC
|  | 78 |  | Mark Mueller | ODOT | 9 | Label station | open |  | SDC
|  | 79 |  | mpickeri | ODOT | 9 | OH-E | open |  | SDC
|  | 80 |  | Mark Mueller | ODOT | 11 | Comment typical to all TH-62 cross sections: Why does the undercut appear to not extend under the entire pavement limits . | open |  | SDC
|  | 81 |  | mmueller | ODOT | 11 | Consider making the description for the undercutting similar to the description below. This points the contractor to the note on sheet 5. The note on sheet 5 says that the Engineer will identify the actual limits based on the proof rolling. This location would only need Geotextile fabric rather than Geogrid. See picture included | open |  | SDC
|  | 82 |  | mmueller | ODOT | 12 | Consider making the description for the undercutting similar to the description below. This points the contractor to the note on sheet 5. The note on sheet 5 says that the Engineer will identify the actual limits based on the proof rolling. This location would only need Geotextile fabric rather than Geogrid. See picture included | open |  | SDC
|  | 83 |  | Mark Mueller | ODOT | 13 | Comment typical to all US-23 cross sections: Considering identify the saw cut line/pavement removal areas. | open |  | SDC
|  | 84 |  | Mark Mueller | ODOT | 16 | Can ditch grading be extended to Sta. 297+00 so that an absolute minimum ditch slope of 0.25% can be met? | open |  | SDC
|  | 85 |  | Mark Mueller | ODOT | 18 | Show existing ditch lines. Show drainage arrows and show proposed ditch connecting to existing ditch lines | open |  | SDC
|  | 86 |  | Mark Mueller | ODOT | 18 | Show existing ditch lines. Show drainage arrows and show proposed ditch connecting to existing ditch lines | open |  | SDC
|  | 87 |  | Tim B | ODOT | 19 | 36" x 36" 36" x 18" | open
|  | 88 |  | Tim B | ODOT | 19 | District 1 uses 3 pd post only | open
|  | 89 |  | Tim B | ODOT | 19 | 36" x 36" | open
|  | 90 |  | Tim B | ODOT | 19 | 9 4.5 | open
|  | 91 |  | Tim B | ODOT | 19 | 9 | open
|  | 92 |  | Tim B | ODOT | 19 | move to ground mounted support no. 3 pay item | open
|  | 93 |  | Tim B | ODOT | 19 | move to ground mounted support no. 3 pay item | open
|  | 94 |  | Tim B | ODOT | 19 | move to ground mounted support no. 3 pay item | open
|  | 95 |  | Tim B | ODOT | 20 | signs are 36" x 36" in the the field | open
|  | 96 |  | Tim B | ODOT | 20 | why not replace this sign as well | open
|  | 97 |  | Tim B | ODOT | 20 | upsize to 36" x 36" and use 2 3# post | open
|  | 98 |  | Tim B | ODOT | 20 | move sign away from cul-de-sac | open
|  | 99 |  | Tim B | ODOT | 20 | will you be removing existing pavement markings? | open
|  | 100 |  | Tim B | ODOT | 20 | sign S-3 will be located 1.35 miles to west, it looks like it is ,located at this location. Put at top of page | open
|  | 101 |  |  | ODOT | 2 | Station needed where cul-de-sac begins | open |  | SDC
|  | 102 |  |  | ODOT | 3 | change SR to CR in Typical section label | open |  | SDC
|  | 103 |  |  | ODOT | 6 | remove "is 3" or less" from maintaining traffic note and replace with "follows SCD MT 101.90" | open
|  | 104 |  |  | ODOT | 6 | Fix spacing in notification of traffic restrictions note | open
|  | 105 |  |  | ODOT | 7 | Quantity for Water in maintenance of traffic should be 3 Mgal | open |  | SDC
|  | 106 |  |  | ODOT | 16 | delete linework for cul-de-sac in the cross sections of US 23 | open |  | SDC