## Sheet1
Utilty | Contact Information | Facilities | Status /Comments | Relocation's
ALTA FIBER (CINCINNATI BELL TELEPHONE) | ALTA FIBER (CINCINNATI BELL TELEPHONE) 221 E 4TH STREET (BUILDING 121-900) CINCINNATI, OH 45202 BRECK M. COWAN, CPM O: (513) 565-7187 C: (513) 702-1040 BRECK.COWAN@CINBELL.COM ROADPROJECTS@CINBELL.COM | EXISTING AERIAL AND SUBSURFACE FACILITIES. AERIAL LINES ARE LOCATED ON POLES ALONG SOUTH SIDE OF SR-133 AS SHOWN IN PLANS. TWO SUBSURFACE DUCT BANK AND VAULTS IN THE PROJECT LIMITS ALONG SOUTH SIDE OF SR-133 IN THE SH EASEMENT. STA 844+15 RT (WITHIN COMMUNITY PARK DRIVE) AND STA 859+10 RT THIS MH IS ADJUSTED TO GRADE (UT-7) | ALTA FIBER VAULT MANHOLES WILL BE ADJUSTED BY CONTRACTOR TO MATCH PATH SURFACE. PLANS INCLUDE PAY ITEMS FOR MANHOLE ADJUSTMENT UT-5 STA 850+99 RT, UT-7 STA 859+10 RT, AERIAL RELOCATION FOR DUKE POLES PENDING CONFIRMATION FROM DUKE ON NEW POLES | NO RELOCATIONS OF SUBSURFACE LINES. AERIAL LINE RELOCATION WILL BE COORDINATED WITH DUKE WHERE CO-LOCATED WITH DUKE POLES
SPECTRUM/CHARTER COMMUNICATIONS | SPECTRUM/CHARTER COMMUNICATIONS JIM OREILLY JIM.OREILLY@CHARTER.COM (513) 386-5272 | EXISTING FIBER CO LOCATED ON DUKE POLES. WILL RELOCATE PENDING COORDINATION WITH DUKE ON NEW POLE LOCATIONS | PENDING CONFIRMATION FROM DUKE ON STATUS OF POLE RELOCATIONS | RELOCATION WILL BE COORDINATED WITH DUKE WHERE CO-LOCATED ON DUKE POLES
CLERMONT COUNTY OFFICE OF ENVIRONMENTAL QUALITY | 4400 HASKELL LANE BATAVIA, OH 45103 HANNAH LUBBERS HLUBBERS@CLERMONTCOUNTYOHIO.GOV (513) 732-7894 EXT. 4 | WATER QUALITY MONITORING STATION AND RIVER GAGE. LOCATED ADJACENT TO EXISTING BRIDGE ABUTMENT STA 841+90 RT | WATER QUALITY STATION WILL REMAIN IN PLACE DURING AND AFTER CONSTRUCTION. MINOR GRADING EAST OF STATION. MAINTAIN ACCESS AT ALL TIMES, NO WORK BETWEEN STATION AND RIVER. | NONE REQUIRED
ELECTRIC/STREET LIGHTING | DUKE ENERGY SHANE ERHART 2010 DANA AVE, EF324 CINCINNATI, OHIO 45207 SHANE.ERHART@DUKE-ENERGY.COM (513) 508-9609 (EMERGENCIES: 651-4182) | EXISTING PRIMARY AND SECONDARY DISTRIBUTION OVERHEAD WITHIN PROJECT LIMITS. STREET LIGHT POLES ALONG SR-133 FUNDED BY VILLAGE OF WILLIAMSBURG. | MOST DUKE POLES AND OVERHEAD ARE BEING RELOCATED BY DUKE AS PART OF SEPARATE PROJECT ALONG SR-133. POLE RELOCATIONS WITHIN THE PROJECT AREA COORDINATED WITH DUKE AND WILL BE COMPLETE PRIOR TO CONSTRUCTION. EXISTING STREET LIGHT POLES WILL BE REMOVED AND COLLOCATED WITH NEW DUKE POLES IN THE VICINITY. DUKE HAS REVIEWED PROPOSED GRADING PLANS AND EXISTING OR NEW POLES WILL ACCOMMODATE PROPOSED GRADING. | MOST EX. POLES RELOCATED BY DUKE AS PART OF SEPARATE DISTRIBUTION PROJECT IN SR133 CORRIDOR. VILLAGE LIGHT POLES RELOCATED OR CONSOLIDATED TO NEW POLE IN SAME VICINITY.
DUKE ENERGY GAS | DUKE ENERGY GAS BRIAN HOLLMANN 139 E. FOURTH ST., RM.460A CINCINNATI, OHIO 45202 BRIAN.HOLLMANN@DUKE-ENERGY.COM (513) 906-0128 | EXISTING GAS DISTRIBUTION LINE IN PROJECT LIMITS SOUTH SIDE OF SR-133 | PROPOSED RELOCATION (LOWERING) OF GAS DISTRIBUTION LINE SCHEDULED FOR NOVEMBER 2023. ADJUSTMENT OF EXISTING VALVES AS SHOWN IN PLANS WILL BE CONCURRENT WITH CONSTRUCTION CONTRACT FOR PATH. | DUKE IS LOWERING 75' OF EXISTING 6" DISTRIBUTION LINE IN VICINITY OF PROPOSED DITCH STA 844+55 RT. IN EIXSTING SH EASEMENT RELOCATION PLANS PROVIDED 10-04-23
VILLAGE OF WILLIAMSBURG WATER AND SEWER DEPARTMENT | VILLAGE OF WILLIAMSBURG WATER AND SEWER DEPARTMENT 107 WEST MAIN STREET, WILLIAMSBURG OH • 45176 KYLE CRIBBET KCRIBBET@WILLIAMSBURGOHIO.ORG (513) 724-6107 | EXISTING SANITARY SEWERS LOCATED IN PROJECT LIMITS ALONG SR-133. SANITARY SEWERS WIL NOT BE AFFECTED THE PROJECT. SANITARY MANHOLES WILL BE ADJUSTED TO PROPOSED PATH GRADE WHERE INDICATED | PLANS INCLUDE PAY ITEMS FOR MANHOLE ADJUSTMENT UT-1 STA 844+64 RT, UT-2 STA 844+75 RT, UT-4 STA 847+89 RT, UT6 STA 851+88 RT, | NONE REQUIRED, ADJUST MANHOLES AT LOCATIONS NOTED
VILLAGE OF WILLIAMSBURG WATER AND SEWER DEPARTMENT | VILLAGE OF WILLIAMSBURG WATER AND SEWER DEPARTMENT 107 WEST MAIN STREET, WILLIAMSBURG OH • 45176 KYLE CRIBBET KCRIBBET@WILLIAMSBURGOHIO.ORG (513) 724-6107 | EXISTING WATER MAIN AND SERVICE LINES LOCATED IN PROJECT LIMITS ALONG SR-133. 2 INCH LATERAL SERVICE LINE NEAR DRIVE 7 MAY NEED TO BE LOWERED. | ADDED GENERAL NOTE TO CONFIRM RELOCATION OF LATERAL SERVICE LINE UT-8 WITH VILLAGE WATER DEPARTMENT. DEPTH AND MATERIAL TO BE CONFIRMED IN THE FIELD. CONFIRMED EXISTING WATER METER NOT IN SERVICE, REMOVED R-5 STA 844+51 RT | WATER MAINS UNAFFECTED, PLANS INCLUDE PAY ITEMS FOR REPLACEMENT OF 20 FT 2" WATER SERVICE LINE UT-8 STA 855+68 RT DUE TO POSSIBLE CONFLICT WITH DRIVE PIPE. ALSO INCLUDES PAY ITEM TO REMOVE AND RESET WATER METER UT-3 STA. 846+82 RT DUE TO GRADE CHANGES.