## Slide 1: CUY-90-6.69 pre-bid meeting – PID 76779
March 11, 2025

## Slide 2: AGENDA
Overview
Schedule
Maintenance of Traffic
Drainage
Tree Clearing

## Slide 3
OVERVIEW

## Slide 4: overview
IR 90 from Hilliard Blvd. to West Blvd (4.6 mi)

## Slide 5: overview
Full-depth pavement replacement
New Drainage
Bridge vertical clearance improvements
Bridge overlays and substructure patching
  Rocky River bridge work is more in-depth
New Lighting
New Signing

## Slide 6
SCHEDULE

## Slide 7: schedule
4/17/25 – Sale
4/28/25 – Award
5/19/25 – Begin Construction
8/1/28 – End Construction

## Slide 8
  MAINTENANCE OF TRAFFIC

## Slide 9: Maintenance of traffic
  EB lane closure allowed during Phase 1 & Winter Phase 1 into Phase 2

## Slide 10: Maintenance of traffic
  EB lane closure
    Allows trunk line installation from Rocky River east to W. 140th St.

## Slide 11: Maintenance of traffic
  Short term WB lane closure at McKinley Ave.

## Slide 12: Maintenance of traffic
  Short term WB lane closure at McKinley Ave.
    Bore/Jack near Riverside Drive

## Slide 13: Maintenance of traffic
Ramp Phasing
  Work window contract revised on sheet 56A
    Ramps to be built in Phase 1:
      Hilliard Blvd. Ramp HA
      West Blvd. Ramp W13

## Slide 14: Maintenance of traffic
Ramp Phasing
  Work window contract revised on sheet 56A
    Ramps that may be built either in Phase 1 or in phase with outside lane & shoulder reconstruction:
      McKinley Ave. – Ramps MC & ME
      Warren Road – Ramps W1 & W1A
      W. 140th St. – Ramp 140-4
      W. 117th St. – Ramps 117-5 & 117-9

## Slide 15
DRAINAGE

## Slide 16: drainage
Drainage
  Reconfigured bore/jack near Riverside Drive

## Slide 17: drainage
Drainage
  Reconfigured manholes at overhead bridges due to limited clearances

## Slide 18: drainage
New Maintenance of Drainage Phasing Table

## Slide 19
TREE CLEARING

## Slide 20: Tree clearing
Trees have been cleared; Stumps remain
  See MOT Phase 1 plans

## Slide 21: Thank you