## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | MOT-Spinning Road PID 113392 | [5 empty] | Last Updated By: | BAW
PM: | MJT |  | OUPS Ticket: | [6 empty] | On: | 2022-10-13
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
Dayton Power & Light | 937-331-4521 | William Gourly |  |  | 2020-11-23 |  | 2021-09-13 |  | 2022-02-08
AES |  | Bill Ward |  |  | 01-11-2021: sent follow up email |  |  |  | Working with Bill Ward to relocate an AES transmission pole if MCES does not allow us to place a MH in close proximety to the existing water line to avoid relocating the pole 2/8/22 Montgomery County Water approved the manhole location, the pole will not need relocated, only stabilized during the installation of the storm sewer.
Crown Castle Fiber | 585-445-5813 | Jon Tarnowski |  |  | 2020-11-23 |  | 2021-09-13 |  | 2022-01-21
|  | Craig Wheeler |  |  | 01-11-2021: sent follow up email |  |  |  | Sent both Jon and Craig a pdf displaying the areas of conflict and told them we will need the fiber optic to be relocated for the storm sewer extention (email saved in utility folder) (utility relocation plans must be submitted to ODOT prior to construction) Called Jon Tarnowski on 2/9/2022 fallowing up on email sent on 1/21/2022 and was directed to Craig Brown as a better point of contact for this project area
01-13-2021: recived as-builts of the fiber optic running the length of the project and updated the depths of the fiber optic in the drawing (saved email in the folder)
2/10/2022 sent email to Craig Brown with areas of fiber optic conflicts 4/19/22 received relocation plans from Craig Snell to move the fiber and the pull box that are in conflict with the proposed storm sewer. This relocation will be completed prior to construction start which is 8/1/23
Charter Communication | 937-396-8372 | Jacob Houdeshell |  |  | 2020-11-23 |  | 2021-09-13 |  | 2022-01-25
(Spectrum) | 937-396-8591 | Ein Whatley |  |  | 01-11-2021: sent follow up email |  | 9-14-2021: Ein Whatley asked if any poles would need moved. I responded to let him know the pole at sta 36+80 will need to be relocated because the storm sewer will be running behind the curb |  | 1/21/2022 send Ein an email notifying him that the cable and a pull box will need to be relocated to allow room for the storm sewer installation 1/25/2022 sent Ein another email containing the location of a pole that will need to be relocated prior to construction (utility relocation plans must be submitted to ODOT prior to construction) 4/19/22 the bull box belongs to Crown Castel, not Spectrum
AT&T - Transmission | 770-584-7083 | Chad Harkness |  |  | 2020-11-23 |  | 2021-09-13
| 614-392-2873 | Austin Stansel |  |  | 11-24-2020: received map showing line in old RR ROW |  | 9-14-2021: response from Austin Stansel on behalf of Pat Sutton confirming that nothing had changed since stage 1 submission. Austin Stensel will be confirming that there will be no conflictls
Centerpoint Energy | 937-312-2521 | Greg Fishman |  |  | 2020-11-23 |  | 2021-09-13 |  | 2022-01-25
| 937-312-2539 | Jeff Pike |  |  | 12-11-2020: Jeff Pike sent Stage 1 comments (email is saved in the utility folder) |  | 9-14-2021: Jeff Pike noted that we extended storm sewer across Sheller Ave. sent him an updated cad file to coordinate the test holes of the gas at sta 36+00 and sta 40+00 |  | Sent Jeff Pike a follow-up email to see where he was at with the relocation plans that we talked about on 10/6/2021 (utility relocation plans must be submitted to ODOT prior to construction) Centerpoint plans to have relocation plans ready before final tracings
12-15-2020: I responded to his comments and sent him a cad file for coordination and updated the plans to show the sizes of the gas mains within the project limits
10-6-2021 Received test holes for confirming that there would be lowering of 4" gas main at approx. Sta. 36+00 and the 8" gas main at approx. sta. 40 will be relocated east away from the 12" outlet
7/27/22 sent cad file to Whitney Land who is working with Centerpoint on their relocations . Jeff pike has sent plans and intends to have relocations complete before the sale date.
10-6-2021: Asked that Jeff Pike get us relocation plans before final tracings submittal and have the work completed prior to the start of construction
Montgomery County Water | 937-781-2631 | Edward Schlaack |  |  | 2020-11-23 |  | 2021-09-13 |  | 02/08/2022: Reached out to Ed Schlaack and confirmed that they will allow us to place a MH in close proximety to existing water line to avoid moving the AES Transmission pole
01-08-2021: Ed Schlaack confirmed water and sanitary look to be shown accurately
AT&T of Ohio | 937-296-3894 | Jess Wead |  |  | 2020-11-23 |  | 2021-09-13 |  | Reached out to Jesse Wead about relocations on 1/26/2022 to find out if the cable in conflict belongs to AT&T
[5 empty] | 12-21-2020: received stage 1 mark-ups, lots of missing facilities, contact from Kieth Stewart and David Pimentel with USIC to get facilities marked |  | 09-13-2021: Jesse Wead did not see all of the att lines that were picked up when we collected more topo on 2-2-2021.
9-14-2021: Called Jesse Wead and fixed the two locations that were not shown correctly. Sent him a follow up email with after the corrections to the plans were made. Received confirmation email that the att lines were now shown correctly in our plans.
01-11-2021: I sent out a follow up email to see if the utilities were marked or anything else was found out
01-11-2021: working with Jesse Wead and David Pimentel to get AT&T lines marked and MJT spoke to David Pimentel
1-22-2021: ATT Lines lines have been marked in the field and we sent a crew out to pick up the additional topo
Level 3 Communication | 513-644-8933 | Terry Spaw |  |  | 2020-11-23 |  | 2021-09-13
Sent to NationalRelo@centurylink.com
and relocations@lumen.com
11-24-2020: Renoy Thomas: confirmed they do not have facilities in the project area
City of Riverside | 937-233-1801 | Kathy Bartlett |  |  | 2020-11-23 |  | 2021-09-13
01-11-2021: sent follow up email
09-09-21: City has no utilities in area besides storm sewer
Miami Valley Lighting | 937-259-7192 | Robyn Livesay |  |  | 2020-11-23 |  | 2021-09-13
01-11-2021: sent follow up email
01-12-2021: received location of street lights in project area from Steven Galyo and they match what we had in the drawing (email saved in folder)

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary