## Sheet1
[5 empty] | OUPS Ticket B201200580-00B |  |  | Last Updated: | AMT | 2022-06-01
OTT-51-03.85, PID: 80032
Stakeholder | Contact | Telephone | OUPS Request Utility Plans | Received Utility Plans or Positive Response | AER Plans Sent | Comments Received | Stage 2 Plans Sent | Comments Received | Stage 3 Plans Sent | Comments Received | Remarks | Attachments | Need followup?
Name and Address
[11 empty] | Received the response on 01/10/22. Aerial Fiber and Electric Transmission lines are within the limits of the bridge. Mary Walton is the contact for First Energy Transmission. We held a utility coordination with First Energy and Frontier on 8/21/23 to discuss the relocations of the poles. We have sent her the CADD files and they are currently working on relocation plans for their facilities. |  | YES
First Energy Electric |  | 419-249-5218
6099 Angola Rd. | Randall Swope | rrswope@firstenergycorp.com | 2022-01-06 | 2022-01-10 | 2022-07-01 |  | 2022-11-02 |  | 2023-07-12
Holland, Ohio 43528 | Timothy Mizer | tmizer@firstenergycorp.com
| Mary Walton | mwalton@firstenergycorp.com
[11 empty] | Amplex has installed 96ct buried fiber optic cable along the east side of OH-51 between Opfer-Lentz Rd and W Fulkert Rd. Attachment shows the location in the plan view and the cross sections. |  | NO
Amplex Internet, Inc. |  | 419-837-5015
22690 Pemberville Rd. | Kathy Baugher | kbaugher@amplex.net | 2022-01-06 | 2022-01-10 | 2022-07-01 | 2022-07-13 | 2022-11-02 |  | N/A |  |  | yes
Luckey, Ohio 43443
Received response on 01/14/2022. No conflict has been found.
Toledo Edison - A First Energy Company
|  |  | 2022-01-06 | 2022-01-14 | 2022-07-01 |  | 2022-11-02
[11 empty] | Copper Cables are within the limits of bridge. Pole at approximate location 104+05 LT is owned by Frontier but has we need input on relocation from First Energy Transmission as it will need to continue to act as a guide pole. We held a utility coordination with First Energy and Frontier on 8/21/23 to discuss the relocations of the poles. Frontier is planning on placing their pole further north and west of where it currently is. |  | YES
Frontier Communications |  | 419-841-7281
3126 McCord Rd. | Amy Roth | amy.l.roth@ftr.com | 2022-01-06 | 2022-01-24 | 2022-07-01 | 2022-07-05 | 2022-11-02 | 2022-11-02 | 2023-07-17 |  |  | yes
Toledo, Ohio 43617
[11 empty] | Received response on 01/14/2022. No conflict has been found. |  | NO
AT&T |  | 419-245-5004
130 N. Erie Street (Room 714) | Robert Fey | r1281@att.com | 2022-01-06 | 2022-01-14 | 2022-07-01 |  | 2022-11-02 |  | N/A
Toledo, Ohio 43624