ITEM 614, MAINTAINING TRAFFIC

A MINIMUM OF 1-LANE OF TRAFFIC IN EACH DIRECTION SHALL BE MAINTAINED AT ALL TIMES ON S.R. 93 BY USE OF THE EXISTING PAVEMENT, STANDARD DRAWING MT-97.12, AND DETAILS IN THESE PLANS.

TWO-WAY TRAFFIC SHALL BE MAINTAINED AT ALL TIMES EXCEPT THAT

ONE-WAY TRAFFIC WILL BE PERMITTED FOR MINIMUM PERIODS OF TIME CONSISTENT WITH THE REQUIREMENTS OF THE SPECIFICATIONS FOR PROTECTION OF COMPLETED ASPHALT CONCRETE COURSES INCLUDING REPAIRS.

AT NO TIME SHALL TRAFFIC BE MAINTAINED ON THE PLANED SURFACE,

AT LEAST ONE COURSE OF ASPHALT CONCRETE SHALL BE IN PLACE BEFORE OPENING TO TRAFFIC. THIS RULE DOES NOT APPLY TO PLANING AT BRIDGES OR ACROSS BRIDGES UNLESS THE BRIDGE IS BEING TREATED THE SAME AS THE ADJACENT ROADWAY.

LENGTH AND DURATION OF LANE CLOSURES AND RESTRICTIONS SHALL BE

AT THE APPROVAL OF THE ENGINEER. THE MAXIMUM LANE CLOSURE LENGTH SHALL BE PER MT-97.12. IT IS THE INTENT TO MINIMIZE THE IMPACT TO THE TRAVELING PUBLIC. LANE CLOSURES OR RESTRICTIONS OVER SEGMENTS OF THE PROJECT, IN WHICH NO WORK IS ANTICIPATED WITHIN A REASONABLE TIME FRAME, AS DETERMINED BY THE ENGINEER, SHALL NOT BE PERMITTED.  THE LEVEL OF UTILIZATION OF MAINTENANCE OF TRAFFIC DEVICES SHALL BE COMMENSURATE WITH THE WORK IN PROGRESS.

TEMPORARY TRAFFIC SIGNALS SHALL BE USED FOR THE EDGE REPAIR WORK

AS SHOWN ON SHEETS 9-10.

TEMPORARY TRAFFIC SIGNALS MAY BE USED FOR BRIDGE DECK SEALING

AND WATERPROOFING. THEY SHALL BE REMOVED ONCE MATERIAL HAS CURED, AS DIRECTED BY THE ENGINEER.

ALL WORK AND TRAFFIC CONTROL DEVICES SHALL BE IN ACCORDANCE WITH CMS 614 AND OTHER APPLICABLE PORTIONS OF THE SPECIFICATIONS, AS WELL AS THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES.  PAYMENT FOR ALL LABOR, EQUIPMENT AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR ITEM 614, MAINTAINING TRAFFIC, UNLESS SEPARATELY ITEMIZED IN THE PLAN.

WORK RESTRICTIONS

DECK SEALING ON BRIDGES PER-93-0500 AND PER-93-0516 SHALL NOT

OCCUR SOONER THAN 5/1/25.

ALL WORK INSIDE NEW LEXINGTON SHALL BE COORDINATED WITH THE VILLAGE. THE CONTRACTOR SHALL SUSPEND WORK DURING FESTIVALS

OR SPECIAL EVENTS OCCURING INSIDE THE VILLAGE, AT APPROVAL OF

THE ENGINEER.

OVERNIGHT TRENCH CLOSING

THE EDGE REPAIR WORK SHALL BE COMPLETED TO A DEPTH OF NO MORE THAN 12 INCHES BELOW THE EXISTING PAVEMENT SURFACE BY THE END

OF EACH WORK DAY. NO TRENCH SHALL BE LEFT OPEN OVERNIGHT EXCEPT FOR SECTION INSIDE THE WORK ZONE (2,000’ MAXIMUM LENGTH).

IN CASE WORK MUST BE SUSPENDED BECAUSE OF INCLEMENT WEATHER

OR OTHER REASONS, THE TRENCH FOR THE UNCOMPLETED EDGE REPAIR

SHALL BE BACKFILLED AT THE DIRECTION OF THE ENGINEER.

NOTIFICATION OF ROAD CLOSURE OR RESTRICTIONS

THE CONTRACTOR WILL ADVISE THE PROJECT ENGINEER A MINIMUM OF TWENTY-ONE (21) DAYS PRIOR TO THE FOLLOWING:  THE START OF CONSTRUCTION ACTIVITIES, LANE RESTRICTIONS, LANE CLOSURES, AND/OR ROAD CLOSURES.  THE PROJECT ENGINEER WILL FORWARD THIS INFORMATION TO THE FOLLOWING:

DISTRICT PUBLIC INFORMATION OFFICER (PIO) BY FAX AT (614) 887-4510

OR EMAIL AT D05.pio@dot.ohio.gov

DISTRICT PERMIT SECTION BY FAX AT (614) 887-4525 OR EMAIL AT brian.bosch@dot.ohio.gov

CENTRAL OFFICE SPECIAL HAUL PERMITS SECTION BY FAX AT (614) 728-4099

OR EMAIL AT hauling.permits@dot.ohio.gov

THE PIO WILL, IN TURN, NOTIFY THE PUBLIC, THE LOCAL EMERGENCY SERVICES, AFFECTED SCHOOLS AND BUSINESSES, AND ANY OTHER IMPACTED LOCAL PUBLIC AGENCY OF ANY OF THE ABOVE-MENTIONED ITEMS, VIA MEDIA SOURCES.

BUTT JOINT

# A BUTT JOINT WILL BE REQUIRED AT THE LOCATIONS SPECIFIED BELOW AND

# PER STANDARD DRAWING BP-3.1 UNLESS OTHERWISE SHOWN IN THE PLANS.

# THE MINIMUM ASPHALT WEDGE LENGTH AT BUTT JOINTS SHALL BE 10’.

# THE GRINDING FOR BUTT JOINTS SHALL BE INCLUDED WITH ITEM 254,

# PAVEMENT PLANING, ASPHALT CONCRETE.

| LOC. | ROUTE | DESCRIPTION | S.L.M. | ITEM 614 ASPHALT CONCRETE FOR MAINTAINING TRAFFIC CU. YD. |
| --- | --- | --- | --- | --- |
| 1A | S.R. 93 | BEGIN WORK | 0.00 | 2.0 |
|  |  | BRIDGE: PER-93-5.00 | 5.00 | 2.0 |
|  |  | BRIDGE: PER-93-5.16 | 5.16 | 2.0 |
|  |  | TOTAL |  | 6.0 |
| 1B | S.R. 93 | BRIDGE: PER-93-6.18 | 6.18 | 4.0 |
|  |  | TOTAL |  | 4.0 |

# COOPERATION BETWEEN CONTRACTORS

# THE STATE OF OHIO HAS CONTRACTED PROJECT PER-93-4.96/VAR PID 96323,

# (cOMPLETION DATE 10/31/24) WHICH MAY BE CONSTRUCTED CONCURRENTLY WITH THIS PROJECT. IT IS IMPERATIVE THAT THE CONTRACTORS COOPERATE FULLY WITH EACH OTHER AS OUTLINED IN SECTION 105.08 OF THE CMS

# MANUAL. ALL MAINTENANCE OF TRAFFIC SHALL BE COORDINATED BETWEEN PROJECTS AND NOT CONFLICT WITH ONE ANOTHER

# ITEM 614, WORK ZONE MARKING SIGN

THE CONTRACTOR SHALL PLACE ALL WORK ZONE MARKING SIGNS

IN ACCORDANCE WITH CMS SECTION 614.04, UNLESS OTHERWISE

DIRECTED BY THE ENGINEER.

R4-1 (DO NOT PASS):

Location 1A:   12 EACH

location 1B:    6 each

R4-2 (PASS WITH CARE):

LOCATION 1A:   7 EACH

LOCATION 1B:   7 EACH

# W8-H12a (NO EDGE LINES):

# location 1a:  12 each

LOCATION 1B:  18 EACH

ALL “NO EDGE LINES” SIGN LOCATIONS SHALL BE APPROVED BY THE

ENGINEER PRIOR TO INSTALLATION.

ANY revisions TO THE CENTER LINE PASSING/NO PASSING LOGS SHALL

BE REFLECTED IN THE WORK ZONE SIGNING.

IN ADDITION, THE CONTRACTOR SHALL ERECT A “GROOVED PAVEMENT”

SIGN 250 FEET IN ADVANCE OF ANY SECTION OF ROADWAY WHERE TRAFFIC MUST TRAVEL ON A PLANED SURFACE. “GROOVED PAVEMENT” SIGNS

SHALL BE INCLUDED FOR PAYMENT WITH THE LUMP SUM BID FOR ITEM

614 MAINTAINING TRAFFIC AS PER CMS SECTION 614.055.

# ITEM 614, WORK ZONE MARKING SIGN

Location 1A:  37 EACH

# LOCATION 1B:  25 EACH

DROP-OFFS IN WORK ZONES

DROP-OFFS THAT DEVELOP DURING CONSTRUCTION OPERATIONS AND THAT ARE NOT OTHERWISE PROVIDED FOR IN THE PLANS SHALL BE TREATED AS SHOWN ON STANDARD DRAWING MT-101.90. WHERE THE PLANS DO NOT PROVIDE SPECIFIC ITEMS FOR LABOR, EQUIPMENT, OR MATERIALS TO IMPLEMENT THE DROP-OFF TREATMENTS SPECIFIED, THEY SHALL BE INCLUDED FOR PAYMENT IN THE LUMP SUM BID FOR ITEM 614, MAINTAINING TRAFFIC.

ITEM 614, WORK ZONE PAVEMENT MARKINGS

THE CONTRACTOR SHALL PLACE ALL WORK ZONE PAVEMENT MARKINGS

IN ACCORDANCE WITH CMS 614.11 AND STANDARD DRAWING MT-99.20 UNLESS OTHERWISE DIRECTED BY THE ENGINEER. THE QUANTITIES BELOW ARE FOR PLACEMENT OF TEMPORARY MARKINGS ON SURFACE AND INTERMEDIATE COURSES FOR BOTH THE CONCRETE AND ASPHALT

SECTIONS OF ROADWAY.

ITEM 614, WORK ZONE CENTER LINE, CLASS I, 642 PAINT

(INTERMEDIATE COURSE)

Location 1A:    5.88 MILE

LOCATION 1B:    5.60 MILE

ITEM 614, WORK ZONE CENTER LINE, CLASS III, 642 PAINT

(SURFACE COURSE)

Location 1A:    5.88 MILE

LOCATION 1B:    5.60 MILE

ITEM 614, WORK ZONE EDGE LINE, CLASS I, 6”, 642 PAINT

(INTERMEDIATE COURSE) (WINTER USE ONLY)

LOCATION 1B:   11.20 MILE

ITEM 614, WORK ZONE CHANNELIZING LINE, CLASS I, 642 PAINT

(INTERMEDIATE COURSE)

Location 1A:   70 feet

ITEM 614, WORK ZONE CHANNELIZING LINE, CLASS III, 642 PAINT

(SURFACE COURSE)

Location 1A:   70 feet

ITEM 614, WORK ZONE STOP LINE, CLASS I, 642 PAINT

(INTERMEDIATE COURSE)

LOCATION 1a:    44 feet

ITEM 614, WORK ZONE STOP LINE, CLASS III, 642 PAINT

(SURFACE COURSE)

LOCATION 1a:    44 feet

ITEM 614, PORTABLE CHANGEABLE MESSAGE SIGN, AS PER PLAN

The Contractor shall furnish, install, maintain and remove, when no longer needed, A changeable message sign, on site, for the duration of the project.  The sign shall be of a type shown on a list of approved PCMS units AVAILABLE ON THE Office of Materials Management WEB PAGE.  The list contains Class A and B units with minimum legibility distances of 650 FEET and 475 FEET, respectively.

Each sign shall be trailer-mounted and equipped with a functional dimming mechanism, to dim the sign during darkness, and a tamper and vandal proof enclosure.  Each sign shall be provided with appropriate training and operation instructions to enable on-site personnel to operate and troubleshoot the unit.  The sign shall also be capable of being powered by an electrical service drop from a local utility company.  THE PCMS SHALL BE DELINEATED IN ACCORDANCE WITH C&MS 614.03.

The probable PCMS locations and work limits for those locations are shown on sheet(s) of the plan.  Placement, operation, maintenance and all activation of the signs by the Contractor shall be as directed by the Engineer.  The PCMS shall be located in a highly visible position yet protected from traffic. The Contractor shall, at the direction of the Engineer, relocate the PCMS to improve visibility or accommodate changed conditions.  When not in use, the PCMS shall be turned off.  Additionally, when not in use for extended periods of time, the PCMS shall be turned, facing away from all traffic.

The Engineer shall be PROVIDED WITH access to each sign unit and shall be provided with appropriate training and operation instructions to enable ODOT personnel to operate and troubleshoot the unit, and to revise sign messages, if necessary.

The Contractor shall implement a system whereby changeable messages will be implemented within 2 hours following telephone notification from the Project Engineer to a designated phone.

All messages to be displayed on the sign will be provided by the Engineer.  A list of all required pre-programmed messages will be given to the Contractor at the project preconstruction conference.  The sign shall have the capability to store up to 99 messages.  Message memory or pre-programmed displays shall not be lost as a result of power failures to the on-board computer.  The sign legend shall be capable of being changed in the field.  three-line presentation formats with up to six message phases shall be supported.  PCMS format shall permit the complete message for each phase to be read at least twice.

The PCMS shall contain an accurate clock and programming logic which will allow the sign to be activated, deactivated or messages changed automatically at different times of the day for different days of the week.

ITEM 614, PORTABLE CHANGEABLE MESSAGE SIGN, AS PER PLAN (Cont’d.)

The PCMS unit shall be maintained in good working order by the Contractor in accordance with the provisions of C&MS 614.07.

The Contractor shall, prior to activating the unit, make arrangements, with an authorized service agent for the PCMS,

to assure prompt service in the event of failure.  Any failure shall not result in the sign being out of service for more than 12 hours, including weekends.  Failure to comply may result in an order to stop work and open all traffic lanes and/or in the Department taking appropriate action to safely control traffic.  The entire cost to control traffic, accrued by the Department due to the Contractor’s noncompliance, will be deducted from moneys due, or to become due the Contractor on his contract.

The Contractor shall be responsible for 24-hour-per-day operation and maintenance of these signs on the project for the duration of the phases when the plan requires their use.

Payment for the ABOVE-DESCRIBED item shall be at the contract unit price.  Payment shall include all labor, materials, equipment, fuels, lubricating oils, software, HARDWARE, and incidentals to perform the ABOVE-DESCRIBED work.

a total of 6 pcms MAY be required for this project.

EDGE REPAIR WORK

(PLACE AS DIRECTED BY THE ENGINEER)

2 PCMS X 6 MONTH = 12 SNMT

Item 614 Portable Changeable Message Sign, AS PER PLAN

Location 1B:  12 SNMT

# ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE

USE OF LAW ENFORCEMENT OFFICERS (LEOS) BY CONTRACTORS OTHER THAN THE USES SPECIFIED IN THIS NOTE WILL NOT GENERALLY BE PERMITTED AT PROJECT COST.   LEOS SHOULD NOT BE USED WHERE THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES (OMUTCD) INTENDS THAT FLAGGERS BE USED.

IN ADDITION TO THE REQUIREMENTS OF C&MS 614 AND THE OMUTCD, A UNIFORMED LEO WITH AN OFFICIAL PATROL CAR (CAR WITH TOP-MOUNTED EMERGENCY FLASHING LIGHTS AND COMPLETE MARKINGS OF THE APPROPRIATE LAW ENFORCEMENT AGENCY) SHOULD BE PROVIDED FOR CONTROLLING TRAFFIC FOR THE FOLLOWING TASKS, AS DIRECTED BY THE ENGINEER:

- WHEN TRAFFIC NEEDS TO BE DIRECTED THROUGH AN ENERGIZED TRAFFIC SIGNAL CONTRARY TO THE SIGNAL DISPLAY (E.G., DIRECTING MOTORISTS THROUGH A RED LIGHT)

IN GENERAL, LEOS SHOULD BE POSITIONED IN ADVANCE OF AND ON THE SAME SIDE AS THE LANE RESTRICTION OR AT THE POINT OF ROAD CLOSURE, AND TO MANUALLY CONTROL TRAFFIC MOVEMENTS THROUGH SIGNALIZED INTERSECTIONS IN WORK ZONES.  LEOS SHOULD NOT FORGO THEIR TRAFFIC CONTROL RESPONSIBILITIES TO APPREHEND MOTORISTS FOR ROUTINE TRAFFIC VIOLATIONS.  HOWEVER, IF A MOTORIST’S ACTIONS ARE CONSIDERED TO BE RECKLESS, THEN PURSUIT OF THE MOTORIST IS APPROPRIATE.

THE LEOS WORK AT THE DIRECTION OF THE CONTRACTOR.  THE CONTRACTOR IS RESPONSIBLE FOR SECURING THE SERVICES OF THE LEOS AND COMMUNICATING THE INTENTIONS OF THE PLANS WITH RESPECT TO DUTIES OF THE LEOS. THE ENGINEER SHALL HAVE FINAL CONTROL OVER THE LEOS’ DUTIES AND PLACEMENT AND WILL RESOLVE ANY ISSUES THAT MAY ARISE BETWEEN THE TWO PARTIES.

THE LEO SHALL REPORT IN TO THE CONTRACTOR PRIOR TO THE START OF THE SHIFT TO RECEIVE INSTRUCTIONS REGARDING SPECIFIC WORK ASSIGNMENTS DURING HIS/HER SHIFT. THE LEO IS EXPECTED TO STAY AT THE PROJECT SITE FOR THE ENTIRE DURATION OF HIS/HER SHIFT.  THE LEO SHALL REPORT TO THE CONTRACTOR AT THE END OF HIS/HER SHIFT.  ONCE THE LEO HAS COMPLETED THE DUTIES DESCRIBED ABOVE AND STILL HAS TIME REMAINING ON HIS/HER SHIFT, THE LEO MAY BE ASKED TO PATROL THROUGH THE WORK ZONE (WITH FLASHING LIGHTS OFF) OR BE PLACED AT A LOCATION TO DETER MOTORISTS FROM SPEEDING.  SHOULD IT BE NECESSARY TO LEAVE THE PROJECT SITE, THE LEO SHALL NOTIFY THE ENGINEER.  THE CONTRACTOR SHALL PROVIDE THE LEO WITH A TWO-WAY COMMUNICATION DEVICE WHICH SHALL BE RETURNED TO THE CONTRACTOR AT THE END OF HIS/HER SHIFT.

LAW ENFORCEMENT OFFICERS (WITH PATROL CAR) REQUIRED BY THE TRAFFIC MAINTENANCE TASKS ABOVE SHALL BE PAID FOR ON A UNIT PRICE (HOURLY) BASIS UNDER ITEM 614, LAW ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE. THE HOURS PAID SHALL INCLUDE MINIMUM SHOW-UP TIME REQUIRED BY THE LAW ENFORCEMENT AGENCY INVOLVED.

ANY ADDITIONAL COSTS (ADMINISTRATIVE OR OTHERWISE) INCURRED BY THE CONTRACTOR TO OBTAIN THE SERVICES OF A LEO ARE INCLUDED WITH THE BID UNIT PRICE FOR ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE.

Item 614 Law Enforcement Officer With Patrol CaR FOR ASSISTANCE

LOCATION 1A: 16 HOURS

SEQUENCE OF OPERATIONS (EDGE REPAIR SLM 5.90-11.50)

IT IS THE INTENT OF THIS SEQUENCE OF OPERATIONS TO PROVIDE A WORK

AREA FOR THE CONTRACTOR WHILE ALSO MAINTAINING TRAFFIC IN A MANNER WHICH IS SAFE FOR THE TRAVELING PUBLIC. THE CONTRACTOR SHALL COMPLETE ALL WORK AS DESCRIBED IN THE SEQUENCE OF OPERATIONS, FOR EACH PHASE OF CONSTRUCTION. BEFORE STARTING WORK ON THE NEXT PHASE OF CONSTRUCTION, APPROVAL SHALL BE GRANTED BY THE PROJECT ENGINEER. BEFORE THE CONTRACTOR MAY PROCEED.

THE CONTRACTOR MAY SUBMIT ALTERNATE METHODS FOR THE MAINTENANCE OF TRAFFIC SEQUENCING, PROVIDED NO ADDITIONAL INCONVENIENCE TO THE TRAVELING PUBLIC RESULTS THERE FROM. NO ALTERNATE PLAN SHALL BE PLACED INTO EFFECT UNTIL APPROVAL, IN WRITING, HAS BEEN GRANTED BY

THE DEPARTMENT.

1.)   PERFORM FULL DEPTH PAVEMENT SAWING PER PHASE 1 TYPICAL SECTION

(SHEET 27) UNDER FLAGGING

2.)   PERFORM EDGE REPAIR WORK PER PHASE 1 TYPICAL SECTION (SHEET 27)

USING TEMPORARY SIGNALS, AS SHOWN ON SHEETS 9-10.

3.)   PERFORM 1.50” PAVEMENT PLANING, PLACE REINFORCED MESH (5’ WIDE)

OVER SAW CUT LINE, AND PLACE 1.75” ASPHALT CONCRETE INTERMEDIATE

COURSE UNDER FLAGGING

4.)   REMOVE AND REPLACE GUARDRAIL AND SIGNING UNDER FLAGGING

5.)   COMPLETE REMAINING PAVEMENT WORK TO MATCH PHASE 2 TYPICAL

SECTION UNDER FLAGGING

ANY WORK NOT SPECIFIED IN THE ABOVE SEQUENCE MAY BE COMPLETED AT ANYTIME DURING THE PROJECT, WITH APPROVAL OF THE ENGINEER.

MAINTAINING EXISTING DRIVES

THE CONTRACTOR SHALL MAINTAIN ACCESS TO ALL RESIDENT AND COMMERCIAL DRIVES TO THE FULLEST EXTENT POSSIBLE. IT IS

UNDERSTOOD THAT FOR SHORT PERIODS OF TIME, FULL ACCESS TO

A DRIVEWAY MAY NOT BE FEASIBLE. THE CONTRACTOR SHALL MAKE ACCOMMODATIONS TO THE RESIDENT/BUSINESS OWNER SO THAT

DURING THESE SHORT INTERVALS, THE HOME/BUSINESS OWNER

CAN STILL HAVE ACCESS TO PARK NEAR THEIR HOME/BUSINESS.

PROPERTIES WITH MULTIPLE ACCESS POINTS, WORK AT ONE DRIVE

AT A TIME. PROPERTIES WITH A SINGLE ACCESS POINT: MAINTAIN

ACCESS TO PROPERTY AT ALL TIMES USING PART WIDTH CONSTRUCTION,

BACKFILL OPEN EXCAVATION WITH ITEM 410 AGGREGATE FOR

TEMPORARY ACCESS.

THE CONTRACTOR SHALL GIVE PRIOR NOTICE TO THE OCCUPANT OF THE PROPERTY 72 HOURS BEFORE THE WORK IS STARTED.THE CONTRACTOR

SHALL BE RESPONSIBLE TO ENSURE THAT U.S. MAIL OR ANY OTHER

DELIVERY WITHIN THE PROJECT LIMITS IS NOT DISRUPTED BY

CONSTRUCTION OPERATIONS.

THE DEPARTMENT WILL ONLY PAY FOR ITEM 410, TRAFFIC COMPACTED SURFACE ONE TIME PER DRIVE. ALL LABOR AND EQUIPMENT REQUIRED

TO MOVE THE COMPACTED AGGREGATE DURING A PHASE SHALL BE AT

THE COST OF THE CONTRACTOR.

THE FOLLOWING ESTIMATED QUANTITY HAS BEEN INCLUDED IN THE

LOCATION SUB-SUMMARY FOR USE AS DIRECTED BY THE ENGINEER TO MAINTAIN AND RESTORE EXISTING DRIVES AS DESCRIBED ABOVE.

ITEM 410, TRAFFIC COMPACTED SURFACE, TYPE C, AS PER PLAN

LOCATION 1B:    250 CU. YD.