## Overlays
STA-30-CONCRETE OVERLAYS
ZONE | DIRECTION | PHASE | STRUCTURES | CLOSE RAMPS | DURATION | DISINCENTIVE PER CALENDAR DAY | ADDITONAL RESTRICTIONS
1 | EB | 1 (INSIDE CONSTRUCTION) | STA-30-1303R AND STA-30-1338 | RAMP P (RAFF RD (SR 297) TO US 30 E) | 1 WEEKEND (6PM FRIDAY - 6AM MONDAY) | 2000 | CANNOT BE PERFORMED WITH ZONE 2 PHASE 1 AND 2 IN THE EASTBOUND DIRECTION
|  | 2 (OUTSIDE CONSTRUCTION) |  | RAMP P (RAFF RD (SR 297) TO US 30 E) | 1 WEEKEND (6PM FRIDAY - 6AM MONDAY) | 2000
| WB | 1 (INSIDE CONSTRUCTION) | STA-30-1303L AND STA-30-1338 | RAMP O (US 30W TO RAFF RD) | 1 WEEKEND (6PM FRIDAY - 6AM MONDAY) | 2000 | NONE
|  | 2 (OUTSIDE CONSTRUCTION) |  | RAMP O (US 30W TO RAFF RD) | 1 WEEKEND (6PM FRIDAY - 6AM MONDAY) | 2000 | NONE
2 | EB | 1 (INSIDE CONSTRUCTION) | STA-30-1479, STA-30-1488, STA-30-1502, AND STA-30-1520 | NONE | 10 CONSECUTIVE CALENDAR DAYS | 5000 | CANNOT BE PERFORMED WITH ZONE 1 PHASE 1 AND 2 IN THE EASTBOUND DIRECTION
|  | 2 (OUTSIDE CONSTRUCTION) | STA-30-1479, STA-30-1488, STA-30-1502 AND STA-30-1520 MAINLINE US 30 | RAMP B (77S TO US 30E) | 10 CONSECUTIVE CALENDAR DAYS | 5000 | CANNOT BE PERFORMED WITH ZONE 3,CANNOT BE PERFORMED WITH STA-62-1870L, CANNOT BE PERORMED WITH ZONE 2 PHASE 2 IN THE WESTBOUND DIRECTION
| WB | 1 (OUTSIDE CONSTRUCTION) | STA-30-1479, STA-30-1488, AND STA-30-1502 | RAMP E (77N TO US 30W) AND RAMP CN-W (CHERRY AVE TO US 30W) | 10 CONSECUTIVE CALENDAR DAYS | 5000
|  | 2 (INSIDE CONSTRUCTION) |  | RAMP CN-W (CHERRY AVE TO US 30W) | 10 CONSECUTIVE CALENDAR DAYS | 5000 | CANNOT BE PERFORMED WITH ZONE 2 PHASE 2 IN THE EASTBOUND DIRECTION
3 | EB | RAMP H LANE OF STA-30-1520 AND STA-30-1557 OUTSIDE CONSTRUCTION | RAMP H LANE OF STA-30-1520 AND STA-30-1558 OUTSIDE CONSTRUCTION | RAMP H (77N TO US 30W) | 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) | 2000 | CANNOT BE PERFORMED WITH ZONE 2 PHASE 2 IN THE EASTBOUND DIRECTION, CANNOT BE PERFORMED WITH ZONE 5 PHASE 2 IN THE WESTBOUND DIRECTION
4 | EB | 1 (OUTSIDE CONSTRUCTION) | STA-30-1580, AND STA-30-1594 | RAMP W-C/ W-CN (US 30E TO CHERRY AVE) | 1 WEEKEND (7PM THURSDAY TO 6AM MONDAY) | 2000 | CANNOT BE COMBINED WITH WORK ZONE 4 WESTBOUND PHASING
|  | 2 (INSIDE CONSTRUCTION) | STA-30-1558, STA-30-1580, AND STA-30-1594 | RAMP W-C/ W-CN (US 30E TO CHERRY AVE) | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY) | 2000
CANNOT BE COMBINED WITH WORK ZONE 4 WESTBOUND PHASING AND WORK ZONE 3
| WB | 1 (OUTSIDE CONSTRUCTION) | STA-30-1558, STA-30-1580, AND STA-30-1594 | RAMP CS-W (11TH ST TO US 30E) AND RAMP E-C (US 30W TO 11TH ST) | 1 WEEKEND (7PM WEDNESDAY TO 6AM MONDAY) | 2000 | CANNOT BE COMBINED WITH WORK ZONE 4 EASTBOUND PHASING
|  | 2 (INSIDE CONSTRUCTION) |  | RAMP CS-W (11TH ST TO US 30E) | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY) | 2000 | CANNOT BE COMBINED WITH WORK ZONE 4 EASTBOUND PHASING
5 | EB | 1 (OUTSIDE CONSTRUCTION) | STA-30-1634, STA-30-1640, AND STA-30-1646 | NONE | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY) | 2000
|  | 2 (INSIDE CONSTRUCTION) |  |  | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY)
| WB | 1 (OUTSIDE CONSTRUCTION) | STA-30-1634, STA-30-1640, AND STA-30-1646 | RAMP B-W (BELDEN AVE TO US 30W) | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY) | 2000
|  | 2 (INSIDE CONSTRUCTION) |  | NONE | 1 WEEKEND (9AM FRIDAY TO 6AM MONDAY)
|  | 1 (INSIDE CONSTRUCTION) |  | RAMP CN-W (CHERRY AVE TO US 30W)
|  | 2 (OUTSIDE CONSTRUCTION) |  | RAMP E (77N TO US 30W) AND RAMP CN-W (CHERRY AVE TO US 30W)

## Ramps
DETOURS FOR US 30 RAMPS
RAMP | RAMP DESCRIPTION | DURATIONS | DETOUR ROUTE | APROX. NUMBER OF PCMS | ADDITIONAL RESTRICTIONS | DISINCENTIVE PER CALENDAR DAY
RAMP C-E | CHERRY AVE TO US 30 EAST | 1 WEEKEND (6PM FRIDAY TO 6AM MONDAY) | US 30 WEST / HARRISON AVE / US 30 EAST | 4 | SEE NOTE 1 BELOW. | 2000
RAMP CN-W | CHERRY AVE TO US 30 WEST | 1 WEEKEND (6PM FRIDAY TO 6AM MONDAY) | US 30 EAST / BELDEN AVE / US 30 WEST | 3 | SEE NOTE 1 BELOW. | 4000
RAMP CS-W | 11TH ST TO US 30 WEST | 1 WEEKEND (6PM FRIDAY TO 6AM MONDAY) | US 30 EAST / BELDEN AVE / US 30 WEST | 3 | SEE NOTE 1 BELOW. | 5000
RAMP E-C | US 30 WEST TO 11TH ST | 1 WEEKEND (6PM FRIDAY - 6AM MONDAY) | US 30 WEST / HARRISON AVE | 3 | SEE NOTE 1 BELOW. | 2000
RAMP O | US 30 WEST TO RAFF RD (SR 297) | 2 WEEKENDS (6PM FRIDAY - 6AM MONDAY) | US 30 WEST / SR 627 (RICHVILLE DR) / US 30 EAST | 3 | SEE NOTE 1 BELOW. | 8000
RAMP P | RAFF RD (SR 297) TO US 30 EAST | 2 WEEKENDS (6PM FRIDAY - 6AM MONDAY) | US 30 WEST / WHIPPLE AVE / US 30 EAST | 3 | SEE NOTE 1 BELOW. | 3000
RAMP T | HARRISON AVE TO US 30 EAST | 2 CONSECUTIVE 10-DAY CLOSURES | US 30 WEST / SR 297 / US 30 EAST | 0 PCMS (DETOUR SIGNS PROVIDED FOR 10-DAY CLOSURES) | SEE NOTE 1 BELOW. | 5000
RAMP W-C | US 30 EAST TO CHERRY AVE | 2 WEEKENDS: 1 WEEKEND RAMP H AND 15.629 OVERLAY: 5PM FRIDAY TO 6AM MONDAY 1 WEEKEND 15.846 AND 15.987 OUTSIDE CONSTRUCTION: 6PM FRIDAY - 6AM MONDAY | US 30 EAST / BELDEN AVE / US 30 WEST | 3 | SEE NOTE 1 BELOW. | 8000
DETOUR FOR US 30 RAMPS AT I-77 INTERCHANGE
RAMP | RAMP DESCRIPTION | DURATIONS | DETOUR ROUTE | APROX. NUMBER OF PCMS | ADDITIONAL RESTRICTIONS | DISINCENTIVE PER CALENDAR DAY
RAMP A | I-77 SOUTH TO US 30 WEST | 1 WEEKEND (8PM FRIDAY TO 6AM MONDAY) | DURING 1 WEEKEND TO PAVE RAMP A: I-77 SOUTH / SR 800 / I-77 NORTH | 3 | SEE NOTE 1 BELOW. | 20000
RAMP B | I-77 SOUTH TO US 30 EAST | 14 CONSECUTIVE CALENDAR DAYS FOR BRIDGE WORK AND 1 WEEKEND (8PM FRIDAY TO 6AM MONDAY) TO PAVE RAMP B | DURING WEEKEND CLOSURE: US30 WEST / RAFF (SR-297) / US30 EAST | 2 PCMS (DETOUR SIGNS PROVIDED) | SEE NOTE 1 BELOW. | 20000
RAMP C | US 30 WEST TO I-77 SOUTH | 14 CONSECUTIVE CALENDAR DAYS FOR BRIDGE WORK AND 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) TO PAVE RAMP C | I-77 NORTH / TUSCARAWAS AVE (SR172) | 2 PCMS (DETOUR SIGNS PROVIDED) | SEE NOTE 1 BELOW. | 5000
RAMP D | US 30 WEST TO I-77 NORTH | 2 WEEKENDS (5PM FRIDAY TO 6AM MONDAY) FOR BRIDGE WORK, 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) TO PAVE RAMP D | US 30 WEST / RAFF (SR-297) / US30 EAST / I-77 NORTH | 3 | SEE NOTE 1 BELOW. | 20000
RAMP E | I-77 NORTH TO US 30 WEST | 1 WEEKEND (8PM FRIDAY TO 6AM MONDAY) | 77 NORTH / TUSCARAWAS ST (SR 172) / 77 SOUTH | 3 | SEE NOTE 1 BELOW. | 5000
RAMP F | US 30 EAST TO I-77 SOUTH | 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) FOR BRIDGE WORK, 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) TO PAVE RAMP F | I-77 NORTH / TUSCARAWAS AVE (SR172) / I-77 SOUTH | 3 | SEE NOTE 1 BELOW. | 8000
RAMP G | US 62 to I-77 NORTH | 1 WEEKEND (5PM FRIDAY TO 6AM MONDAY) TO PAVE RAMP G | US 30 EAST / CHERRY / US 30 WEST | 3 | SEE NOTE 1 BELOW. | 20000
RAMP H | I-77 NORTH TO US 30 EAST | 1 WEEKEND (8PM FRIDAY TO 6AM MONDAY) | 77 NORTH / TUSCARAWAS ST (SR 172) / 77 SOUTH | 3 | SEE NOTE 1 BELOW. | 10000
[7 empty] | RAMP NAME | DESCRIPTION
[7 empty] | RAMP A | ENTRANCE RAMP FROM IR 77 SB TO US 30 WB
[7 empty] | RAMP B | ENTRANCE RAMP FROM IR 77 SB TO US 30 EB
[7 empty] | RAMP C-E | ENTRANCE RAMP FROM SR 43 NB TO US 30 EB
[7 empty] | RAMP CN-W | ENTRANCE RAMP FROM SR 43 SB TO US 30 WB
[7 empty] | RAMP CS-W | ENTRANCE RAMP FROM 11TH ST SE TO US 30 WB
[7 empty] | RAMP D | EXIT RAMP FROM US 30 WB TO IR 77 NB
[7 empty] | RAMP E | ENTRANCE RAMP FROM IR 77 NB TO US 30 WB
[7 empty] | RAMP E-C | EXIT RAMP FROM US 30 WB TO 11TH ST SE
[7 empty] | RAMP H | ENTRANCE RAMP FROM IR 77 NB TO US 30 EB
[7 empty] | RAMP O | EXIT RAMP FROM US 30 WB TO RAFF ROAD
[7 empty] | RAMP P | ENTRANCE RAMP FROM RAFF ROAD TO US 30 EB
[7 empty] | RAMP Q | ENTRANCE RAMP FROM HARRISON AVE TO US 30 WB
[7 empty] | RAMP R | EXIT RAMP FROM US 30 EB TO HARRISON AVE
[7 empty] | RAMP S | EXIT RAMP FROM US 30 WB TO HARRISON AVE
[7 empty] | RAMP T | ENTRANCE RAMP FROM HARRISON AVE TO US 30 EB
[7 empty] | RAMP W-C | EXIT RAMP FROM US 40 EB TO SR 43 NB