                                       SEQ CHAPTER \h \r 1PROGRESS MEETING # 22 Minutes
Project 21-0591
CLE-32-3.50

May 9th, 2024
Attendees:  Green in attendance
Kyle Smally- JRJ 
Paul Cain- JRJ



Chris Kunz – JRJ
Josh Nichols – JRJ

                       Amanda Beiting- CCEO 


Josh Burns – JRJ                                
Josh Bradford-ODOT





	Agenda Topic:
	Action/Discussion Items:

	1. Corrections to last Progress Meeting Minutes:

	NONE

	2. Partnering:

	AWP migration in the works 

	3. Work in Progress:

	Maintaining SWPPP

Underdrains in the median, Capital boring complete


	4. Progress Schedule/Upcoming Work: 
Confirm Weather Days: 


	JRJ-Stabilize last section east end,paving base in the median starting week of 20th
Koko- mobilize in week of May 20th, starting with handwork

	5. Estimates:

	42 is done, 43 ran but was negative due to removed stockpiled materials, working to get it positive

	6. Delays (work on critical path):

	Potential weather delay for April 2024

	7. Interferences (work NOT on critical path):

	None currently. 

	8. Time Extensions:

	October 30, 2024


	9. Change Orders 

	Review some of the outstanding FA submitted

	10. Environmental:

	SWPPP; Ongoing, Start paying them as they are done, keep log even if they are not shown in SWPPP track so they can be entered at a later date if missed

	11. R/W Utilities:

	none

	12. Public Relations/Safety:

	Discussed 

	13. Testing/Materials:

	Discussed

	14. Submittals:


	36 Submittals to date.  No issues


	15. Requests for Information:

	58 will be submitted regarding some outdated signage that Security has questions about

	16. Outstanding Issues:

	48’ conduit, Glen Willow Lake closure at the end of the job. 


	17. EEO/DBE Wages:

	None 

	18. Contractor Issues:

	When base is paved it may create a drainage issue along 32 where base is higher than existing, will have a better idea once all survey data is collected


	19. ODOT Issues:

	Going into part 2 phase 2 early with modified phase 1 to allow for KOKO to have room to slip wall. This allows for Sunesis/ JRJ to do the widened shoulder/ramp F section from 134+95 to 143+50

	20. Open Discussion:


	Notify Holman of Elick culdesac where their entrance will need to be closed

	21. Next Meeting:
a) Date:  May 9th 2024 @9 am
b) Next:  June 13th, 2024 @10 am 
c) Date: DRB #6 June 13 2024@ 11am
d) Location: Project office meeting room 

	Next meeting moved to 10 to lead into DRB


2

