## Sheet1
Utility Contact and Coordination |  | Updated: | 2025-12-18 | Utility Conflicts | Updated: | Updated: | Utility Conflicts | Updated:
PID 123336 - SR 32/HEROLD |  |  |  | and resolution |  |  | and resolution
Company | Contact Info | Stage 2 plans sent: | Stage 2 responded | Conflicts | Stage 2 Repeat responded | Stage 3 plans sent: | Stage 3 responded | Final Plans
Electric - Duke Energy | 2010 DANA AVE., CINCINNATI, OHIO 45207 SHANE ERHART (513) 508-6909 SHANE.ERHART@DUKE-ENERGY.COM |  |  |  |  | 2025-12-11 | Responded 12/16/25: "I don’t see any conflicts here unless you’re re-grading more than I can tell at the guying location" - Shane Erhart
Gas - Duke Energy | 139 E. FOURTH ST., RM 460A CINCINNATI, OHIO 45202 OH/KYHOUSEBILL@DUKE-ENERGY.COM |  |  |  |  | 2025-12-11
Telephone - ALTAFIBER | 221 E. FOURTH STREET CINCINNATI, OHIO 45201, BLDG. 121-900 BRECK COWAN (513) 566-7043 (513) 287 - 2517 BRECK.COWAN@ALTAFIBER.COM ROADPROJECTS@ALTAFIBER.COM |  |  |  |  | 2025-12-11 | Breck called on 12/17/25: They have a copper line with ~3' cover running parallel to the gas main. He doesn't have concern since they want to get rid of that line and we are filling in those areas. The line was added to the plans.
Telephone/Cable - Verizon Business Group | 5400 DUFF DR CINCINNATI, OH 45246 CYNTHIA MARTINEZ (757) 799-8038 CYNTHIA.MARTINEZ@VERIZON.COM |  |  |  |  | 2025-12-11
CLERMONT COUNTY WATER RESOURCE | 4400 HASKELL LANE BATAVIA, OH 45103 TIM CHERRY 513-479-4031 TCHERRY@CLERMONTCOUNTYOHIO.GOV |  |  |  |  | 2025-12-11 | Responded 12/11/25: Area was reviewed and Clermont County utilities will have no impact on this project. -Tim Cherry
CLERMONT COUNTY STORM AND SANITARY | 4400 HASKELL LANE BATAVIA, OH 45103 MICHELLE KNOSE 513-479-4031 MKNOSE@CLERMONTCOUNTYOHIO.GOV |  |  |  |  | 2025-12-11
VILLAGE BATAVIA | 65 N. SECOND ST. BATAVIA, OH 45103 KEN GEIS 513-732-2020 ADMINISTRATOR@BATAVIAOH.GOV |  |  |  |  | 2025-12-11