## contacts
Utility Contacts List
Project: | CUY-71-0467 VAR PAINT | [5 empty] | Date: | 2022-04-19
PID | 105814
Company | Address | City | State | Zip | First | Last | phone | email
Charter Communications | 8179 Dow Circle | Strongsville | OH | 44136 | Rick | Palencar | 440-343-6606 | rick.palencar@charter.com
Illuminating Co./First Energy | 6896 Miller Road, Suite 101 | Brecksville | OH | 44141 | John | Zassick | 440-546-8706 | jmzassick@firstenergycorp.com
MCI/Verizon | 12300 Ridge Road | North Royalton | OH | 44133 | Daniel | Arz | 216-570-9343 | daniel.arz@verizon.com
AT&T Ohio | 13630 Lorain Ave | Cleveland | OH | 44111 | James | Janis | 216-534-7285 | peter.janis@att.com
Dominion Energy Ohio | 320 Springside Drive | Akron | OH | 44333 | James | Sheehe | 330-807-9655 | James.C.Sheehe@dominionenergy.com
Cleveland Water Department | 1201 Lakeside Ave | Cleveland | OH | 44114 | Fred | Roberts | 216-664-2444 | fred_roberts@ClevelandWater.com
Cleveland Public Power | 1300 Lakeside Ave | Cleveland | OH | 44114 | Christopher | Hirzel | 216-563-7212 | chirzel@CPP.ORG
Water Pollution Control | 12302 Kirby Ave | Cleveland | OH | 44108 | Elie | Ramy | 216-664-2756 | eramy@ClevelandWPC.com
Everstream | 1228 Euclid Ave, Suite 250 | Cleveland | OH | 44115 | Stacey | Dasher | 216-408-9205 | sdasher@everstream.net
Windstream | 560 Ternes Ave | Elyria | OH | 44035 | Geoffery | Hamm | 330-256-6133 | geoffrey.p.hamm@windstream.com
Trans Canada/Columbia Gas Transmission | 589 North State Street | Medina | OH | 44256 | Russell | Johnson | 330-410-4379 | russell_johnson@transcanada.com
BP | 4421 Bradley Road | Cleveland | OH | 44109 | Terrie | Berry | 918-409-6197 | Terrie.Berry@bp.com
NEORSD | 3900 Euclid Avenue | Cleveland | OH | 44115 | Mary | Maciejowski | 216-881-6600 | MaciejowskiM@neorsd.org
Atlantic Broadband (formerly WOW) | 105 Blaze Industrial Parkway | Berea | OH | 44017 | Bob | Hammond | 440-625-0349 | rhammond@atlanticbb.com
Lumen for CenturyLink | 4000 Chester Avenue | Cleveland | OH | 44103 | Doug | Holloway | 216-906-6284 | doug.holloway@centurylink.com; relocations@centurylink.com
Crowne Castle | 15565 Neo Parkway | Garfield Heights | OH | 44128 | Jon | Tarnowski | 614-940-2462 | Jon.Tarnowski@crowncastle.com
Signal Service Company (City of Brook Park) | 4341 Cranwood Pkwy | Cleveland | OH | 44128 | Jim | Freck | 216-662-4820 | signal@signalservicecompany.net

## UPDATED CONFLICTS
Utility Conflict Matrix
Project: | CUY-71-0467 VAR PAINT |  | PID | 105814 | Date: | 2022-04-19 | By: | ms consultants, inc.
Utility Company | Contact | Utility Type | Near | Conflict? | Utility Review? | Utility Review Date | Test Hole Required (Level A) | Comments
Charter Communications | Rick Palencar | Aerial communication under bridge | Locations 2, 4 and 5 | Yes | Yes | 9/15/2021 and 2/21/2022 | No | From Rick Palencar: "Charter/Spectrum will be able to detach and lower any lines in conflict (locations 2,4,5) . This would be similar to what we did in the past (Triskett-Berea Rd.) We would protect our lines with a split duct like before. At this point I will be the contact for this work. Thanks Rick" Also...... "Yes, we will lower and protect our lines minimum 2 ft.. Will need between 45 -90 day notice to proceed. If there is no splicing of the existing fiber, the work would be complete in less than 30 days. Thanks Rick"
Illuminating Co./First Energy | John Zassick | None | N/A | No | Yes | 2021-08-16 | No | The Illuminating Company has no facilities in conflict on this project
MCI/Verizon | Daniel Arz | Underground cable | Not identified | No | Yes | 2021-08-12 | No | MCI/Verizon does have plant near the project areas, but the cables are buried and should not be in conflict for bridge painting.
AT&T Ohio | James Janis | Overhead Fiber and Copper telecommunication lines | Locations 4, 5 and 6 | Yes | Yes | 2021-12-31 | No | From Ralph Hutchinson: "AT&T has reviewed your project plans for the above referenced project in the various cities. AT&T does maintain facilities within the project limits on Bridge 4,5,6. Bridge 4 (Northside) - AT&T has (1) fiber and (1) copper cable that spans under the bridge but are not attached to the bridge structure. AT&T’s contractor will lower the existing facilities to ensure there is proper distance from the bridge and cables. *Requesting a minimum of 1 week notice to lower cables. (Southside) – AT&T has (1) fiber that spans under the bridge but is not attached to the bridge structure. AT&T’s contractor will lower the existing facilities to ensure there is proper distance from the bridge and cables. *Requesting a minimum of 1 week notice to lower cables. Bridge 5 (Eastside) – AT&T has (1) copper cable and (1) fiber cable that is attached to the bridge structure. The AT&T contractor will detach and reattach the AT&T cables. AT&T’s contractor will ensure there is proper distance from the bridge once the cables are detached. AT&T’s contractor will coordinate this work with the ODOT awarded contractor during construction. *Requesting a minimum (1) week notice. Bridge 6 AT&T has a 6-duct run within the bridge structure. No relocation plans will be designed. The bridge conduit supports for AT&T’s conduits can be painted. In addition, please note that any work performed by AT&T for investigation, relocation, protection, and/or support of its facilities for another proprietary utility is compensable. Proprietary utilities include but are not limited to electric power, water, gas, sanitary, steam, regional transit, turnpike, and other telecommunication companies."
Dominion Energy Ohio | James Sheehe | None | N/A | No | Yes | 2021-09-15 | No | From James Sheehe: "After a review of the plans for the above referenced project as provided by your office on 8/16/2021, it appears that Dominion Energy Ohio (DEO) does not have any facilities in conflict with the proposed project. If during the course of construction, there is any perceived issue, conflict, or problem with a gas mainline related to the project, the authorized agent for the project should notify DEO immediately by contacting the designer listed below or by email to relocation@dominionenergy.com. DEO will always attempt to work with the authorized agent for the project and the contractor to resolve conflicts and prevent delays."
Cleveland Water Department | Fred Roberts | Underground water | Various Locations | No | Yes | 2021-08-16 | No | I do not see any conflict with water as there is no excavation. Nothing appears attached to the bridge. However, we do have facilities in the area. I have attached our records for each location.
Cleveland Public Power | Christopher Hirzel | Overhead electric | Location 5 | Yes | Yes | 8/12/2021 and 1/3/2022 | No | In response to your email utility inquiry below (by location): 1. CUY-17-0449 CPP appears to be in the clear 2. CUY-480-0813 SE CPP appears to be in the clear 3. CUY-480-0856 ES CPP appears to be in the clear 4. CUY-71-0994 CPP appears to be in the clear 5. CUY-71-1188 CPP is responsible for the streetlighting including those attached to the bridge piers + therefore CPP Streetlighting Department will investigate this location and get back to you." Also....." Mr. Hren, CPP will plan on having the secondary electrical distribution moved out of the area of conflict with this CUY-71-04.67 Paint project by the end of 2022. 6. CUY-C0201-0625 CPP appears to be in the clear
Water Pollution Control | Elie Ramy | None | N/A | No | Yes | 2021-08-25 | No | From Elie Ramy: "WPC finds no potential conflicts to existing WPC facilities"
Everstream | Stacey Dasher | Overhead telecomm | Locations 2 and 4 | Yes | Yes | 2/18/2022 and 2/21/2022 | No | From Gio Reillo: "Please see attached snips, we have aerial plant going under the bridges at location’s 1,2,3 & 4. Location’s 5 & 6 there is not any Everstream plant at the moment. If there is anything else you need or if you would like an engineer to meet with someone from your team on site please let me know and I can make arrangements." And....Everstream can move there plant". Also...."If you can give me a 48 hour notice I can make sure to get it take care of ASAP so our plant won’t cause any conflict. "
Windstream | Geoffery Hamm | Overhead telecomm/fiber | Location 4 | Yes | Yes | 2022-01-06 | No | From Leon Taylor at Windstream: "Looks like we have aerial fiber at sections 3 & 4 Brook Park Rd (17) and 71. Do we need to move? The rest are clear. "
Trans Canada/Columbia Gas Transmission | Russell Johnson | No utility review to date. No impact identified.
BP | Terrie Berry | No utility review to date. No impact identified.
NEORSD | Mary Maciejowski | None | N/A | No | Yes | 2021-11-03 | No | NEORSD facilities are not affected by this project.
Atlantic Broadband (formerly WOW) | Bob Hammond | Overhead telcomm cables | Location 6 | No | Yes | 2021-11-05 | No | From Bob Hammond "The only location where WOW / ABB has plant is location 6. We have an aerial crossing over 71 on Whitney. We do not have any facilities on the bridge itself. I don't see any conflicts."
Lumen for CenturyLink | Doug Holloway | Overhead telcomm cables | Location 5 | Yes | Yes | 2022-03-14 | No | I see a potential conflict at 150th St. We are aerial under the bridge. We may be able to temporary attach them to the pier if they need moved during the bridge structure work. We are only aerial at W150th St, location 5’. Our fiber will have either an ICG tag, or Level 3 tag. It looks to be on the top communications spot and drops down to go under the bridge.
Crowne Castle | Jon Tarnowski | Overhead telcomm cable | Location 4 | Yes | Yes | 2022-03-14 | No | Crown castle line located on south side of SR 17. "our fiber cable (Fibertech/CrownCastle) is the second from top cable highlighted in yellow (with Carolina blue tags)"
Signal Service Company (City of Brook Park) | Jim Freck | Overhead signal cable | Location 4 | Yes | Yes | 2022-04-13 | No | Signal Service Company will temporarily relocate their line.

## conflicts
CUY-71-0467 VAR PAINT | [7 empty] | 2022-04-19
105814
|  | No. of Aerial Lines/Pole Location |  |  |  |  | Confirmed? | Location on pole
Location | Desc. | North | East | South | West | Owner
2 | SR 237/480 Ramp over SR 17 | 1 |  |  |  | Everstream | Yes | top
|  | 1 |  |  |  | Charter/Spectrum | Yes | bottom
| Total | 2 | 0 | 0 | 0
4 | I-71 over SR 17 | 1 |  |  |  | AT&T | Yes | top
|  | 1 |  |  |  | AT&T | Yes | bottom
|  |  |  | 1 |  | Everstream | Yes | top
|  |  |  | 1 |  | Crown Castle | Yes
|  |  |  | 1 |  | Windstream | Yes
|  |  |  | 1 |  | Charter Spectrum | Yes
|  |  |  | 1 |  | AT&T | Yes
|  |  |  | 1 |  | City of Brook Park Signal | Yes | bottom
| Total | 2 | 0 | 6 | 0
5 | I-71 over West 150th St |  |  |  | 1 | CPP | Yes | top
[5 empty] | 1 | CPP | Yes | bottom
|  |  | 1 |  |  | CPP | Yes | top
|  |  | 1 |  |  | CPP | Yes
|  |  | 1 |  |  | AT&T | Yes
|  |  | 1 |  |  | AT&T | Yes
|  |  | 1 |  |  | Century Link/Lumen/Level 3 | Yes | bottom
| Total | 0 | 5 | 0 | 2
Notes:
1 | Locations on pole in purple confirmed