UTILITY NOTE

CUY-71-04.67/VAR PAINT

PID #105814

April 19, 2022

general

- Bidders are advised that the following utility facilities may not be cleared from the construction area at the time of award of the contract. These utility facilities shall remain in place or be relocated within the construction limits of the project as set out below.

- All station locations listed below are approximate unless otherwise stated.

- Relocations are based on the Proposed R/W & Construction Centerline.

- All changes to relocation work as described in the Utility Note must be approved by the ODOT Project Engineer. ODOT shall not be held responsible for delay claims resulting from agreements made between the utility companies and the State’s Highway Contractor without ODOT’s prior consent to the agreement.

- The State’s Highway Contractor shall notify ODOT’s Project Engineer, in writing, within 24 hours of any project related contact with a utility company.

- Company work time frames DO NOT include Ohio Revised Code 48-hour One Call requirements.

- Utility relocation work is based on the sequence of construction in the plan. Any changes made to the sequence of construction, after the project is sold, may impact the utility relocation completion dates.

- It should not be assumed a Company’s work, in all locations, can be performed concurrently, unless otherwise noted. The number of working days for a Company to perform their relocation work may not be consecutive.

- Non-compliance in meeting established target dates could cause ODOT to incur project delays and/or additional costs. In this regard, 5515.02 ORC gives the Department the authority to ensure project clearance and recover costs.

- For further responsibilities of the State’s Highway Contractor and Utility Companies, see the Ohio Department of Transportation’s Construction and Material Specifications, sections 105.07 & 107.16.

- The Companies shall comply with the following requirements, in regards to restoration of areas within the project limits, where their facilities have been relocated due to proposed project work:

  - All excavations shall be backfilled with suitable material and compacted to ODOT specifications.

  - Mounding of dirt over trenches will not be permitted. Preliminary cleanup will be required while working and unsuitable material hauled away.

  - Trenches are not to remain open overnight, other than what is needed to start the next day’s work. Those trenches shall be covered with a steel plate and designated with safety cones or barrels.

  - All disturbed right of way shall be restored to its original condition or better, and seeded and mulched as per Item 659, ODOT specifications. Excavations must be restored within 7 days of original date of disturbance.

  - All trenched driveway approaches shall be backfilled with granular material and compacted to ODOT specifications. Driveway surfaces shall be replaced in kind. Consult with ODOT District Utility Coordinator on how to handle disturbed sidewalks.

- The State’s Highway Contractor may need to coordinate their underground work with a/all Utility Companies within the project limits.

AT&T OHIO:

Attn: James Janis

216-534-7285

peter.janis@att.com

AT&T maintains facilities within the project limits at Bridge Locations 4, 5, and 6.

Bridge Location 4 (Northside) - AT&T has (1) fiber and (1) copper cable that spans under the bridge but are not attached to the bridge structure.  AT&T’s contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least seven (7) days’ notice for AT&T to lower the cables.

Bridge Location 4 (Southside) – AT&T has (1) fiber that spans under the bridge but is not attached to the bridge structure.  AT&T’s contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least seven (7) days’ notice for AT&T to lower the cables.

Bridge Location 5 (Eastside) – AT&T has (1) copper cable and (1) fiber cable that is attached to the bridge structure.  AT&T’s contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least seven (7) days’ notice for AT&T to lower the cables.

Bridge Location 6 - AT&T has a 6-duct run within the bridge structure.  No relocation plans will be designed.  The bridge conduit supports for AT&T’s conduits can be painted.

CHARTER COMMUNICATIONS:

Attn: Rick Palencar

440-343-6606

rick.palencar@charter.com

Charter Communications maintains aerial telecomm facilities within the project limits at Bridge Locations 2, 4, and 6.

At each location, Charter Communications or its contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least ninety (90) days’ notice for Charter to lower the cables. The relocation work will be completed in thirty (30) days.

everstream:

Attn: Stacey Dasher

216-408-9205

sdasher@everstream.net

Everstream maintains aerial telecomm facilities within the project limits at Bridge Locations 2 and 4.

At each location, Everstream or its contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least thirty (30) days’ notice for Everstream to lower the cables.

windstream:

Attn: Geoffrey Hamm

330-256-6133

Geoffrey.p.hamm@windstream.com

Windstream maintains aerial fiber facilities within the project limits at Bridge Location 4.

At the noted location Windstream or its contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least thirty (30) days’ notice for Windstream to lower the cables.

cleveland public power (cpp):

Attn: Chris Hirzel

216-563-7212

chirzel@cpp.org

CPP maintains aerial electric facilities within the project limits at Bridge Location 5.

At the noted location CPP or its contractor will relocate the existing facilities on the east and west side of West 150th Street to below ground. This work will be performed by the end of 2022.

CROWN CASTLE:

Attn: Jon Tarnowski

614-940-2462

Crown Castle maintains aerial fiber facilities within the project limits at Bridge Location 4.

At the noted location Crown Castle or its contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least thirty (30) days’ notice for Crown Castle to lower the cables.

SIGNAL SERVICE COMPANY (CITY OF BROOK PARK TRAFFIC SIGNALS):

Attn: Jim Freck

216-662-4820

The City of Brook Park maintains aerial traffic interconnect facilities within the project limits at Bridge Location 4.

At the noted location Signal Service Company, on behalf of the City of Brook Park, will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least thirty (30) days’ notice for Signal Service Company to lower the cables.

LUMEN FOR CENTURY LINK:

Attn: Doug Holloway

216-906-6284

Lumen maintains aerial fiber optic facilities within the project limits at Bridge Location 5.

At the noted location Lumen or its contractor will lower the existing facilities to ensure there is least two (2) feet from the bottom of the bridge bearings at the piers. The contractor shall give at least thirty (30) days’ notice for Signal Service Company to lower the cables.