Maintenance of Traffic

General

It is the responsibility of the Contractor to provide through vehicular access in both directions at all times throughout the project area. The project shall be constructed in phases in order to minimize traffic disruption and inconvenience to the general public. The Contractor shall be responsible for providing all equipment, materials and manpower needed to adequately maintain traffic as provided for in the plans and specifications.

The Contractor is reminded that, in the conduct of this project, the sequence of operations shall be planned in a fashion which minimizes the number of lane reductions and/or lane width reductions required to maintain traffic through the project.

Permitted lane closures shall be as shown on the Permitted Lane Closure Schedule (PLCS). The time limits shown in this table shall be adhered to or road user costs will be assessed.

Lane Closure/Reduction Required

Length and duration of lane closures and restrictions shall be at the approval of the Engineer. It is the intent to minimize the impact to the traveling public. Lane closures or restrictions over segments of the project in which no work is anticipated within a reasonable time frame, as determined by the Engineer, shall not be permitted. The level of utilization of maintenance of traffic devices shall be commensurate with the work in progress.

Maintenance of Traffic Control Zones

The Contractor shall be responsible to maintain the signs, drums or cones specified in the Standard Construction Drawings. When the Contractor is notified of deficiencies, he shall correct the deficiencies as soon as possible, preferably within 12 hours and no later than 24 hours. If any noted deficiencies are not corrected within 24 hours the Engineer shall deduct one day pay for Item 614 – Maintaining Traffic, not as a penalty but as road user costs. The Contractor shall be subject to these road user costs for each and every day that these provisions are not met. All costs for maintaining the work zones as described above shall be included under Item 614 – Maintaining Traffic.

Suspension of Work

If the Contractor fails to comply with the provisions for traffic control as set forth in these plans or with provisions of the OMUTCD, the Engineer shall suspend work until the Contractor complies with the necessary requirements.

Payment

All work and traffic control devices shall be in accordance with CMS 614 and other applicable portions of the specifications, as well as the Ohio Manual of Uniform Traffic Control Devices. Payment for all labor, equipment, and materials shall be included in the lump sum contract price for Item 614 – Maintaining Traffic unless separately itemized in the plans.

Concrete Median Barrier Replacement

Removing, grading, and installing the replacement barrier in a continuous operation shall be limited to areas behind protection of portable concrete barrier and shall at all times be subject to the approval of the Engineer. The Engineer shall be satisfied that all installations will afford maximum protection for traffic.

Maintaining Traffic – General Provisions

1. Traffic shall be maintained in accordance with the “Schedule of Through Lanes to be Maintained.” The Contractor shall set up and operate his equipment in such a manner as to minimize encroachment upon the traveled width of pavement

2. The Contractor shall notify the Engineer, the responsible law enforcement agency and the Ohio Department of Transportation, District 12 Public Information Officer ((216) 584-2007) not less than 7 days prior to a scheduled disruption of traffic.

3. Nighttime work shall be permitted in accordance with these plans and notes. The Contractor shall provide flood lighting of the work area in accordance with CMS 401.15 in order to assure the safest conditions during nighttime work. A lighting plan for nighttime operations shall be presented to and approved by the Engineer.

4. The Contractor shall furnish, erect and maintain all warning and information signs necessary for maintaining traffic. The sign faces shall be reflectorized with type G sheeting complying with the requirements of CMS 730.19. The Contractor shall determine what signs are needed and submit to the Engineer two weeks in advance of his detailed plans. See the OMUTCD and standard drawings for the minimum signage required.

5. Traffic control devices shall be set up prior to the start of construction and shall be properly maintained during the time special conditions exist. They shall remain in place only as long as they are needed and shall be immediately removed thereafter. Where operations are performed in stages, there shall be in place only those devices that apply to the condition present during the stage in progress. All signs with messages which do not apply during a certain period shall be covered or set aside out of the view of traffic.

6. Placement of final roadway pavement markings and raised pavement markers shall be accomplished in accordance with the "Schedule of Through Lanes to be Maintained." The Contractor shall provide 2 shadow vehicles as per MT-99.20 following the pavement marking equipment. The shadow vehicles shall travel 500' apart with the remote vehicle traveling on the shoulder (left or right as applicable) where usable shoulder is available. The first shadow vehicle in a traffic lane shall be equipped with a truck mounted attenuator meeting NCHRP 350 requirements. Each shadow vehicle shall have a yellow flashing beacon plus 48" construction warning signs mounted on the back facing traffic with standard type messages advising motorists of the work ahead, advisory warning speed, and which lane is closed.

7. During non-working periods, open excavations shall be delineated with warning flashers and/or other approved devices as deemed appropriate by the Engineer.

8. Existing signs located within the road work areas which are necessary for interim or permanent traffic control shall be removed and re-erected in locations as approved by the Engineer.

9. No stoppage of traffic shall occur without law enforcement personnel at each location to direct traffic.

10. Whenever a total closure is implemented, the Contractor shall provide a portable changeable message sign from ODOT’s pre-approved list. It shall be placed 1.5 miles to 2 miles in advance of the closure or as directed by the Engineer.

11. For any operation not specifically mentioned in these plans, the traffic shall be maintained in accordance with the OMUTCD.

Permitted Lane Closure Schedule (PLCS)

Lane closure(s) shall conform to the PLCS. Published PLCS information can be found on the ODOT website.

The monthly published schedules required to be used, for each PLCS segment within the project area, are those that comprise the consecutive 12-month period beginning 15 months prior to the month and year of sale and ending 4 months prior to the month and year of sale.  These same 12 months apply for the life of the project and shall be applied to each respective month of construction (month of lane closure(s) shall match month of PLCS used). Lane closure(s) in place for multiple months shall always comply with the current respective month.

(FOR EXAMPLE: If the sale date for the project was March of 2021, the monthly published schedules for each applicable PLCS segment would be December 2019 to November 2020. If this was a three-year project, year three would still be using the December 2019 to November 2020 monthly schedules. If the project desired to close two lanes in June 2021, reference would be made to the June 2020 schedule(s) for the respective PLCS segment(s). If the same two lanes were desired to be closed again in July 2021, reference would be made to the July 2020 schedule(s) for the respective PLCS segment(s).)

More restrictive changes to the allowable lane closure hours are at the discretion of the Engineer in order to comply with the Traffic Management in Work Zones Policy (21-008(P)) and Standard Procedure (123-001(SP)).

Less restrictive changes to the allowable lane closure hours are subject to the Traffic Management in Work Zones Policy (21-008(P)) and Standard Procedure (123-001(SP)) and shall not be implemented until, and unless, approved by the proper ODOT authority.

Allowable lane closure hours for facilities not covered by the PLCS, if any, shall be as specified elsewhere in the plans.

Alternate Methods

If the Contractor so elects, he may submit alternate methods for the maintenance of traffic, provided the intent of the provisions is followed and no additional inconvenience to the traveling public results there from. A review period of 30 days shall be provided for the Engineer to review the submitted alternate methods. No alternate plan shall be placed into effect until approval has been granted, in writing, by the Director.

All items proposed for use under these provisions must comply with current Department standards for their use when the plan detail, Standard Construction Drawing or other bid document governing their use is not provided as part of the bid package.

Construction Traffic

All construction traffic shall use acceptable truck routes to access the construction area. Use of local residential streets is strictly prohibited unless allowed in writing by the local enforcement authorities.

Interim Completion Date

All work detailed in the plans shall be completed by October 15th, 2026, except for the following items:

- Light pole installations.

- Sign truss installations.

  - Includes all work necessary to remove existing barrier and place proposed barrier around the existing sign trusses once the proposed sign trusses are installed.

- Full depth asphalt repairs and mill and fill activities.

Lanes Open During Holidays or Special Events

No work shall be performed and all existing lanes shall be open to traffic during the following designated holidays or special events:

| New Year’s (observed) | General/Regular Election Day (Nov) |
| --- | --- |
| Memorial Day | Thanksgiving |
| Fourth of July (observed) | Christmas (observed) |
| Labor Day | (Other Holiday or Special Event) |

The period of time that the lanes are to be open depends on the day of the week on which the holiday or special event falls. The following schedule shall be used to determine this period:

| Day of holiday or special event | Time all lanes must be open to traffic |
| --- | --- |
| Sunday | 12:00N Friday through 6:00AM Monday |
| Monday | 12:00N Friday through 6:00AM Tuesday |
| Tuesday | 12:00N Monday through 6:00AM Wednesday |
| Tuesday (Gen./Reg. Election) | 5:00AM Tuesday through 12:00AM Wednesday |
| Wednesday | 12:00N Tuesday through 6:00AM Thursday |
| Thursday | 12:00N Wednesday through 6:00AM Friday |
| Thursday (Thanksgiving only) | 6:00AM Wednesday through 6:00AM Monday |
| Friday | 12:00N Thursday through 6:00AM Monday |
| Saturday | 12:00N Friday through 6:00AM Monday |

During the same periods, maintain pedestrian access if pedestrian access was present prior to construction.

Should the Contractor fail to meet to meet any of these requirements, the Contractor shall be assessed a disincentive per the Lane Value Contract (PN 127).

Floodlighting

Floodlighting of the work site for operations conducted during nighttime periods shall be accomplished so that the lights do not cause glare to the drivers on the roadway. To ensure the adequacy of the floodlight placement, the Contractor and the Engineer shall drive through the work site each night when the lighting is in place and operative prior to commencing any work. If glare is detected, the light placement and shielding shall be adjusted to the satisfaction of the Engineer before work proceeds.

Payment for all labor, equipment and materials shall be included in the lump sum contract price for Item 614, Maintaining Traffic.

Maintaining Traffic and Sequence of Operations

All asphalt concrete operations shall be conducted in a manner that will assure minimum danger and inconvenience to highway users. The procedure for the removal or placement of any existing or proposed asphalt course shall be such that no greater than 1-1/2” discontinuity in the elevation of the traveled surface shall be exposed to traffic.

Traffic shall not be permitted to cross any partial-width removal or resurfacing joint during the actual removal or paving operation except as necessary. Any partial-width longitudinal joints with a discontinuity greater than 1-1/2” which must be exposed to traffic shall be ramped using Item 614 – Asphalt Concrete for Maintaining Traffic at a rate not steeper than 6:1.

Temporary transverse removal or paving joints which must be exposed to traffic shall be ramped using Item 614 – Asphalt Concrete for Maintaining Traffic at a rate not to exceed 1” in 10’.

For removal of existing overlays, a transition may be planed into the existing overlay and may be substituted for the asphalt ramps previously described.

Whenever traffic is subject to partial width removals or overlays prior to full width completion, the Contractor shall provide W8-11-48 “UNEVEN LANES” signs (dual sign installation). Placement shall be as directed by the Engineer and included in the lump sum payment for Item 614 – Maintaining Traffic.

Whenever any part of the traveled surface is closed, the motorists shall be warned and diverted by the Contractor through the use of a flashing arrow, in addition to those provisions set forth in the OMUTCD, the Traffic Engineering Manual and the applicable Standard Construction Drawings.

Major Work Items

The following major work items will require traffic maintenance which shall be incorporated into the Contractor’s sequence of operations.

A. Remove existing RPMs

B. Remove existing NB & SB outside shoulder rumble strips and replace with asphalt

C. Remove existing pavement markings & place work zone pavement markings

D. Remove existing median barrier

E. Place proposed median barrier, lighting, and inlets

F. Place proposed pavement markings and raised pavement markers

G. Place rumble strips

Item 614 – Asphalt Concrete for Maintaining Traffic

This item shall be used to fix any potholes that form in the MOT zone during the life of the project. The following estimated quantity has been carried to the General Summary for use as directed by the Engineer:

Item 614 – Asphalt Concrete for Maintaining Traffic ………………..……….. 25 CY

Rumble Strip Removal and Replacement

All existing rumble strips on the westbound outside shoulder that are in conflict with the proposed movement of traffic during the MOT operations shall be removed by pavement planing. The removed rumble strip areas shall be filled with asphalt concrete surface course. The rumble strip removal and replacement area shall be 2.5 feet wide and 1.5 inches deep, centered on the rumble strip. The pavement planing and placement of asphalt concrete surface course should be completed in the same operation. The estimated removal and replacement length is 34,784 Ft.

Immediately following completion of MOT operations and restoring the traffic to its original position, new rumble strips shall be installed at the location where the existing rumble strips were removed.

The following estimated quantities have been carried to the General Summary:

Item 254 – Pavement Planing, Asphalt Concrete (1.5” depth) ………..3,080 SY

Item 407 – Non-Tracking Tack Coat ……………………………………....262 Gal

Item 442 – Asphalt Concrete Surface Course, 12.5 MM, Type A

(448), As Per Plan, PG70-22M, 1-1/2” …………………….3,080 CY

Item 618 – Rumble Strips, Shoulder, (Asphalt Concrete) …………..14.00 Mile

Item 630 – Signing Misc.: Additional Signs, Ground Mounted, As Directed by the Engineer

When additional signing is needed to maintain traffic, the Contractor shall furnish the sign or signs as directed by the Engineer. These signs shall be ground mounted and meet all the specifications of the plan, proposal and current year CMS.

Payment for this item shall include, but not be limited to, the cost to furnish and erect the sign, including driving posts or other approved methods of sign support, maintaining the sign and removal of the sign.

This item of work shall be used to provide signs that are beyond the requirements of the signage detailed in the Standard Construction Drawings and the OMUTCD.

The following estimated quantity has been carried to the General Summary to be used as directed by the Engineer:

| Item 630, | Signing, Misc.: Additional Signs, Ground Mounted, As Directed by the Engineer | 200 Sq Ft |
| --- | --- | --- |

Maintenance of Existing Signs

Per CMS 614.07, the Contractor shall maintain all existing signs for the duration of the project. For overhead signs being replaced by the project, leave the existing signage in place until the new signage is installed. If the existing signs cannot remain in place until the proposed signs are installed, install temporary ground mounted signs in the outside shoulder upon removal of the existing signs to ensure that directional signs are in place at all times.

Covering of Ground-Mounted Signs--General

When required by other items or incidentally to Item 614 – Maintaining Traffic, cover existing ground-mounted signs with plywood or OSB blanks (1/2” minimum thickness) covering 80% of the sign area and all of the sign legend. The use of low quality materials such as duct tape and black plastic is not permitted.

Item 614 – Work Zone Pavement Markings

The following estimated quantities have been carried to the General Summary to be used as directed by the Engineer for work zone pavement markings per the requirements of CMS 614.04 and 614.11. Remove all conflicting pavement markings prior to placing work zone markings. Place work zone markings at the locations shown on the Maintenance of Traffic Plan Sheets.

Item 614 – Work Zone Lane Line, Class I, 6”, 642 Paint ....................... 48.42 Mile

Item 614 – Work Zone Edge Line, Class I, 6”, 642 Paint ....................... 33.40 Mile

Item 614 – Work Zone Channelizing Line, Class I, 12”, 642 Paint ……... 15,928 Ft

Item 614 – Work Zone Dotted Line, Class I, 6”, 642 Paint ………..…….. 15,852 Ft

Item 614 – Work Zone Raised Pavement Marker

The following estimated quantity has been carried to the General Summary to be used as directed by the Engineer for work zone raised pavement markers per the requirements of SCD MT-99.30.

Item 614 – Work Zone Raised Pavement Marker ……………………… 3,594 Each

Winter Shutdown

If sign truss installations and full depth asphalt repairs are not completed prior to traffic being restored to normal lane configuration, then the Contractor shall place portable barrier and impact attenuators in the median shoulder to protect traffic from any gaps in the proposed barrier yet to be closed and/or any gaps in the pavement between the proposed barrier footer and existing sawcut line in the shoulder. The following estimated quantities have been carried to the General Summary to be used as directed by the Engineer:

Item 614 – Work Zone Impact Attenuator, 24” Wide Hazards, (Unidirectional) …………………………………………………………………………………...…4 Each

Item 622 – Portable Barrier, Unanchored ………………….……………. 1,180 Feet

Construction Access Points

To be able to access the work area, the Contractor will be permitted to set up two construction access points in each direction. Four additional work zone impact attenuators have been provided in the General Summary for this purpose. The quantity of portable barrier has been calculated for the entire length of the project, in both directions. The Contractor shall receive no additional payment for portable barrier or impact attenuators when moving the construction access points to complete the construction of the proposed median barrier. The Contractor shall submit proposed locations for the construction access points to the Engineer for approval prior to setting up the work zone.

Item 614, Work Zone Impact Attenuator for 24” Wide Hazards (Unidirectional)

This item shall consist of furnishing and installing a non-gating impact attenuator.  Furnish an impact attenuator from the Office of Roadway Engineering’s approved list for Work Zone Impact Attenuators, from the Roadway Standards Approved Products web page.

Installation shall be at the locations specified in the plans in accordance with the manufacturer’s specifications.

The Contractor shall repair or replace a damaged unit within 24 hours of a damaging impact.

When bidirectional designs are specified, the Contractor shall supply appropriate transitions.

When gating impact attenuators are desired, the Contractor shall submit documentation to the Engineer for acceptance.

The cost for the additional barrier required for a gating impact attenuator shall be included in the cost of the gating impact attenuator.

Payment for the above work shall be made at the unit price bid and shall include all labor, tools, equipment and materials necessary to construct and maintain a complete and functional impact attenuator system, including all related backups, transitions, leveling pads, hardware and grading, not separately specified, as required by the manufacturer.

| Item 614, | Work Zone Impact Attenuator for 24” Wide Hazards (Unidirectional) | 2 Each |
| --- | --- | --- |

Item 622 – Portable Barrier, 50”, As Per Plan

This work shall consist of furnishing, maintaining, and subsequently removing a 50-inch Portable Barrier at the locations shown on the plans. For details, see SCD RM-4.1.

Portable steel barrier is an approved alternative to portable concrete barrier. For information on approved vendors, see the Approved Products List maintained by the Office of Roadway Engineering.

Portable Barrier, 32 inches high with an 18-inch minimum height glare screen may be used at the option of the Contractor. The glare screen shall be constructed using one of the screens provided on the approved list, available on the Office of Roadway Engineering website.

Paddle or intermittent type glare screens shall be designed using a 20 degree cut-off angle based on tangent alignment. That spacing shall be used throughout the barrier length without regard to barrier curvature.

The glare screen system shall be securely fastened to the 32-inch Portable Barrier using the hardware and procedures specified by the manufacturer.

For directions on how to install the glare screen and the barrier, see the manufacturer’s instructions.

Payment shall include all labor, material, and equipment necessary to perform the work and shall be paid for at the contract price per foot for Item 622, Portable Barrier, 50”, As Per Plan.

| Delineation of Portable and Permanent Barrier Item 622, | Portable Barrier, 50”, As Per Plan | 39,170 Feet |
| --- | --- | --- |

Barrier Reflectors and Object Markers shall be installed on all Portable Barrier (PB) used for traffic control; and, on permanent concrete barrier (including bridge parapets) located within 5 feet of the edge of the adjacent travel lane.

Barrier Reflectors shall conform to C&MS 626, except that the spacing shall be as per Traffic SCD MT-101.70. Object Markers and their installation shall conform to C&MS 614.03 and SCD MT-101.70. When the PB or permanent barrier (including bridge parapets) contains glare screen, one set of three vertical stripes of sheeting shall be considered equivalent to an object marker, one-way.

The following estimated quantities have been included in the plans and carried to the General Summary:

| Item 614, | Barrier Reflector, Type 1 (One-Way) | 370 Each |
| --- | --- | --- |
| Item 614, | Object Marker, One-Way | 370 Each |

Payment shall be full compensation for all material, labor, incidentals and equipment necessary for furnishing, installing, maintaining and removing each of the above items

Along runs of increased barrier delineation where this item is provided, the quantity shall be measured as the entire length of the run of increased barrier delineation, including the spaces between the individual delineation panels or stacks of barrier reflectors.

Delineation of Temporary and Permanent Guardrail

Barrier Reflectors shall be installed on all temporary guardrail used for traffic control; and, on all permanent guardrail located within 5 feet of the edge of the adjacent travel lane. Barrier Reflectors shall conform to C&MS 626 and the spacing shall be approximately 50 feet.

Object Markers shall be installed on all temporary and permanent guardrail located within 5 feet of the edge of the adjacent travel lane. Guardrail-mounting of Object Markers shall be made by installing the object markers on the extension blocks rather than directly onto the guardrail itself. Object markers shall conform to C&MS 614.03 and the spacing shall be approximately 50 feet with a 25 foot offset from the Barrier Reflectors.

The following estimated quantities have been included in the plans and carried to the General Summary:

Payment shall be full compensation for all material, labor, incidentals and equipment necessary for furnishing, installing, maintaining and removing the above item(s).

| Item 614, | Barrier Reflector, Type 3, (One-Way) | 740 Each |
| --- | --- | --- |
| Item 614, | Object Marker, One-Way | 740 Each |

Item 614, Portable Changeable Message Signs, As Per Plan

The Contractor shall furnish, install, maintain and remove, when no longer needed, a changeable message sign. The sign shall be of a type shown on a list of approved PCMS units available on the Office of Materials Management web page. The list contains Class A and B units with minimum legibility distances of 800 feet and 650 feet, respectively.

Each sign shall be trailer-mounted and equipped with a functional dimming mechanism, to dim the sign during darkness, and a tamper and vandal proof enclosure. Each sign shall be provided with appropriate training and operation instructions to enable on-site personnel to operate and troubleshoot the unit. The sign shall also be capable of being powered by an electrical service drop from a local utility company. The PCMS shall be delineated in accordance with C&MS 614.03.

Placement, operation, maintenance and all activation of the signs by the Contractor shall be as directed by the Engineer. The PCMS shall be located in a highly visible position yet protected from traffic. The Contractor shall, at the direction of the Engineer, relocate the PCMS to improve visibility or accommodate changed conditions. When not in use, the PCMS shall be turned off. Additionally, when not in use for extended periods of time, the PCMS shall be turned away from all traffic.

The Engineer shall be provided access to each sign unit and shall be provided with appropriate training and operation instructions to enable ODOT personnel to operate and troubleshoot the unit, and to revise sign messages, if necessary.

The Contractor shall implement a system whereby changeable messages will be implemented within 8 hours following telephone notification from the Project Engineer to a designated phone.

All messages to be displayed on the sign will be provided by the Engineer. A list of all required pre-programmed messages will be given to the Contractor at the project preconstruction conference. The sign shall have the capability to store up to 99 messages. Message memory or pre-programmed displays shall not be lost as a result of power failures to the on-board computer. The sign legend shall be capable of being changed in the field. Three-line presentation formats with up to six message phases shall be supported. PCMS format shall permit the complete message for each phase to be read at least twice.

The PCMS shall contain an accurate clock and programming logic which will allow the sign to be activated, deactivated or messages changed automatically at different times of the day for different days of the week.

The PCMS shall contain a cellular telephone data link which will (in active cellular phone areas) allow remote sign activation, message changes, message additions and revisions to time of day programs. The system shall also permit verification of current and programmed messages. One remote data input device (laptop computer plus modem or equivalent) shall be furnished for use by the District Traffic Engineer, or equivalent, and shall be insured against theft.) The PCMS unit shall be maintained in good working order by the Contractor in accordance with the provisions of C&MS 614.07. The Contractor shall, prior to activating the unit, make arrangements, with an authorized service agent for the PCMS, to assure prompt service in the event of failure. Any failure shall not result in the sign being out of service for more than 12 hours, including weekends. Failure to comply may result in an order to stop work and open all traffic lanes and/or in the Department taking appropriate action to safely control traffic. The entire cost to control traffic, accrued by the Department due to the Contractor’s noncompliance, will be deducted from moneys due, or to become due the Contractor on his contract.

The Contractor shall be responsible for 24-hour-per-day operation and maintenance of these signs on the project for the duration of the phases when the plan requires their use.

Payment for the above described item shall be at the contract unit price. Payment shall include all labor, materials, equipment, fuels, lubricating oils, software, hardware and incidentals to perform the above described work.

| Item 614, | Portable Changeable Message Sign, As Per Plan | 24 Sign Month |
| --- | --- | --- |
| Assuming 4 PCMS Sign(s) for 6 Month(s) |  |  |

Item 614, Law Enforcement Officer with Patrol Car for Assistance During Construction Operations

Use of Law Enforcement Officers (LEOs) by contractors other than the uses specified below shall not be permitted at project cost nor time compensation. LEOs should not be used where the OMUTCD intends that flaggers be used.

In addition to the requirements of C&MS 614 and the OMUTCD, a uniformed LEO with an official patrol car (car with top-mounted emergency flashing lights and complete markings of the appropriate law enforcement agency) shall be provided for the following traffic control tasks:

- During the entire advance preparation and closure sequence where complete blockage of traffic is required.

- During a traffic signal installation when impacting the normal function of the signal or the flow of traffic, or when traffic needs to be directed through an energized traffic signal contrary to the signal display (e.g., directing motorists through a red light).

- During periods where traffic needs to be directed contrary to a traffic control device (flagger, sign [e.g. stop sign, street or highway signs, etc], signal or other device used to regulate, warn or guide traffic). Traffic in this instance includes vehicular, pedestrian and/or shared use path users.

In addition to the requirement of C&MS 614 and the OMUTCD, a uniformed LEO with an official patrol car (car with top-mounted emergency flashing lights and complete markings of the appropriate law enforcement agency) should be provided for the following traffic control tasks as approved by the Engineer:

- For lane closures that meet all of the criteria listed below: during initial set-up periods, tear down periods, substantial shifts of a closure point or when new lane closure arrangements are initiated for long-term lane closures/shifts (for the first and last day of major changes in traffic control setup).

  - Criteria

    - On a multi-lane divided interstate, other freeway or expressway; and,

    - An authorized speed limit of 45 mph or greater that is in effect at the time of the operation; and,

    - AADT of 50,000 (or AADT of 30,000 with 25% or higher percent trucks)

In general, LEOs should be positioned in advance of and on the same side as the lane restriction (or at the point of road closure), and to manually control traffic movements through signalized intersections and/or in contrary to other traffic control devices in work zones.

LEOs should not forgo their traffic control responsibilities to apprehend motorists for routine traffic violations. However, if a motorist’s actions are considered to be reckless, then pursuit of the motorist is appropriate.

The LEOs work at the direction of the Contractor. The Contractor is responsible for securing the services of the LEOs with the appropriate agencies and communicating the intentions of the plans with respect to duties of the LEOs. The Engineer shall have final control over the LEOs’ duties and placement, and will resolve any issues that may arise between the two parties.

Ensure provided LEOs have been trained appropriate to the job decisions they are required to make while on the project, in accordance with C&MS 614.03.

The LEO shall report in to the Contractor prior to the start of the shift, in order to receive instructions regarding specific work assignments during his/her shift. The LEO is expected to stay at the project site for the entire duration of his/her shift. The LEO shall report to the Contractor at the end of his/her shift. Should it be necessary to leave the project site, the LEO shall notify the Engineer. The Contractor shall provide the LEO with a two-way communication device that shall be returned to the Contractor at the end of his/her shift.

LEOs (with patrol car) required by the traffic maintenance tasks above shall be paid for on a unit price (hourly) basis under Item 614, Law Enforcement Officer (With Patrol Car) for Assistance. The following estimated quantities have been carried to the General Summary.

| Item 614, | Law Enforcement Officer With Patrol Car for Assistance | 100 Hours |
| --- | --- | --- |

The hours paid shall include any minimum show-up time required by the law enforcement agency involved.

Any additional costs (administrative or otherwise) incurred by the Contractor to obtain the services of an LEO are included with the bid unit price for Item 614, Law Enforcement Officer With Patrol Car for Assistance.

Work Zone Speed Zones (WZSZs)

The following Work Zone Speed Zone (WZSZ) Speed Limit Revision(s) have been approved for use on this project when work zone conditions and factors are met as described below:

| WZSZ Revision Number(s) | County-Route-Section(s) | Direction(s) |
| --- | --- | --- |
| WZ - 65281 | CUY-90-20.45 |  |

Potential WZSZ locations shall have an original (pre-construction) posted speed limit of 55 mph or greater, a qualifying work zone condition of at least 0.5 mile in length, an expected work duration of at least three hours, and a work zone condition in place that reduces the existing functionality of the travel lanes or shoulders (i.e., lane closure, lane shift, crossover, contraflow and/or shoulder closure). The length of the work zone condition is measured from the beginning of the taper for the subject work zone condition impacting the travel lanes and/or shoulder to the end of the downstream taper, where drivers are returned to typical alignment. An expected work duration of at least three hours is required to balance the additional exposure created by installing and removing WZSZ signing with the time needed to complete the work.

If the work zone meets these minimum criteria, it shall be analyzed further using Table 1 below to determine if and when it qualifies for a speed limit reduction. Depending on the original posted speed limit, the type of temporary traffic control used, and whether or not workers are present, a warranted WZSZ will vary in the approved speed limit to be posted over time.

C&MS Item 614, Paragraph 614.02(B), indicates that two directions of a divided highway are considered separate highway sections. Therefore, if the work on a multi-lane divided highway is limited to only one direction, a speed limit reduction in the direction of the work does not automatically constitute a speed limit reduction in the opposite direction. Each direction shall be analyzed independently from each other.

All WZSZS fluctuate between two approved reduced speed limits or between an approved reduced speed limit and the original posted speed limit. Only one of two signing strategies shall be used to implement a WZSZ.

WZSZS using DSL Sign Assemblies shall be in accordance with this note, Approved List, Supplemental Specifications (SS) 808 and 908, and Traffic SCD MT-104.10.

WZSZS using temporary flatsheet Speed Limit signs shall be in accordance with this note and SCD MT-104.10. Additionally payment may be removed, or a disincentive applied, for WZSZS using temporary flatsheet Speed Limit signs the same as described in the most recent publication of SS 808 in regards to WZSZS using DSL Sign Assemblies (see SS 808.06 paragraphs 4 through 7, including Table 1).]

Only one warranted speed limit applies at any one time; speed limit reductions are not cumulative. WZSZs shall not be used for Moving/Mobile activities, as defined in OMUTCD Part 6.

When looking up the warranted work zone speed limits, always use the original, pre-construction, posted speed limit. Do not use a prior or current work zone speed limit as a look up value in the table. Positive Protection is generally regarded as portable barrier or other rigid barrier in use along the work area within the subject warranted work zone condition. Without Positive Protection is generally regarded as using drums, cones, shadow vehicle, etc., along the work area within the subject warranted work zone condition. Workers are considered as being present when on-site, working within the subject warranted work zone condition. When the work zone condition reducing the existing functionality of the travel lanes or shoulders is removed, the speed limit displayed shall return to the original posted speed limit.

Table 1: Warranted Work Zone Speed Limits (MPH) for Work Zones on High-Speed (55 mph or greater) Multi-Lane Highways

|  | WITH Positive Protection |  | WITHOUT Positive Protection |  |
| --- | --- | --- | --- | --- |
| Original Posted Speed Limit | Workers Present | Workers NOT Present | Workers Present | Workers NOT Present |
| 70 | 60 | 65 | 55 | 65 |
| 65 | 55 | 60 | 50 | 60 |
| 60 | 55 | 60 | 50 | 60 |
| 55 | 50 | 55 | 45 | 55 |

The following estimated quantity has been carried to the General Summary.

| Item 808, | Digital Speed Limit (DSL) Sign Assembly | 48 Sign Mnth |
| --- | --- | --- |
| Assuming 8 DSL Sign Assembly(ies) for 6 Months |  |  |

Work Zone Increased Penalties Sign (R11-H5a)

R11-H5a-48 signs shall be furnished, erected, and maintained in good condition and/or replaced as necessary and subsequently removed by the Contractor. Signs shall be mounted at the appropriate offsets and elevations as prescribed by the Ohio Manual of Uniform Traffic Control Devices. They shall be maintained on supports meeting current safety criteria.

The signs may be erected or uncovered no more than four hours before the actual start of work.  The signs shall be removed or covered no later than four hours following restoration of all lanes to traffic with no restrictions, or sooner as directed by the Engineer. Temporary sign covering and uncovering due to temporary lane restorations shall be guided by the four-hour limitations stated above. Such lane restorations should be expected to remain in effect for 30 or more consecutive calendar days, such as during winter shut-downs.

The signs on the mainline shall be dual mounted unless not physically possible. The first sign shall be placed between the ROAD WORK AHEAD (W20-1) sign and the next sign in the sequence. Signs shall be erected on each entrance ramp and every 2 miles through the construction work limits. Signs on the mainline shall be R11-H5a-48. Signs used on the ramps shall be R11-H5a-24. R11-H5a-24 signs may be used in the median in lieu of R11-H5a-48 signs if it is not physically possible to provide R11-H5a-48 signs in the median.

The R11-H5a-48 signs shall be mounted on 2 No. 3 posts when located within clear zones.

The Contractor may use signs and supports in used, but good, condition provided the signs meet current ODOT specifications.

Work Zone Increased Penalties signs and supports will be measured as the number of sign installations, including the sign and necessary supports. If a sign and support combination is removed and reerected at another location as directed by the Engineer, it shall be considered another unit.

Payment for accepted quantities, complete, in place will be made at the contract unit price.  Payment shall be full compensation for all materials, labor, incidentals and equipment for furnishing, erecting, maintaining, covering during suspension of work, and removal of the sign and support.

| Item 614, | Work Zone Increased Penalties Sign | 16 Each |
| --- | --- | --- |

Worksite Traffic Supervisor

Subject to approval of the Engineer, the Contractor shall employ and identify (someone other than the superintendent) a prequalified Worksite Traffic Supervisor (WTS) before starting work in the field. The WTS shall be trained in accordance with CMS 614.03, shall have successfully completed ODOT administered WTS testing (and re-testing when applicable) and be listed on the ODOT prequalified WTS roster. Prequalification expires every 5 years. Re-testing shall be successfully repeated every 5 years to remain prequalified.

The name of the prequalified WTS and related 24-hour contact information shall be provided to the Engineer at the preconstruction conference. If the designated WTS will not be available full time (24/7), the Contractor may designate an alternate (secondary) WTS to be available when the primary is off duty; however, the primary WTS shall remain the point of contact at all times. Any alternate (secondary) WTS is subject to the same training, prequalification and other requirements outlined within this plan note. At all times the Engineer, or Engineer’s representatives, must be informed of who the primary WTS (and secondary WTS, if applicable) is at the current time.

The WTS position has the primary responsibility of implementing the Traffic Management Plan (TMP), monitoring the safety and mobility of the entire work zone, and correcting Temporary Traffic Control (TTC) deficiencies for the entire work zone. The WTS, and alternate WTS when on duty, shall have sufficient authority to effectively carry out the identified WTS responsibilities and duties. The duties of the WTS are as follows:

- Be available on a 24-hour per day basis.

- Be on site for all emergency TTC needs within one hour of notification by police or project staff, and effect corrective measures immediately on existing work zone TTC devices.

- Attend preconstruction meeting and all project meetings where TTC management is discussed.

- Be available on site for other meetings or discussions with the Engineer upon request.

- Be aware of all existing and proposed TTC operations of the contractor, subcontractors and suppliers, and ensure coordination occurs between them to eliminate conflicting temporary and/or permanent traffic control.

- Coordinate project activities with all Law Enforcement Officers (LEOs). The WTS shall also be the main contact person with the LEOs while LEOs are on the project.

- Coordinate and facilitate meetings with ODOT personnel, LEOs and other applicable entities before each plan phase switch to discuss the work zone TTC for implementing the phase switch. Submit a written detail of MOT operations and schedule of events to implement the switch between phase plans to the Engineer 5 calendar days prior to this meeting.

- Be present, on site for, and involved with, each TTC set up/take down and each phase change in accordance with CMS 614.03.

- On a continual basis ensure that the TTC zone and all related devices are installed, maintained and removed in compliance with the contract documents.

- On a continual basis facilitate corrective action(s) necessary to bring deficient TTC zones and all related devices into compliance with contract documents in the timeframe determined by the Engineer.

- Inspect, evaluate, propose necessary modifications to, and document the effectiveness of, the TTC devices and traffic operations on a DAILY BASIS (7 days a week). In addition, perform one weekly night inspection of the work zone setup for daytime work operations; and one daytime inspection per week for nighttime projects. This shall include (but not be limited to) documentation on the following project events:

  - Initial TTC setup (day and night review).

  - Daily TTC setup and removal.

  - When construction staging causes a change in the TTC setup.

  - Crash occurrences within the construction area and within the influence area(s) approaching the work zone.

  - Removal of TTC devices at the end of a phase or project.

  - All other emergency TTC needs.

- Complete the Department approved (CA-D-8) within GoFormz after each inspection as required in # 11 and submit it to the Engineer by the end of the workday in which the inspection occurred. The CA-D-8 includes a checklist of all TTC maintenance items to be reviewed. Contact GoFormz.Help@dot.ohio.gov to obtain a user account. Any deficiencies observed shall be noted on the CA-D-8, along with recommended or completed corrective actions and the dates by which such corrections were, or will be, completed. A copy of the current CA-D-8 document can be found on the Office of Construction Administration’s Inspection Forms website.

- Have copies of the ODOT Temporary Traffic Control Manual and contract documents available at all times on the project.

The Department will deduct:

- The prorated daily amount of Item 614 Maintaining Traffic for any day in which the WTS fails to perform the duties set forth above. The prorated daily amount will be equal to the original bid amount for Item 614 Maintaining Traffic divided by the difference between the original completion date and the first day of work, in calendar days.

- 1% of the original bid amount for Item 614 Maintaining Traffic for any day that a failure to perform WTS duties reoccurs or a TTC issue is identified in the field and is not corrected in the given timeframe per the Engineer. Deduction B shall not apply to situations covered by Deduction C.

- 1% of the original bid amount for Item 614 Maintaining Traffic for any day that a lane or ramp is blocked (fully or partially) without TTC, as determined by the Engineer. This deduction shall be in addition to any other disincentives established for unauthorized lane use.

For days in which more than one deduction listed above occur, the highest deduction amount will apply.

If three or more total days result in issues described in Deduction B or C above, the primary WTS (and any alternate WTS, if applicable) shall be immediately removed from the work in accordance with C&MS 108.05. Upon removal the Engineer shall notify ODOT Central Office (WTSPrequalification@dot.ohio.gov) to register a removal at the project level against the statewide prequalification for the primary WTS (and alternate WTS, if applicable). Accumulation of three project level removals (from any projects statewide) shall cause statewide disqualification for any formerly Prequalified WTS. A WTS (and alternate WTS, if applicable) may be immediately and concurrently removed from the work at the project level in accordance with C&MS 108.05 and disqualified statewide from the ODOT prequalified WTS roster (regardless of the number of project level removals), as well as being subject to other potential consequences, in cases of falsified, dishonest or otherwise unethical activity or documentation.

Payment for the above requirements, responsibilities and duties shall be included in the lump sum price bid for Item 614, Maintaining Traffic.

Traffic Incident Management (TIM) During MOT

Ohio TIM is Ohio’s traffic incident management program which is committed to maintaining the safe and effective flow of traffic during emergencies as to prevent further damage, injury or undue delay of the motoring public. In addition to complying with the provision of OMUTCD Chapter 6I, Control of Traffic Through Traffic Incident Management Areas, the Contractor shall actively participate in TIM planning and implementation as outlined below.

- Superintendent shall identify the individual persons on the project who will, or may need to, perform the duties herein. At a minimum, include the superintendent, foremen and supervisors (or equivalent) as well as the Worksite Traffic Supervisor (WTS; if applicable to the project). These individually identified persons shall collectively be known as Contractor Traffic Incident Management (TIM) Contacts. Notify the Project Engineer of the Contractor TIM Contacts (along with contact information for each) at or before the preconstruction meeting.

- Superintendent shall notify the Engineer immediately if any Contractor TIM Contact is added, removed or the contact information changes over the course of the project.

- Prior the first day of work in the field, each Contractor TIM Contact on the project shall have attended and successfully completed Ohio TIM Training provided by the Department or designee. Training information can be found online.

- Superintendent, at a minimum, shall attend and actively participate in a Department scheduled TIM meeting before construction work begins and before each phase change. These meetings will result in a Department issued project specific Traffic Incident Management Plan (TIMP). At the TIM meetings the attending Contractor TIM Contacts shall:

  - Collaborate with ODOT and Safety Forces;

  - Share project specific details that impact TIM responders; and

  - Recommend ways to incorporate necessary emergency access and other TIM elements for TIM responders given project specific work being completed and project specific phasing.

- Contractor TIM Contacts shall implement components of the resulting TIMP (such as approved emergency ingress/egress points, etc), as directed by the Engineer in accordance with 109.05.

- Contractor TIM Contacts shall perform, at a minimum, the following functions when an incident/crash occurs:

  - If observed or present when occurs, call 911 and then notify the Traffic Management Center (TMC) to provide the following:

    - Location, including milepost number and direction of travel

    - Number and type of vehicles involved, if known

    - Estimated extent of damage or injury, if known

    - Estimated number of patients involved, if known

    - Any potential hazardous conditions, if known

    - The placard number on any hazardous materials placard from a safe distance, if applicable and visible

  - Following an incident/crash:

    - Initiate traffic management/provide temporary traffic control as indicated in the TIMP, as directed by the Engineer in accordance with 109.05.

    - Recommend roadway repair needs.

    - Provide repair resources and initiate repairs, as directed by the Engineer in  accordance with 109.05.

    - Attend and participate in an After Action Review (AAR).

All costs, unless otherwise specified, resulting from the above requirements shall be considered to be included in the lump sum price for Item 614, Maintaining Traffic. Failure to perform the requirements of this Plan Note will result in a daily fine of 2% of Item 614, Maintaining Traffic and may result in one or more Contractor TIM Contacts being removed from the list of Ohio TIM trained individuals (at the sole discretion of the Ohio TIM Executive Committee). In the event an individual is removed from the Ohio TIM trained list, the individual will be removed from Contractor TIM Contact responsibilities on all projects.