## Sheet1
Parcel Number on R/W Plan | Owner Name | Acquisition Estimated Start Date | Estimated Months to Clear | Estimated ODOT Ownership Date | Parcel Available for Construction/Utility Relocation Date [Contractual] | Comments
18 | STEVEN L. SOLLARS AND LISA E. SOLLARS….. | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
21 | JOHN M. GERMANN | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
22 | MARIN LAND CO., AN OHIO COPORATION | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
23 | JOHN H HISER MARK S HISER | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
24 | WILEY INDUSTRIES, LLC, A DELAWARE LIMITED LIABILITY COMPANY | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
25 | FAYETTE COUNTY BOARD OF COMMISSIONERS | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12
27 | FAYETTE COUNTY BOARD OF COMMISSIONERS | 2023-06-20 | 9 months | 2024-04-04 | 2024-04-12