## Sheet1
PHASE 6R - Haul Road Requirements - Assumes July 2021 Sale
STONE - First 3 months after sale | [12 empty] | 750 | trucks | Could be done at night especially if we got a 12 hour window per day (7P-7A) from the OWJ
Causeway | 10000 |  | CY | x | 1.5 | tons/CY | = | 15000 | tons | / | 20 | tons/truck = | 750 | trucks
COFFERDAMS, FORMS, EQUIPMENT MOB - First 3 months after sale | [12 empty] | 10 | trucks | Nights ok
DRILLED SHAFT CASINGS - First 4 months after sale | [12 empty] | 10 | trucks | Nights ok
REBAR - First 6 months after sale | [12 empty] | 2 | trucks | Nights ok
CONCRETE 6 - 8 months after sale | [12 empty] | 332.9704 | trucks | Could be done at night, but possibly an issue for residents
Piers 13-17 | 11516 |  | CY | x | 5/22 piers |  | = | 2617.2727 | CY | / | 10 | CY/truck= | 261.7273 | trucks
Shafts 13&14 | 8 | ft | wide |  | 50 | deep | x | 6 | each | = | 279.1111 | CY | 27.9111 | trucks
Shafts 15-17 | 4.5 | ft | wide |  | 69 | shafts | x | 12 | each | = | 433.32 | CY | 43.332 | trucks
10' BRIDGE TUB GIRDERS & CRANES - 14-16 months after sale | [12 empty] | 30 | trucks | These cannot be driven down the slope - they need access from the bottom. Nights OK.
Assumed date of Zimmer Development (July 2022)
DECK POUR - 18-20 months after sale | [12 empty] | 93 | trucks
DEMOB MATERIALS AND EQUIPMENT - 20 months after sale | [12 empty] | 10 | trucks
REMOVE CAUSEWAY - 24 months after sale | [12 empty] | 750 | trucks
[13 empty] | 1987.9704 | Trucks Total
PHASE 6A - Haul Road Requirements
Phase 6A is mainly built while I-70 WB traffic is on the I-70 EB lanes, so we have a little more flexibility onto and off site. The intent was a hyper-build where the I-70W over the river and over the RR were done at the same time which would require access from the park or RR. However, if construction were done more sequentially then most access can be to and from the freeway level. However, as soon as the developer buys the RR property it can be appropriated and we will have access 3 monhts later, so 6A planning is less critical.