## MASTER
FRA-70-13.10 - Project 6A
Disincentive Amounts
DISINCENTIVE
# | SHEET | ACTIVITY | AFFECTED ROADWAY(S) | LENGTH OF DETOUR (MI) | LENGTH OF WORK ZONE (MI) | RESTRICTION TYPE | RESTRICTION TIME | CALCULATED | RECOMMENDED
1 |  | BEAM PLACEMENT OVER SR 315 SB TO I-71 SB MAINLINE | SR 315 SB TO I-71 SB MAINLINE | 5.7 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
2 |  | CROSSOVER CONSTRUCTION/REMOVAL OR BEAM PLACEMENT OVER I-71 NB TO I-70 WB RAMP | I-71 NB TO I-70 WB RAMP | 6.8 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
3 |  | BEAM PLACEMENT OVER I-71 NB TO SR 315 NB MAINLINE | I-71 NB TO SR 315 NB MAINLINE | 5.5 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
4 |  | BEAM PLACEMENT OVER I-70 EB MAINLINE | I-70 EB MAINLINE | 3.7 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
5 |  | BEAM PLACEMENT OVER I-70 WB TO I-71 SB RAMP | I-70 WB TO I-71 SB RAMP | 5.3 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
6 |  | BEAM PLACEMENT OVER SR 315 SB TO I-70 EB RAMP | SR 315 SB TO I-70 EB RAMP | 3.8 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
7 |  | BEAM PLACEMENT OVER I-70 WB MAINLINE | I-70 WB MAINLINE | 5 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
8 |  | TRAFFIC SWITCHES TO TR-1 | I-70 EB TO I-71 SB RAMP | 4.1 |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
9 |  | BEAM PLACEMENT OVER I-70 WB TO SR 315 NB RAMP | I-70 WB TO SR 315 NB RAMP |  |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
10 |  | BEAM PLACEMENT OVER I-70 WB TO RICH/TOWN RAMP | I-70 WB TO RICH/TOWN RAMP |  |  | ROAD CLOSURE | 10PM TO 5AM DAILY |  | SEE LANE VALUE CONTRACT TABLE
11 |  | WATER LINE INSTALLATION /RELOCATION W. MOUND STREET | W. MOUND ST. | 0.7 | 0.2 | ROAD CLOSURE | 1 CALENDAR DAY (WEEKEND ONLY) | $2,000 PER DAY | $2,000 PER DAY
12 |  | W. MOUND ST. & CIVIC CENTER DR. INTERSECTION CLOSURE | W. MOUND STREET & CIVIC CENTER DRIVE | 0.24 | 0.09 | ROAD CLOSURE | 45 CONSECUTIVE CALENDAR DAYS | $800 PER DAY | $1,000 PER DAY
13 |  | W. MOUND ST. & JEWETT ST. INTERSECTION CLOSURE | W. MOUND STREET & JEWETT STREET | 0.17 | 0.09 | ROAD CLOSURE | 20 CONSECUTIVE CALENDAR DAYS | $100 PER DAY | $1,000 PER DAY
14 |  | W. MOUND ST. & 2ND ST. INTERSECTION CLOSURE | W. MOUND STREET & 2ND STREET | 0.27 | 0.09 | ROAD CLOSURE | 30 CONSECUTIVE CALENDAR DAYS | $1,500 PER DAY | $1,500 PER DAY
15 |  | W. MOUND ST. & LUDLOW ST. INTERSECTION CLOSURE | W. MOUND STREET & LUDLOW STREET | 0.18 | 0.09 | ROAD CLOSURE | 20 CONSECUTIVE CALENDAR DAYS | $100 PER DAY | $1,000 PER DAY
16 |  | 2ND STREET RAMP TO I-70 WB RAMP CONSTRUCTION | 2ND STREET RAMP | 1.6 | 0.1 | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $2,800 PER DAY | $3,000 PER DAY
17 |  | 2ND STREET RAMP TO I-71 SB RAMP CONSTRUCTION | 2ND STREET RAMP | 1.6 | 0.1 | ROAD CLOSURE | 90 CONSECUTIVE CALENDAR DAYS | $2,800 PER DAY | $3,000 PER DAY
18 |  | SR 315 SB TO I-70 EB RAMP CLOSURE | SR 315 SB TO I-70 EB RAMP | 3.8 | 4.7 | ROAD CLOSURE | 360 CONSECUTIVE CALENDAR DAYS | $0 PER DAY* | $5,000 PER DAY
19 |  | W. MOUND ST. TO I-70 EB RAMP CLOSURE | W. MOUND ST. TO I-70 EB RAMP | 1.5 | 0.3 | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $9,400 PER DAY | $9,000 PER DAY
20 |  | I-70 WB TO SR 315 NB RAMP CLOSURE | I-70 WB TO SR 315 NB RAMP | 3.9 | 4.3 | ROAD CLOSURE | 360 CONSECUTIVE CALENDAR DAYS | $0 PER DAY* | $5,000 PER DAY
21 |  | I-70 WB TO RICH STREET CLOSURE | I-70 WB TO RICH STREET RAMP | 4.1 | 0.5 | ROAD CLOSURE | 360 CONSECUTIVE CALENDAR DAYS | $25,500 PER DAY | $25,000 PER DAY
22 |  | I-71 SB TO GREENLAWN AVE RAMP CLOSURE | I-71 SB TO GREENLAWN AVE. RAMP | 4.1 | 0.2 | ROAD CLOSURE | 30 CONSECUTIVE CALENDAR DAYS | $24,300 PER DAY | $25,000 PER DAY
23 |  | I-70 EB TO I-71 SB RAMP CLOSURE | I-70 EB TO I-71 SB RAMP | 4.1 | 3.6 | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $2,900 PER DAY | $3,000 PER DAY
24 |  | NORTHBOUND SHORT STREET CLOSURE | NORTHBOUND SHORT STREET | 0.61 | 0.25 | NB CLOSURE | 60 CONSECUTIVE CALENDAR DAYS | $1,300 PER DAY | $1,500 PER DAY
25 |  | CROSSOVER CONSTRUCTION/REMOVAL | I-70 EB (CYPRESS - SR 315) |  |  | LANE CLOSURE IN EXCESS MOT | 10PM TO 5AM DAILY |  | $200 PER MIN PER LANE
26 |  | CROSSOVER CONSTRUCTION/REMOVAL | I-70 WB (HIGH - FOURTH ST.) |  |  | LANE CLOSURE IN EXCESS MOT | 10PM TO 5AM DAILY |  | $200 PER MIN PER LANE
27 |  | RAMP TR-2B TIE IN CONSTRUCTION | I-70 WB (SHORT - HIGH) |  |  | LANE CLOSURE IN EXCESS MOT | 10PM TO 5AM DAILY |  | $200 PER MIN PER LANE
* Detour Length is shorter than the Work Zone Length (calculated amount is negative)
Notes:
City Street minimum disincentive = $1,000 PER DAY
Interstate minumum disincentive = $5,000 PER DAY

## PLAN - GENERAL NOTES
DO NOT EDIT DISINCENTIVES IN THIS TAB, USE MASTER TAB
DISINCENTIVE AMOUNTS FOR TYPICAL ROAD CLOSURES AND LANE RESTRICTIONS
ACTIVITY | AFFECTED ROADWAY(S) | RESTRICTION TYPE | SHEETS | RESTRICTION TIME | DISINCENTIVE
S.R. 315 SB TO I-71 SB CLOSURE | S.R. 315 SB MAINLINE | ROAD CLOSURE | 83-87 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-71 NB TO I-70 WB CLOSURE | I-71 NB TO I-70 WB RAMP | ROAD CLOSURE | 88-91 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-71 NB TO SR 315 NB CLOSURE | I-71 NB TO SR 315 NB MAINLINE | ROAD CLOSURE | 92-98 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 EB MAINLINE CLOSURE | I-70 EB MAINLINE | ROAD CLOSURE | 99-104 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 WB TO I-71 SB CLOSURE | I-70 WB TO I-71 SB RAMP | ROAD CLOSURE | 105-110 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
SR 315 SB TO I-70 EB CLOSURE | SR 315 SB TO I-70 EB RAMP | ROAD CLOSURE | 111-115 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 WB MAINLINE CLOSURE | I-70 WB MAINLINE | ROAD CLOSURE | 116-122 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 EB TO I-71 SB CLOSURE | I-70 EB TO I-71 SB RAMP | ROAD CLOSURE | 123-125 | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 WB TO SR 315 NB CLOSURE | I-70 WB TO SR 315 NB RAMP | ROAD CLOSURE | 126-131A | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE
I-70 WB TO RICH/TOWN CLOSURE | I-70 WB TO RICH/TOWN RAMP | ROAD CLOSURE | 131B-131F | 10PM TO 5AM DAILY | SEE LANE VALUE CONTRACT TABLE

## PHASE 1
DO NOT EDIT DISINCENTIVES IN THIS TAB, USE MASTER TAB
DISINCENTIVE AMOUNTS FOR PHASE 1 ROAD CLOSURES AND LANE RESTRICTIONS
ACTIVITY | AFFECTED ROADWAY(S) | RESTRICTION TYPE | RESTRICTION TIME | DISINCENTIVE
W. MOUND STREET WATER LINE INSTALLATION | W. MOUND ST. | ROAD CLOSURE/ LANE RESTRICTIONS | 1 CALENDAR DAY (WEEKEND ONLY) | $2,000 PER DAY
W. MOUND STREET STORM SEWER INSTALLATION AND UTILITY EXPLORATION | W. MOUND ST. & SHORT STREET | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $2,000 PER DAY
W. MOUND ST. & CIVIC CENTER DR. INTERSECTION CLOSURE | W. MOUND STREET & CIVIC CENTER DRIVE | ROAD CLOSURE | 45 CONSECUTIVE CALENDAR DAYS | $1,000 PER DAY
W. MOUND ST. & JEWETT ST. INTERSECTION CLOSURE | W. MOUND STREET & JEWETT STREET | ROAD CLOSURE | 20 CONSECUTIVE CALENDAR DAYS | $1,000 PER DAY
W. MOUND ST. & 2ND ST. INTERSECTION CLOSURE | W. MOUND STREET & 2ND STREET | ROAD CLOSURE | 30 CONSECUTIVE CALENDAR DAYS | $1,500 PER DAY
W. MOUND ST. & LUDLOW ST. INTERSECTION CLOSURE | W. MOUND STREET & LUDLOW STREET | ROAD CLOSURE | 20 CONSECUTIVE CALENDAR DAYS | $1,000 PER DAY

## PHASE 2
DO NOT EDIT DISINCENTIVES IN THIS TAB, USE MASTER TAB
DISINCENTIVE AMOUNTS FOR PHASE 2 ROAD CLOSURES AND LANE RESTRICTIONS
ACTIVITY | AFFECTED ROADWAY(S) | RESTRICTION TYPE | RESTRICTION TIME | DISINCENTIVE
2ND STREET RAMP TO I-70 WB RAMP CONSTRUCTION | 2ND STREET RAMP | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $3,000 PER DAY

## PHASE 3
DO NOT EDIT DISINCENTIVES IN THIS TAB, USE MASTER TAB
DISINCENTIVE AMOUNTS FOR PHASE 3 ROAD CLOSURES AND LANE RESTRICTIONS
ACTIVITY | AFFECTED ROADWAY(S) | RESTRICTION TYPE | RESTRICTION TIME | DISINCENTIVE
W. MOUND ST. TO I-70 EB RAMP CLOSURE | W. MOUND ST. TO I-70 EB RAMP | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $9,000 PER DAY
I-70 EB TO I-71 SB RAMP CLOSURE | I-70 EB TO I-71 SB RAMP | ROAD CLOSURE | 14 CONSECUTIVE CALENDAR DAYS | $3,000 PER DAY
2ND STREET RAMP TO I-71 SB RAMP CONSTRUCTION | 2ND STREET RAMP | ROAD CLOSURE | 90 CONSECUTIVE CALENDAR DAYS | $3,000 PER DAY

## PHASE 4
DO NOT EDIT DISINCENTIVES IN THIS TAB, USE MASTER TAB
DISINCENTIVE AMOUNTS FOR PHASE 4 ROAD CLOSURES AND LANE RESTRICTIONS
ACTIVITY | AFFECTED ROADWAY(S) | RESTRICTION TYPE | RESTRICTION TIME | DISINCENTIVE
SHORT STREET CONSTRUCTION | NB SHORT STREET (LIBERTY TO MOUND) | NB CLOSURE | 60 CONSECUTIVE CALENDAR DAYS | $1,500 PER DAY