## LEO with Patrol Car
Phase | Location | Operation | Number of LEOs | Hours per LEO | Total Hours | Notes
Typical Detours | SR 315 SB | Set-Up | 21 | 8 | 168 | Used during beam erections over SR 35 SB. Used for the removal an erection of Overhead Sign supports. 3 LEO's per setup/tear down.
|  | Tear-Down | 21 | 8 | 168
| I-71 NB to I-70 WB | Set-Up | 9 | 8 | 72 | Used during beam erections over the ramp from I-71 NB to I-70 WB. 3 LEO's per setup/tear down.
|  | Tear-Down | 9 | 8 | 72
| I-71 NB to SR 315 NB | Set-Up | 18 | 8 | 144 | Used during beam erections over I-71 NB to SR 315 NB. 3 LEO's per setup/tear down.
|  | Tear-Down | 18 | 8 | 144
| I-70 EB | Set-Up | 18 | 8 | 144 | Used during beam erections over I-70 EB. 3 LEO's per setup/tear down.
|  | Tear-Down | 18 | 8 | 144
| I-70 WB to I-71 SB | Set-Up | 21 | 8 | 168 | Used during beam erections over the ramp from I-70 WB to I-71 SB. Used for the removal an erection of Overhead Sign supports. 3 LEO's per setup/tear down.
|  | Tear-Down | 21 | 8 | 168
| SR 315 SB TO I-70 EB | Set-Up | 9 | 8 | 72 | Used during beam erections over the ramp from SR 315 SB to I-70 EB. 3 LEO's per setup/tear down.
|  | Tear-Down | 9 | 8 | 72
| I-70 WB | Set-Up | 18 | 8 | 144 | Used during beam erections over I-70 WB. Used for the removal an erection of Overhead Sign supports. 3 LEO's per setup/tear down.
|  | Tear-Down | 18 | 8 | 144
Phase 1 | I-71 SB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
| I-70 WB to I-71 SB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
| I-70 WB | Set-Up | 2 | 8 | 16 | Work zone set up/tear down for new bridge piers.
|  | Tear-Down | 2 | 8 | 16
| I-70 WB | Set-Up | 2 | 8 | 16 | Work zone set up/tear down for median work for new sign truss.
|  | Tear-Down | 2 | 8 | 16
Phase 2A-2C | I-71 SB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
Phase 2D | I-70 WB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
Phase 3A | I-70 WB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
| Ramp D6 | Set-Up | 1 | 8 | 8 | One LEO at the ramp during initial closure
|  | Tear-Down | 1 | 8 | 8
Phase 3B | Mound to I-70 EB | Set-Up | 1 | 8 | 8 | One LEO at the ramp during initial closure
|  | Tear-Down | 1 | 8 | 8
| I-70 EB to I-71 SB | Set-Up | 1 | 8 | 8 | One LEO at the ramp during initial closure
|  | Tear-Down | 1 | 8 | 8
| I-71 SB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
| I-70 EB | Set-Up | 2 | 8 | 16
|  | Tear-Down | 2 | 8 | 16
PHASE 3C |  | Final Paving & Striping | 6 | 8 | 48
|  |  |  | Total | 2208

## LEO without Patrol Car
Phase | Location | Operation | Number of LEOs | Hours per LEO | Total Hours | Notes
1D | 2nd & Mound | Set-Up | 1 | 8 | 8 | Set up and tear down work zone within the signalized intersection
|  | Tear-Down | 1 | 8 | 8
1D | Mound & Front |  | 1 | 16 | 16 | Interconnect work within the intersection
2D | 2nd & Mound | Set-Up | 1 | 8 | 8 | Set up and tear down work zone within the signalized intersection
|  | Tear-Down | 1 | 8 | 8
|  |  |  | Total | 48