ITEM 614, MAINTAINING TRAFFIC

A MINIMUM OF TWO (2) LANES OF TRAFFIC IN EACH DIRECTION SHALL BE MAINTAINED ON GUE-70 AT ALL TIMES, EXCLUDING THE CLOSURE TIMES STATED IN THE LANE VALUE CONTRACT TABLE BELOW. RAMP CLOSURES

AT THE GUE-70/285 INTERCHANGE ARE PERMITTED PER THE INCENTIVE/ DISINCENTIVE CONTRACT TABLE.

LANE VALUE CONTRACT TABLE

| LOCATION | CRITICAL WORK: TIME WHEN ONE (1) LANE/RAMP MAY BE CLOSED | TIME UNIT | DISINCENTIVE ($ PER TIME UNIT) |
| --- | --- | --- | --- |
| GUE-70- 12.32-17.52 E.B. & W.B. | MAINLINE PAVEMENT REPAIR 6PM SUNDAY- 10AM THURSDAY (MAY 1ST TO AUGUST 1ST) ALL OTHER WORK ODOT PLCS WEBSITE (WEBSITE LINK ON THIS SHEET) | 15 MIN. | $2,500 |

INCENTIVE/ DISINCENTIVE CONTRACT TABLE

| LOCATION | I.R. 70 & S.R. 285 INTERCHANGE |  |  |  |
| --- | --- | --- | --- | --- |
| CRITICAL WORK: TIME WHEN RAMP MAY BE CLOSED | RAMP A | RAMP B | RAMP C | RAMP D |
| DAYS | 14 | 14 | 14 | 14 |
| INCENTIVE/ DISENCETIVE PER DAY | $5K | $5K | $5K | $5K |
| MAXIMUM INCENTIVE | $10K | $10K | $10K | $10K |

THE CONTRACTOR SHALL NOTIFY THE PROJECT ENGINEER AT LEAST THREE

(3) BUSINESS DAYS IN ADVANCE OF IMPLEMENTATION OF THE RAMP CLOSURES SO THAT THE PROJECT ENGINEER CAN SEND EMAIL NOTIFICATION TO THE OFFICE OF STATEWIDE TMC, DWZTM AND SPECIAL HAULING PERMITS AT LEAST TWO (2) BUSINESS DAYS IN ADVANCE OF THE LANE CLOSURE.

THE CONTRACTOR SHALL PROVIDE NOTICE OF RAMP CLOSURES TO ALL TRAFFIC AT LEAST SEVEN CALENDAR DAYS IN ADVANCE OF CLOSURE THROUGH THE USE OF PORTABLE CHANGEABLE MESSAGE SIGNS. THE

PCMS SHOULD BE ERECTED AS SHOWN IN THE PLANS AND/OR AS DIRECTED

BY THE ENGINEER. THE PCMS SHOULD BE ERECTED WELL IN ADVANCE OF

THE CLOSURE AREA TO AVOID DISTRACTING MOTORISTS. TEMPORARY TRAFFIC SIGNALS MAY BE NECESSARY AT THE I.R. 70/ S.R. 285 INTERCHANGE FOR RAMP CONCRETE PAVEMENT REMOVAL AND REPLACMENT. THEY SHALL BE REMOVED ONCE MATERIAL HAS CURED, AS DIRECTED BY THE ENGINEER.

AREAS THAT ARE PLANED SHALL NOT BE OPENED TO TRAFFIC. ALL PLANED AREAS MUST BE INLAID WITH A PROPOSED COURSE OF ITEM 442,

ASPHALT CONCRETE PRIOR TO BEING OPENED TO TRAFFIC.

LANE CLOSURES WILL BE ACCOMPLISHED IN ACCORDANCE WITH THE STANDARD DRAWINGS LISTED ON THE TITLE SHEET, IN CONSIDERATION

OF THE TRAFFIC FLOW. LANE CLOSURES SHALL ONLY OCCUR DURING CONTRACTOR WORK HOURS.

ITEM 614, MAINTAINING TRAFFIC (CONT’D)

OVERNIGHT CLOSURES MUST MEET SPECIFICATIONS AS OUTLINED IN THE CONSTRUCTION AND MAINTENANCE OPERATIONS SECTION OF THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES FOR STREETS AND HIGHWAYS. THE ROADWAY SHALL NOT BE OPENED TO TRAFFIC WITHOUT EITHER THE PERMANENT OR WORK ZONE MARKINGS IN PLACE.

LENGTH AND DURATION OF LANE CLOSURES AND RESTRICTIONS SHALL BE NO LONGER THAN 2 MILES, UNLESS DIRECTED BY THE ENGINEER. IT IS THE INTENT TO MINIMIZE THE IMPACT TO THE TRAVELING PUBLIC. LANE CLOSURES OR RESTRICTIONS OVER SEGMENTS OF THE PROJECT, IN WHICH NO WORK IS ANTICIPATED WITHIN A REASONABLE TIME FRAME, AS DETERMINED BY THE ENGINEER, SHALL NOT BE PERMITTED. THE LEVEL OF UTILIZATION OF MAINTENANCE OF TRAFFIC DEVICES SHALL BE COMMENSURATE WITH THE WORK IN PROGRESS. THE CONTRACTOR WILL HAVE ON SITE AND IN WORKING AND OR SUITABLE CONDITION; ALL EQUIPMENT, TOOLS, LABORERS, LEO'S, TRAFFIC CONTROL DEVICES AND INCIDENTALS NECESSARY TO EFFICIENTLY PERFORM THE CLOSURE BEFORE INITIALIZING THE LANE CLOSURE.

ALL WORK AND TRAFFIC CONTROL DEVICES SHALL BE IN ACCORDANCE WITH CMS 614 AND OTHER APPLICABLE PORTIONS OF THE SPECIFICATIONS, AS WELL AS THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. PAYMENT FOR ALL LABOR, EQUIPMENT AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR ITEM 614, MAINTAINING TRAFFIC, UNLESS SEPARATELY ITEMIZED IN THE PLAN.

WORK RESTRICTIONS

NO WORK SHALL OCCUR PRIOR TO MAY 1ST, 2026 UNLESS APPROVED BY THE ENGINEER.

INTERIM COMPLETION DATE

THE ALLOWABLE LANE CLOSURES STATED IN THE LANE VALUE CONTRACT TABLE FOR “MAINLINE PAVEMENT REPAIR” WORK SHALL BE COMPLETED BY AUGUST 1ST, 2026. ALL LANE CLOSURES AFTER THIS DATE SHALL ADHERE TO THE PERMITTED LANE CLOSURE SCHEDULE (PLCS) PLAN NOTE LISTED ON THIS SHEET.

NOTIFICATION OF ROAD CLOSURE OR RESTRICTIONS

THE CONTRACTOR WILL ADVISE THE PROJECT ENGINEER A MINIMUM OF TWENTY-ONE (21) DAYS PRIOR TO THE FOLLOWING:  THE START OF CONSTRUCTION ACTIVITIES, LANE RESTRICTIONS, LANE CLOSURES, AND/OR ROAD CLOSURES.  THE PROJECT ENGINEER WILL FORWARD THIS INFORMATION TO THE FOLLOWING:

DISTRICT PUBLIC INFORMATION OFFICER (PIO) BY FAX AT (614) 887-4510

OR EMAIL AT D05.pio@dot.ohio.gov

DISTRICT PERMIT SECTION BY FAX AT (614) 887-4525 OR EMAIL AT brian.bosch@dot.ohio.gov

CENTRAL OFFICE SPECIAL HAUL PERMITS SECTION BY FAX AT (614) 728-4099 OR EMAIL AT hauling.permits@dot.ohio.gov

THE PIO WILL, IN TURN, NOTIFY THE PUBLIC, THE LOCAL EMERGENCY SERVICES, AFFECTED SCHOOLS AND BUSINESSES, AND ANY OTHER IMPACTED LOCAL PUBLIC AGENCY OF ANY OF THE ABOVE-MENTIONED ITEMS, VIA MEDIA SOURCES.

LANES OPEN DURING HOLIDAYS OR SPECIAL EVENTS

NO WORK SHALL BE PERFORMED AND ALL EXISTING LANES ON I.R. 70 SHALL BE OPENED TO TRAFFIC DURING THE FOLLOWING DESIGNATED HOLIDAYS

OR EVENTS: EASTER, MEMORIAL DAY, FOURTH OF JULY, LABOR DAY, THANKSGIVING, CHRISTMAS, NEW YEARS

The period of time that the lanes are to be open depends on the day of the week on which the holiday or event falls. The following schedule shall be used to determine this period:

| DAY OF WEEK | TIME ALL LANES MUST BE OPEN TO TRAFFIC |
| --- | --- |
| SUNDAY | 12:00N FRIDAY THROUGH 6:00AM MONDAY |
| MONDAY | 12:00N FRIDAY THROUGH 6:00AM TUESDAY |
| TUESDAY | 12:00N MONDAY THROUGH 6:00AM WEDNESDAY |
| WEDNESDAY | 12:00N TUESDAY THROUGH 6:00AM THURSDAY |
| THURSDAY | 12:00N WEDNESDAY THROUGH 6:00AM FRIDAY |
| THURSDAY (THANKSGIVING) | 12:00N WEDNESDAY THROUGH 6:00AM MONDAY |
| FRIDAY | 12:00N THURSDAY THROUGH 6:00AM MONDAY |
| SATURDAY | 12:00N FRIDAY THROUGH 6:00AM MONDAY |

Should the Contractor fail to meet any of these requirements,

the Contractor shall be assessed A DISINCENTIVE PER LANE VALUE CONTRACT (PN 127).

PERMITTED LANE CLOSURE SCHEDULE (PLCS)

LANE CLOSURE(S) SHALL CONFORM TO THE PLCS. PUBLISHED PLCS INFORMATION CAN BE FOUND ON THE ODOT WEBSITE AT:

https://www.transportation.ohio.gov/working/data-tools/resources/permitted-lane-closure

THE MONTHLY PUBLISHED SCHEDULES REQUIRED TO BE USED, FOR EACH PLCS SEGMENT WITHIN THE PROJECT AREA, ARE THOSE THAT COMPRISE THE CONSECUTIVE 12-MONTH PERIOD BEGINNING SEPTEMBER 2024 THROUGH AUGUST 2025. THESE SAME 12 MONTHS APPLY FOR THE LIFE OF THE PROJECT AND SHALL BE APPLIED TO EACH RESPECTIVE MONTH OF CONSTRUCTION (MONTH OF LANE CLOSURE(S) SHALL MATCH MONTH OF PLCS USED). LANE CLOSURE(S) IN PLACE FOR MULTIPLE MONTHS SHALL ALWAYS COMPLY WITH THE CURRENT RESPECTIVE MONTH.

MORE RESTRICTIVE CHANGES TO THE ALLOWABLE LANE CLOSURE HOURS ARE AT THE DISCRETION OF THE ENGINEER IN ORDER TO COMPLY WITH THE TRAFFIC MANAGEMENT IN WORK ZONES POLICY (21-008(P)) AND STANDARD PROCEDURE (123-001(SP)). LESS RESTRICTIVE CHANGES TO THE ALLOWABLE LANE CLOSURE HOURS ARE SUBJECT TO THE TRAFFIC MANAGEMENT IN WORK ZONES POLICY (21-008(P)) AND STANDARD PROCEDURE (123-001(SP)) AND SHALL NOT BE IMPLEMENTED UNTIL, AND UNLESS, APPROVED BY THE PROPER ODOT AUTHORITY.  ALLOWABLE LANE CLOSURE HOURS FOR FACILITIES NOT COVERED BY THE PLCS, IF ANY, SHALL BE AS SPECIFIED ELSEWHERE IN THE PLANS.

EXISTING MOT EXCEPTIONS THAT HAVE ALREADY BEEN APPROVED IN ACCORDANCE TO THE TRAFFIC MANAGEMENT IN WORK ZONES POLICY AND STANDARD PROCEDURE ARE DETAILED IN THE APPROVED MAINTENANCE OF TRAFFIC (MOT) POLICY EXCEPTION(S) PLAN NOTE ON SHEET 8.

ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE

Use of law enforcement officers (LEOs) by contractorsother than the uses specified in this note will not be permitted at project cost.  LEOs should not be used where the Ohio Manual of Uniform Traffic Control Devices(OMUTCD) intends that flaggers be used.

In addition to the requirements of C&MS 614 and the OMUTCD, a uniformed LEO with an official patrol car (car with top-mounted emergency flashing lights and complete markings of the appropriate law enforcement agency) should be provided for controlling traffic for the following tasks, as directed BY THE ENGINEER:

- For lane closures: during initial set-up periods, tear down periods, substantial shifts of a closure point or when new lane closure arrangements are Initiated, and night work

on the interstate.

In general, LEOs should be positioned at the point of lane restriction or road closure and to manually control traffic movements through intersections in work zones.

LEOs should not forgo their traffic control responsibilities to apprehend motorists for routine traffic violations.  However, if

a motorist’s actions are considered to be reckless, then pursuit

of the motorist is appropriate.

The LEOs work at the direction of the Contractor.  The Contractor is responsible for securing the services of the LEOs and communicating the intentions of the plans with respect to duties of the LEOs. The Engineer shall have final control over the LEOs’ duties and PLACEMENT AND will resolve any issues that may arise between the two parties.

The LEO shall report in to the Contractor prior to the start of the shift to receive instructions regarding specific work assignments during his/her shift.  The LEO is expected to stay at the project site for the entire duration of his/her shift. the leo shall report to the contractor at the end of his/her shift. once the leo has completed the duties described above and still has time remaining on his/her shift, the leo may be asked to patrol through the work zone (with flasihg lights off) or be placed at a location to deter motorists from speeding.  should it be necessary to leave the project site, the leo shall notify the engineer. The Contractor shall provide the LEO with a two-way communication device which shall be returned to the Contractor at the end of his/her shift.

Law enforcement officers (with patrol car) required by the traffic maintenance tasks above shall be paid for on a unit price (hourly) basis under Item 614, Law Enforcement Officer (With Patrol Car) for assistance. The hours paid shall include minimum show-up time required by the law enforcement agency involved.

Any additional costs (administrative or otherwise) incurred by the Contractor to obtain the services of a LEO are included with the bid unit price for Item 614, Law enforcement Officer With Patrol Car FOR ASSISTANCE.

Item 614 Law Enforcement Officer With Patrol CaR FOR ASSISTANCE

Location 1:  800 Hour

ITEM 614, PORTABLE CHANGEABLE MESSAGE SIGN, AS PER PLAN

The Contractor shall furnish, install, maintain and remove, when no longer needed, A changeable message sign, on site, for the duration of the project.  The sign shall be of a type shown on a list of approved PCMS units AVAILABLE ON THE Office of Materials Management WEB PAGE.  The list contains Class A and B units with minimum legibility distances of 650 FEET and 475 FEET, respectively.

Each sign shall be trailer-mounted and equipped with a functional dimming mechanism, to dim the sign during darkness, and a tamper and vandal proof enclosure.  Each sign shall be provided with appropriate training and operation instructions to enable on-site personnel to operate and troubleshoot the unit.  The sign shall also be capable of being powered by an electrical service drop from a local utility company.  THE PCMS SHALL BE DELINEATED IN ACCORDANCE WITH C&MS 614.03.

The probable PCMS locations and work limits for those locations are shown on sheet(s) of the plan.  Placement, operation, maintenance and all activation of the signs by the Contractor shall be as directed by the Engineer.  The PCMS shall be located in a highly visible position yet protected from traffic. The Contractor shall, at the direction of the Engineer, relocate the PCMS to improve visibility or accommodate changed conditions.  When not in use, the PCMS shall be turned off.  Additionally, when not in use for extended periods of time, the PCMS shall be turned, facing away from all traffic.

The Engineer shall be provided access to each sign unit and shall be provided with appropriate training and operation instructions to enable ODOT personnel to operate and troubleshoot the unit, and to revise sign messages, if necessary.

The Contractor shall implement a system whereby changeable messages will be implemented within 2 hours following telephone notification from the Project Engineer to a designated phone.

All messages to be displayed on the sign will be provided by the Engineer.  A list of all required pre-programmed messages will be given to the Contractor at the project preconstruction conference.  The sign shall have the capability to store up to 99 messages.  Message memory or pre-programmed displays shall not be lost as a result of power failures to the on-board computer.  The sign legend shall be capable of being changed in the field.  three-line presentation formats with up to six message phases shall be supported.  PCMS format shall permit the complete message for each phase to be read at least twice.

The PCMS shall contain an accurate clock and programming logic which will allow the sign to be activated, deactivated or messages changed automatically at different times of the day for different days of the week.

ITEM 614, PORTABLE CHANGEABLE MESSAGE SIGN, AS PER PLAN (Cont’d.)

The PCMS unit shall be maintained in good working order by the Contractor in accordance with the provisions of C&MS 614.07.  The Contractor shall, prior to activating the unit, make arrangements, with an authorized service agent for the PCMS, to assure prompt service in the event of failure.  Any failure shall not result in the sign being out of service for more than 12 hours, including weekends.  Failure to comply may result in an order to stop work and open all traffic lanes and/or in the Department taking appropriate action to safely control traffic.  The entire cost to control traffic, accrued by the Department due to the Contractor’s noncompliance, will be deducted from moneys due, or to become due the Contractor on his contract.

The Contractor shall be responsible for 24-hour-per-day operation and maintenance of these signs on the project for the duration of the phases when the plan requires their use.

Payment for the ABOVE-DESCRIBED item shall be at the contract unit price.  Payment shall include all labor, materials, equipment, fuels, lubricating oils, software, HARDWARE, and incidentals to perform the ABOVE-DESCRIBED work.

a total of 8 pcms WILL be required for this project.

RESURFACING WORK

(PLACE 2-MILE AND 6-MILE FROM BEGIN/ END WORK LIMITS)

I.R. 70 EB: 2 PCMS X 6 MONTH = 12 SNMT

I.R. 70 WB: 2 PCMS X 6 MONTH = 12 SNMT

RAMP CLOSURES

(PLACE AS DIRECTED BY THE ENGINEER)

4 PCMS X 1 MONTH = 4 SNMT

Item 614 Portable Changeable Message Sign, AS PER PLAN

Location 1:  28 SNMT

DAYTIME LANE CLOSURES FOR MARKING REPAIRS

THE CONTRACTOR SHALL PROVIDE TRAFFIC CONTROL FOR DAYTIME LANE CLOSURES TO PROVIDE A SAFE AREA FOR ODOT PERSONAL TO MARK PAVEMENT AND BRIDGE REPAIRS AHEAD OF RESURFACING OPERATIONS. THE CLOSURE WILL BE A MOVING OPERATION AND SHALL ADHERE TO MT-99.20, AT THE APPROVAL OF THE ENGINEER. THE ESTIMATED COMPLETION TIME TO MARK THE PAVEMENT REPAIRS IS FIVE (5) 6-HOUR WORKDAYS, to be performed during THE PERMITTED lane closure schedule (PLCS). PAYMENT SHALL BE INCLUDED IN THE LUMP SUM BID FOR ITEM 614, MAINTAINING TRAFFIC.

DROP-OFFS IN WORK ZONES

DROP-OFFS THAT DEVELOP DURING CONSTRUCTION OPERATIONS AND THAT ARE NOT OTHERWISE PROVIDED FOR IN THE PLANS SHALL BE TREATED AS SHOWN ON STANDARD DRAWING MT-101.90.  WHERE THE PLANS DO NOT PROVIDE SPECIFIC ITEMS FOR LABOR, EQUIPMENT, OR MATERIALS TO IMPLEMENT THE DROP-OFF TREATMENTS SPECIFIED, THEY SHALL BE INCLUDED FOR PAYMENT IN THE LUMP SUM BID FOR ITEM 614, MAINTAINING TRAFFIC.

ITEM 614, WORK ZONE SPEED ZONES (WZSZS)

THE FOLLOWING WORK ZONE SPEED ZONE (WZSZ) SPEED LIMIT REVISION(S) HAVE BEEN APPROVED FOR USE ON THIS PROJECT WHEN WORK ZONE CONDITIONS AND FACTORS ARE MET AS DESCRIBED BELOW:

WZSZ REVISION NUMBER	  COUNTY & ROUTE                 DIRECTION

WZ-30811	                   GUE-70-(12.32-17.52)             eb/wb

POTENTIAL WZSZ LOCATIONS SHALL HAVE AN ORIGINAL (PRE-CONSTRUCTION) POSTED SPEED LIMIT OF ≥ 55 MPH, A QUALIFYING WORK ZONE CONDITION OF AT LEAST 0.5 MILEIN LENGTH, AN EXPECTED WORK DURATION OF AT LEAST THREE HOURS, AND A WORK ZONE CONDITION IN PLACE THAT REDUCES THE EXISTING FUNCTIONALITY OF THE TRAVEL LANES OR SHOULDERS (I.E., LANE CLOSURE, LANE SHIFT, CROSSOVER, CONTRAFLOW AND/OR SHOULDER CLOSURE). THE LENGTH OF THE WORK ZONE CONDITION IS

MEASURED FROM THE BEGINNING OF THE TAPER FOR THE SUBJECT WORK ZONE CONDITION IMPACTING THE TRAVEL LANES AND/OR SHOULDER TO THE END OF THE DOWNSTREAM TAPER, WHERE DRIVERS ARE RETURNED TO TYPICAL ALIGNMENT. AN EXPECTED WORK DURATION OF AT LEAST THREE HOURS IS REQUIRED TO BALANCE THE ADDITIONAL EXPOSURE CREATED BY INSTALLING AND REMOVING WZSZ SIGNING WITH THE TIME NEEDED TO COMPLETE THE WORK.

IF THE WORK ZONE MEETS THESE MINIMUM CRITERIA, IT SHALL BE ANALYZED FURTHER USING TABLE 1 BELOW TO DETERMINE IF AND WHEN IT QUALIFIES FOR A SPEED LIMIT REDUCTION. DEPENDING ON THE ORIGINAL POSTED SPEED LIMIT, THE TYPE OF TEMPORARY TRAFFIC CONTROL USED, AND WHETHER OR NOT WORKERS ARE PRESENT, A WARRANTED WZSZ WILL VARY IN THE APPROVED SPEED LIMIT TO BE POSTED OVER TIME.

C&MS ITEM 614, PARAGRAPH 614.02(B), INDICATES THAT TWO DIRECTIONS OF A DIVIDIED HIGHWAY ARE CONSIDERED SEPARATE HIGHWAY SECTIONS. THEREFORE, IF THE WORK ON A MULTI-LANE DIVIDED HIGHWAY IS LIMITED TO ONLY ONE DIRECTION, A SPEED LIMIT REDUCTION IN THE DIRECTION OF THE WORK DOES NOT AUTOMATICALLY CONSTITUTE A SPEED LIMIT REDUCTION IN THE OPPOSITE DIRECTION. EACH DIRECTION SHALL BE ANALYZED INDEPENDENTLY FROM EACH OTHER.

ALL WZSZS FLUCTUATE BETWEEN TWO APPROVED REDUCED SPEED LIMITS OR BETWEEN AN APPROVED REDUCED SPEED LIMIT AND THE ORIGINAL POSTED SPEED LIMIT. ONLY ONE OF TWO SIGNING STRATEGIES SHALL BE USED TO IMPLEMENT A WZSZ.

WZSZS USING DSL SIGN ASSEMBLIES SHALL BE IN ACCORDANCE WITH THIS NOTE, SUPPLEMENTAL SPECIFICATIONS 808, 908 AND TRAFFIC SCD MT-104.10

ONLY ONE WARRANTED SPEED LIMIT APPLIES AT ANY ONE TIME; SPEED LIMIT REDUCTIONS ARE NOT CUMULATIVE. WZSZS SHALL NOT BE USED FOR MOVING/MOBILE ACTIVITIES, AS DEFINED IN OMUTCD PART 6.

ITEM 614, WORK ZONE SPEED ZONES (WZSZS) (Cont’d.)

WHEN LOOKING UP THE WARRANTED WORK ZONE SPEED LIMITS, ALWAYS USE THE ORIGINAL, PRE-CONSTRUCTION, POSTED SPEED LIMIT. DO NOT USE A PRIOR OR CURRENT WORK ZONE SPEED LIMIT AS A LOOK UP VALUE IN THE TABLE. POSITIVE PROTECTION IS GENERALLY REGARDED AS PORTABLE BARRIER OR OTHER RIGID BARRIER IN USE ALONG THE WORK AREA WITHIN THE SUBJECT WARRANTED WORK ZONE CONDITION. WITHOUT POSITIVE PROTECTION IS GENERALLY REGARDED AS USING DRUMS, CONES, SHADOW VEHICLE, ETC., ALONG THE WORK AREA WITHIN THE SUBJECT WARRANTED WORK ZONE CONDITION. WORKERS ARE CONSIDERED AS BEING PRESENT WHEN ON-SITE, WORKING WITHIN THE SUBJECT WARRANTED WORK ZONE CONDITION. WHEN THE WORK ZOE CONDITION REDUCING THE EXISTING FUNCTIONALITY OF THE TRAVEL LANES OR SHOULDERS IS REMOVED, THE SPEED LIMIT DISPLAYED SHALL RETURN TO THE ORIGINAL POSTED SPEED LIMIT.

TABLE 1: WARRANTED WORK ZONE SPEED LIMITS (MPH) FOR WORK ZONES ON HIGH-SPEED (≥55 MPH) MULTI-LANE HIGHWAYS.

| original posted speed limit | with positive protection |  | without positive protection |  |
| --- | --- | --- | --- | --- |
|  | workers present | workers not present | workers present | workers not present |
| 70 | 60 | 65 | 55 | 65 |
| 65 | 55 | 60 | 50 | 60 |
| 60 | 55 | 60 | 50 | 60 |
| 55 | 50 | 55 | 45 | 55 |

a total of 6 DSL SIGN ASSEMBLIES WILL be required for this project.

2-mile moving zone (resurfacing)

I.R. 70 EB: 3 DSL X 6 MONTH = 18 SNMT

I.R. 70 WB: 3 DSL X 6 MONTH = 18 SNMT

ITEM 614, DIGITAL SPEED LIMIT (DSL) SIGN ASSEMBLY

Location 1:  36 SNMT

FLOODLIGHTING

FLOODLIGHTING OF THE WORK SITE FOR OPERATIONS CONDUCTED DURING NIGHTTIME PERIODS SHALL BE ACCOMPLISHED SO THAT THE LIGHTS DO NOT CAUSE GLARE TO THE DRIVERS ON THE ROADWAY. TO ENSURE THE ADEQUACY OF THE FLOODLIGHT PLACEMENT, THE CONTRACTOR AND THE ENGINEER SHALL DRIVE THROUGH THE WORK SITE EACH NIGHT WHEN THE LIGHTING IS IN PLACE AND OPERATIVE PRIOR TO COMMENCING ANY WORK. IF GLARE IS DETECTED, THE LIGHT PLACEMENT AND SHIELDING SHALL BE ADJUSTED TO THE SATISFACTION OF THE ENGINEER BEFORE WORK PROCEEDS. PAYMENT FOR ALL LABOR, EQUIPMENT AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM BID FOR ITEM 614, MAINTAINING TRAFFIC.

ITEM 614, WORK ZONE PAVEMENT MARKINGS

THE CONTRACTOR SHALL PLACE ALL WORK ZONE PAVEMENT MARKINGS IN ACCORDANCE WITH CMS 614.11 AND STANDARD DRAWING MT-99.20 UNLESS OTHERWISE DIRECTED BY THE ENGINEER. THE FOLLOWING QUANTITIES ARE BEING CARREID TO THE LOCATION SUB- SUMMARIES FOR PLACEMENT OF TEMPORARY MARKINGS ON THE SURFACE COURSE FOR ENTIRE PROJECT.

ITEM 614, WORK ZONE LANE LINE, CLASS I, 6”, 642 PAINT

(TWO APPLICATIONS INCLUDED FOR CUTBACK JOINT)

LOCATION 1:  20.80 MILE

ITEM 614, WORK ZONE EDGE LINE, CLASS I, 6”, 642 PAINT

(TWO APPLICATIONS INCLUDED FOR OUTSIDE WHITE EDGE LINES)

LOCATION 1:  32.62 MILE (INCLUDES RAMPS)

ITEM 614, WORK ZONE CHANNELIZING LINE, CLASS I, 12”, 642 PAINT

LOCATION 1:  3,755 FEET

ITEM 614, WORK ZONE DOTTED LINE, CLASS I, 6”, 642 PAINT

LOCATION 1:  2,805 FEET

ITEM 614, WORK ZONE STOP LINE, CLASS III, 642 PAINT

LOCATION 1:  155 FEET (RAMPS)

ITEM 614, WORK ZONE MARKING SIGN

THE CONTRACTOR SHALL PLACE ALL WORK ZONE MARKING SIGNS

IN ACCORDANCE WITH CMS SECTION 614.04, UNLESS OTHERWISE

DIRECTED BY THE ENGINEER.

W8-H12A-48 (NO EDGE LINES)

ONE PER MILE FOR PAVEMENT REPAIRS (SEE SHEET 9)

ITEM 614, WORK ZONE MARKING SIGN

LOCATION 1:     10 EACH

ITEM 614, REPLACEMENT DRUM

DRUMS FURNISHED BY THE CONTRACTOR IN ACCORDANCE WITH THE REQUIREMENTS OF THE PLANS, SPECIFICATIONS, AND PROPOSAL WHICH BECOME DAMAGED BY TRAFFIC FOR REASONS BEYOND THE CONTROL

OF THE CONTRACTOR SHALL BE REPLACED IN KIND WHEN ORDERED BY

THE ENGINEER. REPLACEMENT DRUMS SHALL BE NEW.

PAYMENT FOR THE NEW DRUMS SHALL BE MADE AT THE CONTRACT PRICE

PER EACH FOR ITEM 614, REPLACEMENT DRUM, AND SHALL INCLUDE THE

COST OF REMOVING AND DISPOSING OF THE DAMAGED DRUM AND

PROVIDING AND MAINTAINING THE REPLACEMENT DRUM IN ACCORDANCE WITH THE CONTRACT REQUIREMENTS FOR THE ORIGINAL DRUM.

ITEM 614, REPLACEMENT DRUM

LOCATION 1:    25 EACH

APPROVED MAINTENANCE OF TRAFFIC (MOT) POLICY EXCEPTION(S)

PORTIONS OF THE MOT PLANS AS DESCRIBED BELOW HAVE APPROVED MOT EXCEPTION(S) PER TRAFFIC MANAGEMENT IN WORK ZONES POLICY (21-008(P)) AND STANDARD PROCEDURE (123-001(SP)).

APPROVED MOT EXCEPTION(S) INCLUDE: LANE CLOSURES ON GUE-70 EASTBOUND AND WESTBOUND WITHIN THE PROJECT LIMTIS WILL BE PERMITTED FROM 6PM SUNDAY TO 10AM THURSDAY. THE LANE CLOSURES MAY ONLY TAKE PLACE BETWEEN MAY 1ST 2026 TO AUGUST 1ST 2026. ONLY ONE LANE CLOSURE PER DIRECTION WILL BE PERMITTED.

WORK INCLUDES:

FULL DEPTH PAVEMENT/JOINT REPAIRS (SHEET 20)

MEDIAN U-TURN WIDENING (SHEET 17)

EXPANSION JOINT REPAIRS ON GUE-70-1275 & 1656 BRIDGES (SHEET 18)

ANY VIOLATIONS OUTSIDE THE APPROVED LANE CLOSURE WINDOW SHALL ADHERE TO THE LANE VALUE CONTRACT LISTED ON SHEET 5.

SUPPLEMENTAL ADVANCE WARNING SIGNS PER MT-95.50 SHALL BE INSTALLED FOR EACH LANE CLOSURE ALONG WITH PORTABLE CHANGEABLE MESSAGE SIGNS AS DESCRIBED ON SHEET 6.

A MAINTENANCE OF TRAFFIC MEETING SHALL BE HELD A MINIMUM OF SEVEN (7) CALENDAR DAYS PRIOR TO THE IMPLEMENTATION OF EACH APPROVED MOT EXCEPTION. THIS MEETING SHALL INCLUDE THE DISTRICT WORK ZONE TRAFFIC MANAGER JOSH OTWORTH AS WELL AS THE CONTRACTOR, WORKSITE TRAFFIC SUPERVISOR AND ANY SUBCONTRACTORS INVOLVED WITH TEMPORARY TRAFFIC CONTROL.

IN ADDITION TO ANY NOTIFICATIONS REQUIRED IN OTHER NOTES,THE CONTRACTOR SHALL NOTIFY THE PROJECT ENGINEER AT LEAST THREE (3) BUSINESS DAYS IN ADVANCE OF IMPLEMENTATION OF THE APPROVED MOT EXCEPTION(S) REFERENCED ABOVE SOTHAT THE PROJECT ENGINEER CAN SEND EMAIL NOTIFICATIONTO THE OFFICE OF ROADWAY ENGINEERING, STATEWIDE TMC,DWZTM AND SPECIAL HAULING PERMITS AT LEAST TWO (2) BUSINESSDAYS IN ADVANCE OF THE IMPLEMENTATION OF THE APPROVED

MOT EXCEPTION(S) REFERENCED ABOVE. REFERENCE "EXCEPTION REQUEST APPROVAL DATED 06/11/2025 FOR PID 122215 IN THE NOTIFICATION AND OTHER CORRESPONDENCE.

ANY CHANGES TO THE MOT THAT IMPACT THE PREVIOUSLY APPROVED MOT EXCEPTION(S) LISTED ABOVE SHALL BE APPROVED IN WRITING BY THE MOT EXCEPTION COMMITTEE (MOTEC). IN THE EVENT THAT SUCH CHANGES ARE PROPOSED, THE REQUEST SHALL BE COORDINATED THROUGH THE DISTRICT WORK ZONE TRAFFIC MANAGER (DWZTM) A MINIMUM OF 30 CALENDAR DAYS PRIOR TO THE DESIRED IMPLEMENTATION DATE. IF THE DISTRICT AGREES WITH THE PROPOSED CHANGES THE DWZTM SHALL SEEK APPROVAL FROM THE MOTEC. IN THE EVENT THE PROPOSED CHANGES ARE APPROVED IN WRITING, THE CLOSURES ARE STILL SUBJECT TO NOTIFICATION REQUIREMENTS WITHIN THIS NOTE PRIOR TO IMPLEMENTATION.