# SEQUENCE OF OPERATIONS

# IT IS THE INTENT OF THIS SEQUENCE OF OPERATIONS TO PROVIDE A WORK AREA FOR THE CONTRACTOR WHILE ALSO MAINTAINING TRAFFIC

# IN A MANNER WHICH IS SAFE FOR THE TRAVELING PUBLIC. IT MAY BE NECESSARY FOR THE CONTRACTOR TO ALTERNATE BETWEEN PHASES

# IN ORDER TO MEET WORK RESTRICTIONS FOUND IN ODOT'S "DROP-OFFS IN WORK ZONES" STANDARD DRAWING MT-101.90.

IF THE CONTRACTOR SO ELECTS, HE/SHE MAY SUBMIT ALTERNATE METHODS FOR THE MAINTENANCE OF TRAFFIC, PROVIDED THE INTENT

# OF THE ABOVE PROVISIONS ARE FOLLOWED AND NO ADDITIONAL INCONVENIENCE TO THE TRAVELING PUBLIC RESULTS THEREFROM. NO

# ALTERNATE PLAN SHALL BE PLACED INTO EFFECT UNTIL APPROVAL HAS BEEN GRANTED, IN WRITING, BY THE ENGINEER.

ALL WORK NOT SPECIFIED IN THE SEQUENCE OF OPERATIONS CAN BE COMPLETED ANYTIME DURING THE DURATION OF THE PROJECT AT

THE APPROVAL OF THE ENGINEER.

ALL TEMPORARY OR PERMANENT PAVEMENT MARKINGS SHALL BE IN PLACE BEFORE ANY PAVEMENT IS OPENED TO TRAFFIC

LANES CLOSED IN BOTH THE EASTBOUND AND WESTBOUND DIRECTION SHALL BE AT THE APPROVAL OF THE ENGINEER

PHASE 1:  
(1)  CLOSE outside LANE AND MAINTAIN TRAFFIC BY USE OF THE inside LANE

(2)  MILL/FILL RUMBLE STRIPS AND EXISTING EDGE LINE (4’ WIDE) ON outside SHOULDER WITH ITEM 441, INTERMEDIATE COURSE.

see quantity below, clean shoulder of debris IF NECESSAry

(3)  PERFORM LINEAR GRADING and seeding and mulching

PHASE 2:

(1)  PERFORM FULL DEPTH PAVEMENT/JOINT REPAIRS PER TYPICAL SECTIONS on sheet 10

(2)  perform widening of median u-turns on sheet 17

(3)  pERFORM PARTIAL DEPTH REPAIRS AT GUE-70-1275 L/R AND 1656 L/R BRIDGES on sheet 18

PHASE 3:  
(1)  CLOSE inside LANE AND MAINTAIN TRAFFIC BY USE OF THE outside LANE AND PAVED SHOULDER

(2)  PLANE inside LANE AND SHOULDER AT DEPTH DETAILED IN PLANS

(3)  IMMEDIATELY PLACE ITEM 442, ASPHALT CONCRETE SURFACE COURSE FOR inside LANE AND SHOULDER

PER TYPICAL SECTION ON THIS SHEET (USE PATCHING PLANED SURFACE AS NEEDED)

PHASE 4:  
(1)  CLOSE outside LANES AND MAINTAIN TRAFFIC BY USE OF THE inside LANE AND PAVED SHOULDER

(2)  PLANE outside LANES AND SHOULDER AT DEPTHS DETAILED IN PLANS

(3)  IMMEDIATELY PLACE ITEM 442, ASPHALT CONCRETE SURFACE COURSE FOR outside LANES AND SHOULDER

(RAMP AREAS WHERE APPLICABLE) PER TYPICAL SECTION ON THIS SHEET (USE PATCHING PLANED SURFACE AS NEEDED)

PHASE 5:  
(1)  INSTALL COMPACTED AGGREGATE, 2” deep joint sealer, RUMBLE STRIPS, PERMANENT PAVEMENT MARKINGS, AND

RAISED PAVEMENT MARKERS. OPEN ROADWAY TO UNRESTRICTED TRAFFIC

THE BELOW ITEMS SHALL BE USED TO MILL/FILL IN RUMBLE STRIPS FOR MAINTAINING TRAFFIC AS DESCRIBED IN PHASE 1 ABOVE.

THE FOLLOWING QUANTITIES HAVE BEEN CARRIED TO THE GENERAL SUMMARY.

ITEM 254, PAVEMENT PLANING, ASPHALT CONCRETE, 1.00”

LOCATION 1: (12.32-17.52) x 5280’ = 27,456 ft: (2(27,456' x 4’))/9 = 24,406 SQ.YD.

ITEM 441, ASPHALT CONCRETE INTERMEDIATE COURSE, TYPE 1, (449)

LOCATION 1: (12.32-17.52) x 5280’ = 27,456 ft: (2(27,456' x 4' x (1.00"/12)))/27 = 678 CU.YD.