## Sheet1
LANE VALUE CONTRACT TABLE
DESCRIPTION OF CRITICAL LANE/RAMP TO BE MAINTAINED | RESTRICTED TIME PERIOD | TIME UNIT | DISINCENTIVE $ PER TIME UNIT
IR-275 | SEE PLCS | 1 MINUTE PERIOD | 340 | DESCRIPTION OR LOCATION OF CRITICAL WORK | COMPLETION DATE | TIME PERIOD | DISINCENTIVE $ PER TIME UNIT
ALL LANES OPEN TO TRAFFIC
ALL RAMPS OPEN TO TRAFFIC | 5 AM TO 10 PM | 1 MINUTE PERIOD | 230 | I-275 IN EITHER DIRECTION: WORK STARTED IN 2025 SHALL BE COMPLETED IN ENTIRETY OF THAT DIRECTION INCLUDING RPMs | 2025-10-01 | DAY | 3500