## Sheet 1
PERMITTED LANE CLOSURE TIMES AND UNAUTHORIZED LANE USE TABLE
LOCATION |  | DIRECTION | EX. NO. OF THRU LANES | 1 LANE CLOSED |  | 2 LANES CLOSED |  | 15 MINUTE SHORT DURATION COMPLETE CLOSURES | COMPLETE CLOSURE | TIME UNIT | DISINCENTIVE PER LANE PER TIME UNIT
|  |  |  | WEEKDAY | WEEKEND | WEEKDAY | WEEKEND
IR-75 |  | BOTH | 3 | 8 PM - 6 AM | 7 PM - 6 AM | 11 PM - 5 AM | 10 PM - 6 AM | 12 AM - 4 AM | MOTPE 1A/B: 11 PM - 5 AM | 1 MINUTE | 540
SR-562 |  | BOTH | 2 | 8 PM - 6 AM | 7 PM - 7 AM | NOT APPLICABLE |  | 11 PM - 5 AM | MOTPE 2A/B: 11 PM - 5 AM | 1 MINUTE | 305
RAMPS |  | BOTH |  | NOT APPLICABLE |  | NOT APPLICABLE |  | NOT ALLOWED | 10 PM - 5 AM | 1 MINUTE | 540
Prosser Ave |  | BOTH | 1 | ANYTIME; MAINTAIN 1 LANE OF 2-WAY TRAFFIC |  | NOT APPLICABLE |  | ANYTIME | SEE 11.2.4 | 1 MINUTE | 40
NOTES:
1 | NO CLOSURES 2 HOURS BEFORE TO 1 HOUR AFTER THE START TIME OF EVENTS AT GREAT AMERICAN BALL PARK, PAUL BROWN STADIUM, OR HERITAGE BANK ARENA. THIS RESTRICTION ALSO APPLIES TO ANY OTHER LOCAL VENUE REACHING AN ATTEDANCE OF 20,000+.
2 | NO CLOSURES FROM 30 MINUTES BEFORE THE SCHEDULED FINISH TIME TO 2 HOURS AFTER EVENTS AT GREAT AMERICAN BALL PARK, PAUL BROWN STADIUM, OR HERITAGE BANK ARENA. THIS RESTRICTION ALSO APPLIES TO ANY OTHER LOCAL VENUE REACHING AN ATTEDANCE OF 20,000+.
3 | NO SHORT TERM SHOULDER CLOSURES BETWEEN THE HOURS OF 6 AM TO 9 AM AND 3 PM TO 7 PM MONDAY THROUGH FRIDAY.
4 | RAMPS ARE PERMITTED TO BE CLOSED OVERNIGHT FOR MOT TRAFFIC SWITCHES ONLY. ONLY ONE RAMP IS PERMITTED TO BE CLOSED AT A TIME.
5 | FOLLOW HOLIDAY RESTRICTIONS PER TEM 642-6.