## Utility Log
O.U.P.S 1-800-362-2764 |  | COMPANY ID: Euthenics, Inc. |  |  |  |  | PROJECT: HOL-39-00.25 |  | PID: 115928 | Last Updated By: BPS | 2024-05-31 | 10:30
PM: Brandon Sopko, P.E. |  | OUPS TICKET 01/9/23 Design and Markings: A300903771-00A |  |  |  |  | Location- S.R. 39 structure over Small Run Holmes County, OH |  |  | Additional Notes:
Utility Company | Utilty | Contact | Project Notification Notice (Emailed by ODOT or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Utility Location | Sent Stage 1 Plans | Received Comments | Sent Stage 2 Plans | Received Comments | Sent Stage 3 Plans | Received Comments | Remarks | UG or OH
Name and Address | Type | Name
6" watermain - S.R.39, N side of roadway through existing structure
Village of Loudonville | Water | Garret Dewitt |  | Sent OUPS | Received |  | 2023-06-27 | Sent Stage 1 Plans
156 North Water Street |  | g.dewitt@loudonville-oh.us |  | Ticket on | plans by
P.O. Box 150 |  | 419-994-3214 |  | 2023-01-11 | email, |  | 2023-09-18 | Re-sent Stage 1 Plans.
Loudonville, Ohio 44842 |  |  |  |  | date unknown
[7 empty] | 2023-10-25 | Called Mr Dewitt to get an update on the utilities since there has been no email response. Left a voicemail, currently awaiting call back.
[7 empty] | 2023-10-31 | Received an email from Mr. Dewitt stating "The location of the lines on the prints appear to be accurate as shown."
8" sanitary main - crosses south of existing roadway. Will require relocation
Village of Loudonville | Sanitary | Garret Dewitt |  | Sent OUPS |  |  | 2023-06-27 | Sent Stage 1 Plans
156 North Water Street | Storm | g.dewitt@loudonville-oh.us |  | Ticket on
P.O. Box 150 |  | 419-994-3214 |  | 2023-01-11 |  |  | 2023-09-18 | Re-sent Stage 1 Plans.
Loudonville, Ohio 44842
[7 empty] | 2023-10-25 | Called Mr Dewitt to get an update on the utilities since there has been no email response. Left a voicemail, currently awaiting call back.
[7 empty] | 2023-10-31 | Received an email from Mr. Dewitt stating "The location of the lines on the prints appear to be accurate as shown."
Underground lines along the N side of S.R. 39, will conflict with proposed structure
Ohio Edison | Electric | Amy Conley |  | Sent OUPS | Received |  | 2023-06-27 | Sent Stage 1 Plans to John Zassick. He sent Amy Conley's information | 2024-05-31 | Sent Stage 2 Plans and authorization letter
6896 Miller Road |  | conleya@firstenergycorp.com |  | Ticket on | marking confirmation
Brecksville, OH 44141 |  |  |  | 2023-01-11 | email on |  | 2023-09-18 | Re-sent plans to John Zassick. He again pointed us to Mrs. Conley. Plans were sent to her, along with our apology for the mix up.
|  | Mike Beck |  |  | 2023-01-11
beckm@firstenergycorp.com
730 South Ave |  | 330-740-7704
Youngstown, OH 44502 | [6 empty] | 2023-09-22 | Received an update from ODOT District 11. They said that "The responses received with Stage 1 from Ohio Edison/ First Energy should include the location of these facilities." We have not yet received stage 1 responses.
[7 empty] | 2023-10-25 | Reached out to Mr. Mike Beck, whom we have worked with before and whose information was provided to us by the district. As we do not have a phone number for Mrs. Conley and she has been unresponsive, we are hoping he can provide the number.
4" plastic line terminates prior to project limits, no conflict anticipated
Dominion Energy Ohio (DEO) | Gas | W. Michael North |  | Sent OUPS | Received |  | 2023-06-27 | Sent Stage 1 Plans | 2024-05-17 | ODOT District 11 stated that we can remove Dominion Energy Ohio from the
320 Springside Drive, Suite 320 |  | w.michael.north@dominionenergy.com |  | Ticket on | plans by |  |  |  |  | Stage 2 Plans.
Akron, OH 44333 |  | 330-664-2575 |  | 2023-01-09 | email on |  | 2023-07-13 | Mr. North from Dominion reviewed the plans and believes there is no conflict. Official No Conflict Letter received and logged.
Attn: 2nd Floor Relocation Design |  |  |  |  | 2023-01-11
Ph: 330-664-2409 |  | Submit plans to:
Fax: 888-504-0126 |  | relocation@dominionenergy.com |  |  |  |  | 2023-10-25 | Left a voicemail with Mr. North asking if it would be approporaite to list him as the official contact on the plans. Awaiting callback.
[7 empty] | 2023-10-26 | Spoke with Mr North, he gave us the information for Kyle McCall, the proper contact.
Kyle McCall
|  | kyle.j.mccall@dominionenergy.com |  |  |  |  | 2023-11-21 | Emailed Mr. North to verify that all Dominion facilities are clear. He confirmed this, and informed us that the valve at the end is actually a test point and can be adjusted easily with the proposd grade.
330-801-8299
TBD - Overhead and underground telecom lines at project site
Frontier Communications | Communications | Giovanni Loreti |  | Sent OUPS | Rcieved Marking |  | 2023-06-27 | Sent Stage 1 Plans | 2024-05-31 | Sent Stage 2 Plans and authorization letter
1534 State Route 511 |  | giovanni.loreti@ftr.com |  | Ticket on | confirmation
Ashland, Ohio 44805 |  | 419-282-6552 |  | 2023-01-11 | email on |  | 2023-09-19 | Re-sent stage 1 plans to Mr. Loretti. He responded, bringing Chris Avery into the conversation. Chris is covering the area for Frontier, awaiting further response.
2023-01-11
Chris Avery
|  | ira.avery@ftr.com |  |  |  |  | 2023-10-25 | Called Chris's listed number but was given Mr Loretti's desk. Left a voicemail explaining the situation.
419-282-6551
TBD - Overhead and underground telecom lines at project site
Charter (Spectrum) | Communications | Jason Sprague |  |  |  |  | 2023-06-27 | Sent Stage 1 Plans | 2024-05-31 | Sent Stage 2 Plans and authorization letter
2904 State Road |  | 216-575-8016 x216-555-5740
Ashtabula, OH 44004 |  | 440-361-0024 (cell) |  |  |  |  | 2023-09-18 | Re-sent Stage 1 Plans. Mr. Sprague responded, noting that the project is outside his area and adding other area supervisors, Ron Ickes and Sean Beavis to the conversation. ODOT Stage 1 comments suggest that Ron Ickes is the contact for the area, listing him on the plans for now. Awaiting response.
jason.sprague@charter.com
Ron Ickes
5520 Whipple Ave NW |  | ron.ickes@charter.com
North Canton, OH 44720 |  | 330-494-9200 |  |  |  |  | 2023-10-25 | Called the number provided for Mr Ickes. After being re-directed, and operator was able to provide me a different number that was no longer in service. Reached out via email per BPS. Awaiting response.
Corey Richardson
|  | corey.richardson@charter.com |  |  |  |  | 2023-10-26 | Mr Ickes said to send him the plans and he would have his coordinator field check. Sent as requested. Spoke on the phone with Corey Richardson, who was currently doing the field review and will get us his thoughts as soon as he has them. He will be the contact going forward.
330-760-9909
[7 empty] | 2023-11-21 | Emailed Mr. Richardson requesting his input on the existing telecom lines and his initial thoughts on relocating within right of way, if it comes to that.