## Item 514 - Field Painting
Item 513 - Structural Steel, Misc.: Intermediate Stiffener | [6 empty] | = | 26 | Each
Total along Girder A = |  | 10
Total along Girder B = |  | 8
Total along Girder C = |  | 8
| Total = | 26
Item 513 - Structural Steel, Misc.: Horizontal Cross Frame Members | [6 empty] | = | 1 | Each
Total between Girder A & B = |  |  | 0
Total between Girder B & C = |  |  | 1
|  | Total = | 1
Item 513 - Structural Steel, Misc.: 3" Diameter Core Sample | [6 empty] | = | 1 | Each
Core Sample from the Web of Girder B = |  |  |  | 1
|  |  | Total = | 1
Item 514 - Field Painting of Structural Steel | [6 empty] | = | 1030.4889 | ft2
Girder
Web:
Length = | 48 | inches
Thickness = | 0.375 | inches
Flange: |  |  |  |  | Total Girder Painting = |  |  | 763.125 | ft2
Width = | 14 | inches
Thickness = | 0.75 | inches
Girder Length = | 22 | feet
Girder Perimeter = |  | 138.75 | inches
|  | 11.5625 | feet
One Girder Section = |  | 254.375 | ft2
Stiffener
Height = | 4 | feet
Width = | 5 | inches
Thickness = | 0.3125 | inches
Stiffener Perimeter = |  | 10.3125 | inches
|  | 0.85938 | feet |  | Total Stiffener Painting = |  |  | 206.25 | ft2
One Stiffener Section = |  | 3.4375 | ft2
*Painting New and Old Stiffeners*
Total along Girder A = |  | 20
Total along Girder B = |  | 20
Total along Girder C = |  | 20
| Total = | 60
Cross Frame
Height = | 3 | inches
Width = | 3 | inches
Web Thickness = | 0.3125 | inches
*Lengths pulled from Detail*
Length = | 6.8879 | feet
| 6.8879 | feet |  |  | Total Cross Frame Painting = |  |  | 61.1139 | ft2
| 6.5955 | feet
Cross Frame Perimeter = |  | 12 | inches
|  | 1 | foot
One Cross Frame Section = |  |  | 20.3713 | ft2
Item 514 - Grinding Fins, Tears, Slivers on Existing Structural Steel | [6 empty] | = | 2 | MNHR
Man hours for Grinding = |  | 2
| Total = | 2
Item 514 - Final Inspection Repair | [6 empty] | = | 1 | Each
Final Inspection = |  | 1
| Total = | 1
Item 519 - Patching Concrete Structure, As Per Plan | [6 empty] | = | 15 | ft2
Patch by Girder A
Width = | 2.5 | feet
Height = | 2.5 | feet
[6 empty] | Patch by Girder A = |  | 7 | ft2
Patch by Girder C
Width = | 3 | feet
Height = | 1.5 | feet
[6 empty] | Patch by Girder C = |  | 5 | ft2
|  | *Total Concrete Patching Quantity |  |  |  | Total Concrete Patch |  | 15 | ft2
has been increased by 25%