## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | MOT-WOODMAN DR RECONSTRUCTION (PID: 115003) | [5 empty] | Last Updated By: | DMS
PM: | mjt |  | OUPS Ticket: | B121501915-00B | [5 empty] | On: | 2024-07-08
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
ATT - Ohio |  | Howard Laudermilk |  |  | 2022-07-25 | 7-25-22: Auto response from Howard stating he is out of office | 2023-02-20 |  | 2024-02-14
3233 Woodman Drive |  | HL1596@att.com |  |  |  | until August 1st.
Dayton, OH 45420 | [5 empty] | 7-22-22: Howard said no indication of att local plans around. Does
|  | Alan Stutes |  |  |  | not see any conflicts due to no faciliites in area.
AS1634@att.com
ATT - Transmission |  | Chad Harkness |  |  |  | 7-27-22: Dan stating the line down on the trail is an ATT
155 Commerce Park Drive |  | chad.harkness@mcgfiber.com |  |  |  | Transmission fiber. Provided a faciliites map. No overhead
Suite #1 |  | Dan Gardner |  |  |  | lines in the area. No conflicts anticipated.
Westerville, OH 43082 |  | dan.gardner@mcgfiber.com
Dayton City Water and Sewer |  | Emad Toufils |  |  | 2022-07-25 |  | 2023-02-20 |  | 2024-02-14
320 W. Monument Avenue |  | emad.toufils@daytonohio.gov
Dayton, OH 45402
AES Ohio (Formerly DPL) |  | William Gourley |  |  | 2022-07-25 | 2022-07-26: bill ward provides staking sheet of electric and | 2023-02-20 | 2023-02-20: william gourley auto response | 2024-02-14
1900 Dryden Road |  | william.gourley@aes.com |  |  |  | description of options on how to provide power services |  | 2023-02-23: bill ward asking for voltage requirements for lighting.
Distribution Engineering Area 136 | [7 empty] | 2023-02-27: bill ward provided a service plan for the project. AES ohio power service
Dayton, OH 45439 |  | William Ward
william.ward@aes.com
Lumen (Marked as Level 3) |  | relocation@lumen.com |  |  | 2022-07-25 | 2022-07-25: leslie said she received plans, they are under review, | 2023-02-20 | 2023-02-20: leslie dingman saying recipt, providing map, COEC believe no conflicts | 2024-02-14
9490 Meridian Way | [5 empty] | and provided facilities maps of lumen. Appears to be no conficts |  | 2023-02-20: phone call from lumen and both agreement no conflicts. Only line
West Chester, OH 45069 |  | Leslie Dingman |  |  |  | and line under bridge by trail is a lumen facility. |  | is underground along creekside trail (fiber optic main)
|  | leslie.dingman@lumen.com | [5 empty] | 2023-02-21: lumen stating no conflicts anticipated in email but a rep from lumen
should be on site when construction begins
Centerpoint Energy (Formerly Vectren) |  | publicproject@centerpointenergy.com |  |  | 2022-07-25 | 2022-08-08: auto response listing Jeff Pike as distribution engineer | 2023-02-20 | 2023-02-20: Jeff Pike saying no change in their status, still no conflicts. | 2024-02-14 | 2-14-23: jeff pike responded that he agrees no conflicts are anticipated still
2345 E. Main Street | [5 empty] | and Jeff Donnely as transmission engineer on site
Danville, IN 46122 |  | Jeff Pike
|  | jeffrey.t.pike@centerpointenergy.com |  |  |  | 2022-08-09: Dan Sarkis saying no transmission on project.
|  | Jeff Donnelly |  |  |  | 2022-08-11: Jeff Pike providing the utility basemaps for the
|  | jeff.donnelly@centerpointenergy.com |  |  |  | distribution lines. Doesn’t see a conflict.
Charter/Spectrum |  | DL-Southern-Ohio-Outside-Plant@charter.com |  |  | 2022-07-25 | 7-25-22: Erik Granger kickback saying email does not exist. | 2023-02-20 | 1-Tara is having her crew locate the missing Fiber line and we may be in conflict with this Utility | 2024-02-14
3691 Turner Road | [7 empty] | 6-Tara has no concerns with the layout and we adjusted the curb location, which eliminates any potential redesign of the curb ramps.
Dayton, OH 45415 |  | Erik Granger
erik.granger@charter.com
|  | Tara Williamson |  |  | 2023-01-12 | 1-Tara is having her crew locate the missing Fiber line and we may be in conflict with this Utility
| 937-396-8374 | Tara.Williamson@charter.com |  |  |  | 6-Tara has no concerns with the layout and we adjusted the curb location, which eliminates any potential redesign of the curb ramps.
Montgomery County Engineering |  | Eric Moody |  |  | 2022-07-25 | 7-25-22: eric moody email saying address no longer exist | 2023-02-20 | 2023-02-20: Gary Shoup asking for full set of plans. Plans sent to county and David | 2024-02-08 | 2-8-24: sent gary shoup updated plan sheets and asked for comments or approval
451 W. Third Street |  | moodye@mcohio.org | [5 empty] | Shileds from the county would be reviewing.
10th Floor | [5 empty] | 8-25-22: Ed Schlaack responded with comments, ownership |  |  |  | 2-8-24: sent gary and david shields a link to the full set of Stage 3 plans
Dayton, OH 45422 |  | Gary Shoup |  |  |  | of lines, and adjustment of manhole regulations. Also concerned
|  | shoupg@mcohio.org |  |  |  | about light pole foundation depth near their 21" sanitary by |  |  |  | 2-15-24: gary sent 1 comment back, minimal update
Eastman Avenue. Provided marked up plans
Paul Gruner
grunerp@mcohio.org
Ed Schlaack
SchlaackE@mcohio.org
David Shields
ShieldsD@mcohio.org
Greater Dayton RTA |  | Daniel Bloomingdale |  |  | 2022-07-25 | 7-25-22: Dan auto response email saying out of office until 8/1 | 2023-02-20 | 2023-02-20 - sending a separate mot plan to dan bloomingdale | 2024-02-08 | 2-8-24: sent bloomingdale updated MOT plans and Traffic Sheets for final construction
4 S. Main Street |  | dbloomingdale@greaterdaytonrta.org |  |  |  | 8-16-22: Sending proposed staging in email to Dan |  |  |  | siginage and striping. Asking for comments and/or approval.
Dayton, OH 45402 | [5 empty] | 8-25-22: resending email and clarifying what we need rom him
|  | Nathan Owens |  |  |  | 9-2-22: talking with dan on phone and him saying he will get what |  |  |  | 2-8-24: auto response saying nathan owens is the updated contact for the project
|  | nowens@greaterdaytonrta.org |  |  |  | we need from him the following week
[6 empty] | 9-9-22: re emailed dan looking for a written response |  |  |  | 2-8-24: sent nathan owens an update email asking for comments or approval.
2-14-24: nate owens stating he will look at the plans and be in touch
7-8-24: sending nate owens final plans and asking for acceptance

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary