SEQUENCE OF CONSTRUCTION

PHASE 1 – BRIDGE CONSTRUCTION AND SR-91 CLOSED AND DETOURED

THE CONTRACTOR IS PERMITTED A 16 CALENDAR DAY CLOSURE OF SR 91 TO CONSTRUCT THE SUM-91-14.54 BRIDGE. SR 91 WILL BE CLOSED FROM JUST NORTH OF THE RAILROAD ACCESS DRIVEWAY TO JUST SOUTH OF THE NORTH YOURS TRULY DRIVEWAY. THE FOLLOWING DRIVEWAYS WILL BE CLOSED:

SOUTH YOURS TRULY DRIVEWAY – 36 S. MAIN ST.

EVAPORATOR WORKS DRIVEWAY – 51 S. MAIN ST.

SOUTH PNC DRIVEWAY – 37 S. MAIN ST.

ACCESS TO ALL OF THESE PROPERTIES WILL BE MAINTAINED AT ALL TIMES USING THEIR OTHER DRIVEWAYS WHICH WILL REMAIN OPEN.

THE SOUTH YOURS TRULY DRIVEWAY WILL BE RECONSTRUCTED DURING THIS PHASE.

SOUTHBOUND ATTERBURY BLVD. WILL BE CLOSED AT SR 303 AND DETOURED AS SHOWN IN THE PLANS. ACCESS TO ALL OF THESE PROPERTIES WILL BE MAINTAINED AT ALL TIMES. THIS CLOSURE AND DETOUR IS ALSO LIMITED TO 16 DAYS.

THE RELOCATED WEST CURB, CATCH BASINS, AND MULTI-USE PATH SHALL BE CONSTRUCTED FROM STA. 767+23.93 TO STA. 769+29.

OTHER WORK MAY BE PERFORMED WITHIN THE 16 DAY CLOSURE.

SEE THE STRUCTURE GENERAL NOTES FOR A MORE DETAILED DESCRIPTION OF THE BRIDGE WORK.

PHASE 2 – WEST CURB AND MULTI-USE PATH CONSTRUCTION

THE WORK IN THIS PHASE INCLUDES THE REMAINDER OF THE CONSTRUCTION OF THE RELOCATED WEST CURB, CATCH BASINS, AND MULTI-USE PATH.

THE TWO WAY LEFT TURN LANE (TWLTL) WILL BE CLOSED DURING THIS PHASE AND TRAFFIC WILL BE SHIFTED EAST TO ALLOW FOR A CONSTRUCTION ZONE ON THE WEST SIDE.

PHASE 3 – RESURFACING

THE WORK IN THE PHASE INCLUDES RESURFACING AND RESTRIPING OF SR-91 BETWEEN THE LIMITS OF THE WEST CURB RELOCATION.

Should the contractor exceed any of the durations in any of the phases stated in the above sequence of construction, the contractor shall be assessed a disincentive in the amount of $10,000 per day or portion thereof.

Item 614, Maintaining Traffic

ThE PURPOSE OF THIS PROJECT IS TO REPLACE THE WESTERN PORTION OF THE SR-91 BRIDGE OVER A TRIBUTARY OF BRANDYWINE CREEK. THIS PROJECT ALSO PROVIDES FOR A 8’ OR 10’ MULTI-USE PATH ON THE WEST SIDE THAT REQUIRES NEW CURB, CATCH BASINS AND RESURFACING.

THIS ITEM SHALL CONSIST OF MAINTENANCE OF TRAFFIC ON EXISTING ROADWAYS AND RAMPS IN ACCORDANCE WITH THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES FOR STREETS AND HIGHWAYS, CURRENT EDITION, LATEST REVISION, THE SPECIFICATIONS AND THE FOLLOWING:

1. when traffic is not detoured: a minimum of one Ten foot lane in each direction shall be maintained on the existing and completed pavement during construction of the work.

2. THE CONTRACTOR SHALL INFORM THE DISTRICT OFFICE (330) 786-2208 AND THE CITY OF HUDSON (330) 342-1770 EIGHTEEN (18) DAYS PRIOR TO THE BEGINNING OF WORK.

3. TRUCK MOUNTED ATTENUATORS [TMA'S] SHALL BE USED AS SHOWN IN THE STANDARD CONSTRUCTION DRAWINGS.

4. UNDER NO CIRCUMSTANCES SHALL THE CONTRACTOR BE PERMITTED TO HAVE SUCCESSIVE WORK ZONES UNLESS THE DISTANCE BETWEEN THE DRUMS, BARRICADES OR CONES EXCEEDS ONE [1] MILE.

5. FOR ROUTES NOT ON THE PERMITTED LANE CLOSURE CHART, ONLY DURING OFF-PEAK PERIODS (ie ANY PERIOD OTHER THAN 6-8AM AND 3-6PM) SHALL THE CONTRACTOR INSTALL AND SUBSEQUENTLY RESET ALL TRAFFIC CONTROL NECESSARY FOR THE WORK ZONE FOR EACH CONSTRUCTION PHASE.

6. IN ADDITION TO THE REQUIREMENTS OF 614.11 WORK ZONE PAVEMENT MARKINGS, AT THE END OF EACH DAY OF WORK, THE CONTRACTOR SHALL REPLACE (WITH WORK ZONE MARKINGS) ALL LANE, CENTER, STOP OR CHANNELIZING LINES THAT WERE REMOVED OR COVERED DURING THE PAVEMENT REMOVAL OR PLACEMENT OPERATIONS. QUANTITIES FOR SUCH PLACEMENT ARE CARRIED AS PART OF THE ITEMS LISTED UNDER 614 WORK ZONE PAVEMENT MARKINGS.

7. A QUANTITY OF 10 CU. YDS. OF ITEM 614 ASPHALT CONCRETE FOR MAINTAINING TRAFFIC SHALL BE PROVIDED FOR USE IN MAINTAINING PAVEMENT, SHOULDERS AND OTHER LOCATIONS AS DIRECTED BY THE ENGINEER.

8. PRIOR TO OPENING TO TRAFFIC EACH LANE SHALL BE IN A SAFE, PASSABLE CONDITION. ALL TRANSVERSE JOINTS SHALL EXTEND ACROSS THE FULL LANE AND

SHOULDER WIDTH AND EACH LANE SHALL BE FREE FROM UNEVEN LONGITUDINAL JOINTS. THE CONTRACTOR SHALL PROVIDE ASPHALT WEDGES FOR TRANSVERSE JOINTS WHEREVER THERE ARE PAVEMENT ELEVATION DIFFERENCES.

9. THE CONTRACTOR SHALL PLACE THE SIGNS: W8-1 [BUMP] PER OMUTCD 2C.28; W8-11 [UNEVEN LANES] PER OMUCTD 6F.45; AND W6-3 [TWO-WAY TRAFFIC] PER OMUTCD 6F.32. PAYMENT FOR THESE SIGNS SHALL BE INCIDENTAL TO THE LUMP SUM ITEM 614-MAINTAINING TRAFFIC.

THE FOLLOWING QUANTITIES SHALL BE USED FOR THE MAINTENANCE OF TRAFFIC ON THIS PROJECT:

614, WORK ZONE CENTER LINE, CLASS III, 642 PAINT 0.16 MILE

10. Length and duration of lane closures and restrictions shall be at the approval of the Engineer. It is the intent to minimize the impact to the traveling public. Lane closures or restrictions over segments of the project in which no work is anticipated within a reasonable time frame, as determined by the Engineer, shall not be permitted. The level of utilization of maintenance of traffic devices shall be commensurate with the work in progress.

11. The Contractor shall provide, erect and maintain signs and sign supports, as detailed in the Ohio Manual of Uniform Traffic Control Devices, and Type III barricades of the type and location AS SHOWN IN THE PLANS.

All work and traffic control devices shall be in accordance with C&MS 614 and other applicable portions of the specifications, as well as the Ohio Manual of Uniform Traffic Control Devices. Payment for all labor, equipment and materials shall be included in the lump sum contract price for Item 614, Maintaining Traffic, unless separately itemized in the plan.

Item 614, Maintaining Traffic (TIME LIMITATION ON A DETOUR)

A minimum of one lane of traffic in each direction ON SR 91 shall be maintained at all times, except for a period not to exceed 16 consecutive calendar days, when through traffic may be detoured as shown on sheet 13 in order to install the new concrete box sections and restore pavement to maintain traffic as shown in phase 2. ATTERBURY BLVD. traffic shall be maintained at all times, except for a period not to exceed 16 consecutive calendar days, when SOUTHBOUND ATTERBURY BLVD. traffic may be detoured as shown on sheet 19. a disincentive in the amount of $5000 per day for each calendar day the roadway remains closed to traffic beyond the specified limit.

Item 614, Maintaining Traffic (Lanes Open During Holidays or Special Events)

PHASE 1 CONSTRUCTION IS NOT TO TAKE PLACE UNTIL AFTER JULY 8, 2024.

PHASE 2 AND 3 CONSTRUCTION SHALL BE COMPLETED BY AUGUST 20, 2024.

No work shall be performed and all existing lanes shall be open to traffic during the following designated holidays or events:

Christmas 	Fourth of July

New Year’s 	Labor Day

Memorial Day 	Thanksgiving

easter

one DAY PRIOR TO AND DURING SPECIAL EVENTS TWO LANES (ONE IN EACH DIRECTION) SHALL REMAIN OPEN, ALL DRIVEWAYS SHALL BE FULLY OPEN, THE SITE CLEAN AND SECURED, AND PEDESTRIAN ACCESS SHALL BE MADE AVAILABLE.

Should the Contractor fail to meet any of these requirements, the Contractor shall be assessed

a disincentive OF $10,000/DAY per the lane value contract (PN 127).

| DESCRIPTION OF CRITICAL LANE TO BE MAINTAINED | RESTRICTED TIME PERIOD | TIME UNIT | DISINCENTIVE $ PER TIME UNIT |
| --- | --- | --- | --- |
| SUM-91 NB AND SB | AFTER 16 DAY CLOSURE | EACH DAY | $10,000 |
| ATTERBURY BLVD. | AFTER 16 DAY CLOSURE | EACH DAY | $10,000 |

Interim start and completion date OF SUM-91-14.49 Replacement

SR-91 shall not be closed completely to traffic prior to July 8, 2024 to complete the replacement of SUM-91-14.49. All work associated with the replacement SUM-91-14.54 shall be completed by August 20, 2024. Should the contractor fail to meet the interim completion date of August 20, 2024 a disincentive in the amount of $10,000 per day or portion thereof shall be assessed.

Item 614, Maintaining Traffic (NOTICE OF CLOSURE SIGN)

Notice of Closure signs (W20-H13) shall be erected by the Contractor prior to the scheduled road closure in accordance with the Notice of Closure Time Table below.

The signs shall be erected on the right-hand side Of the road facing traffic. They shall be placed so as not to interfere with the visibility of any other traffic control signs. On roadways,

they should be erected at or near the point of closure.

Notice of Closure Sign Time Table

Item Duration of Closure Sign Displayed to Public

ROAD ≥ 2 weeks 14 calendar days prior to closure

The sign shall display the date of the closure in MMM-DD format and the number of days of the closure. The last line of the W20-H13 sign lists a phone number which a motorist may call for additional information. This is to be a specific office within the District rather than the general switchboard number.

DETOUR NOTIFICATION

THE CONTRACTOR SHALL ADVISE THE ODOT DISTRICT OFFICE (330-786-3148) AND CITY EIGHTEEN (18) DAYS IN ADVANCE OF WHEN THE DETOUR ROUTE SHOULD BE IN EFFECT. ALL WORK ZONE DEVICES REQUIRED SHALL BE FURNISHED, ERECTED, MAINTAINED, AND SUBSEQUENTLY REMOVED BY THE CONTRACTOR.

THE CONTRACTOR SHALL NOTIFY THE FOLLOWING AGENCIES AT LEAST SEVEN WORKING DAYS PRIOR TO THE IMPLEMENTATION OF THE DETOUR:

• ALL PUBLIC AND PRIVATE SCHOOLS OPERATING IN THE CITY OF HUDSON, AND THEIR TRANSPORTATION DEPARTMENTS.

• UNITED STATES POST OFFICE, (800) 275-8777

• HUDSON FIRE DEPARTMENTS, (330) 342-1860

• HUDSON EMS DEPARTMENTS, (330) 342-1860

• HUDSON POLICE DEPARTMENT, (330) 342-1800

• REPUBLIC SERVICES, (330) 830-9050

• AA SANITATION, (330) 650-4105

• KIMBLE COMPANIES, (800) 201-0005

• WASTE MANAGEMENT, (800) 343-6047

IN ADDITION TO THESE REQUIREMENTS, THE CONTRACTOR SHALL PROVIDE A WRITTEN NOTICE TO THE LOCAL HUDSON NEWSPAPER DESCRIBING THE DETOUR ROUTE(S) AND EXPECTED TIMES OF CLOSURE. THIS NOTICE MUST BE PUBLISHED IN THE NEWSPAPER SEVEN DAYS PRIOR TO THE IMPLEMENTATION OF THE DETOUR. THE NEWSPAPER MUST BE GIVEN SUFFICIENT ADVANCED NOTICE TO MEET THIS DEADLINE.

PAYMENT FOR ALL WORK ASSOCIATED WITH THE DETOUR SHALL BE INCLUDED UNDER THE LUMP SUM BID FOR ITEM 614, DETOUR SIGNING.

TRAFFIC CONTROL INSPECTOR

THE CONTRACTOR SHALL DESIGNATE AN INDIVIDUAL OTHER THAN THE SUPERINTENDENT AND SUBJECT TO THE APPROVAL OF THE ENGINEER, TO CONTINUOUSLY   INSPECT ALL TRAFFIC CONTROL DEVICES WHENEVER CONSTRUCTION WORK IS BEING PERFORMED WITHIN THE WORK LIMITS OF THE PROJECT. THE DESIGNATED INDIVIDUAL SHALL ALSO INSPECT ALL TRAFFIC DEVICES

AT THE BEGINNING AND AT THE END OF EACH WORK DAY. THE DESIGNATED INDIVIDUAL OR A QUALIFIED REPRESENTATIVE SHALL ALSO BE AVAILABLE ON AN

AROUND THE CLOCK BASIS TO REPAIR AND/OR REPLACE DAMAGED OR MISSING TRAFFIC CONTROL DEVICES. THESE INDIVIDUALS SHALL BE EQUIPPED WITH CELLULAR PHONES AND THEIR NAMES AND PHONE NUMBERS SHALL BE GIVEN TO THE PROJECT ENGINEER AT THE PRE-CONSTRUCTION MEETING. THE DESIGNATED INDIVIDUAL MAY HAVE OTHER CONSTRUCTION RELATED DUTIES AS LONG AS IMMEDIATE ATTENTION IS GIVEN TO TRAFFIC CONTROL. PAYMENT FOR THE SERVICES OF THE TRAFFIC CONTROL INSPECTOR SHALL BE INCLUDED IN THE LUMP SUM PRICE BID FOR ITEM 614 MAINTAINING TRAFFIC.

ITEM 614 - LAW ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE DURING CONSTRUCTION OPERATIONS

USE OF LAW ENFORCEMENT OFFICERS (LEOS) BY CONTRACTORS OTHER THAN THE USES SPECIFIED BELOW WILL NOT BE PERMITTED AT PROJECT COST. LEOS SHOULD NOT BE USED WHERE THE OMUTCD INTENDS THAT FLAGGERS BE USED.

IN ADDITION TO THE REQUIREMENTS OF CMS 614 AND THE OMUTCD, A UNIFORMED LEO WITH AN OFFICIAL PATROL CAR (CAR WITH TOP-MOUNTED EMERGENCY

FLASHING LIGHTS AND COMPLETE MARKINGS OF THE APPROPRIATE LAW ENFORCEMENT AGENCY) SHALL BE PROVIDED FOR THE FOLLOWING TRAFFIC CONTROL TASKS:

DURING THE ENTIRE ADVANCE PREPARATION AND CLOSURE SEQUENCE WHERE COMPLETE BLOCKAGE OF TRAFFIC IS REQUIRED.

FOR LANE CLOSURES:  DURING INITIAL SET-UP PERIODS, TEAR DOWN PERIODS, SUBSTANTIAL SHIFTS OF A CLOSURE POINT OR WHEN NEW LANE CLOSURE ARRANGEMENTS ARE INITIATED FOR LONG-TERM LANE CLOSURES/SHIFTS (FOR THE FIRST AND LAST DAY OF MAJOR CHANGES IN TRAFFIC CONTROL SETUP).

LEOS SHOULD NOT FORGO THEIR TRAFFIC CONTROL RESPONSIBILITIES TO APPREHEND MOTORISTS FOR ROUTINE TRAFFIC VIOLATIONS. HOWEVER, IF A

MOTORIST'S ACTIONS ARE CONSIDERED TO BE RECKLESS, THEN PURSUIT OF THE MOTORIST IS APPROPRIATE.

IN GENERAL LEOS SHOULD BE POSITIONED IN ADVANCE OF AND ON THE SAME SIDE AS THE LANE RESTRICTION OR AT THE POINT OF ROAD CLOSURE, AND TO MANUALLY

CONTROL TRAFFIC MOVEMENTS THROUGH SIGNALIZED INTERSECTIONS IN WORK ZONE.

THE LEOS WORK AT THE DIRECTION OF THE ENGINEER. THE CONTRACTOR IS RESPONSIBLE FOR SECURING THE SERVICES OF THE LEOS WITH THE APPROPRIATE

AGENCIES AND COMMUNICATING THE INTENTIONS OF THE PLANS WITH RESPECT TO DUTIES OF THE LEOS. THE ENGINEER SHALL HAVE FINAL CONTROL OVER THE LEOS'

DUTIES AND PLACEMENT, AND WILL RESOLVE ANY ISSUES THAT MAY ARISE BETWEEN THE TWO PARTIES.

THE LEO SHALL REPORT IN TO THE CONTRACTOR PRIOR TO THE START OF THE SHIFT, IN ORDER TO RECEIVE INSTRUCTIONS REGARDING SPECIFIC WORK ASSIGNMENTS DURING HIS/HER SHIFT. THE LEO IS EXPECTED TO STAY AT THE PROJECT SITE FOR

THE ENTIRE DURATION OF HIS/HER SHIFT. THE LEO SHALL REPORT TO THE CONTRACTOR AT THE END OF HIS/HER SHIFT. ONCE THE LEO HAS COMPLETED THE

DUTIES DESCRIBED ABOVE AND STILL HAS TIME REMAINING ON HIS/HER SHIFT, THE LEO MAY BE ASKED TO PATROL THROUGH THE WORK ZONE (WITH FLASHING LIGHTS OFF) OR BE PLACED AT A LOCATION TO DETER MOTORISTS FROM SPEEDING. SHOULD IT BE NECESSARY TO LEAVE THE PROJECT SITE, THE LEO SHALL NOTIFY THE

ENGINEER. THE CONTRACTOR SHALL PROVIDE THE LEO WITH A TWO-WAY COMMUNICATION DEVICE WHICH SHALL BE RETURNED TO THE CONTRACTOR AT THE

END OF HIS/HER SHIFT.

LEOS (WITH PATROL CAR) REQUIRED BY THE TRAFFIC MAINTENANCE TASKS ABOVE SHALL BE PAID FOR ON A UNIT PRICE (HOURLY) BASIS UNDER ITEM 614, LAW

ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE. THE FOLLOWING ESTIMATED QUANTITIES HAVE BEEN CARRIED TO THE GENERAL SUMMARY.

ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE   40 HOURS

THE HOURS PAID SHALL INCLUDE ANY MINIMUM SHOW-UP TIME REQUIRED BY THE LAW ENFORCEMENT AGENCY INVOLVED.

ANY ADDITIONAL COSTS (ADMINISTRATIVE OR OTHERWISE) INCURRED BY THE CONTRACTOR TO OBTAIN THE SERVICES OF AN LEO ARE INCLUDED WITH THE BID

UNIT PRICE FOR ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE.

Item 614, Portable Changeable Message Signs, As Per Plan

The Contractor shall furnish, install, maintain and remove, when no longer needed, a changeable message sign. The sign shall be of a type shown on a list of approved PCMS units available on the OFFICE OF MATERIALS MANAGEMENT web page. The list contains Class A and B units with minimum legibility distances of 800 feet and 650 feet, respectively.

Each sign shall be trailer-mounted and equipped with a functional dimming mechanism, to dim the sign during darkness, and a tamper and vandal proof enclosure. Each sign shall be provided with appropriate training and operation instructions to enable on-site personnel to operate and troubleshoot the unit. The

sign shall also be capable of being powered by an electrical service drop from a local utility company. The PCMS shall be delineated in accordance with C&MS 614.03.

Placement, operation, maintenance and all activation of the signs by the Contractor shall be as directed by the Engineer. The PCMS shall be located in a highly visible position yet protected from traffic. The Contractor shall, at the direction of the Engineer, relocate the PCMS to improve visibility or accommodate changed conditions. When not in use, the PCMS shall be turned off. Additionally, when not in use for extended periods of time, the PCMS shall be turned away from all traffic.

The Engineer shall be provided access to each sign unit and shall be provided with appropriate training and operation instructions to enable ODOT personnel to operate and troubleshoot the unit, and to revise sign messages, if necessary.

All messages to be displayed on the sign will be provided by the Engineer. A list of all required pre-programmed messages will be given to the Contractor at the project preconstruction conference. The sign shall have the capability to store up to 99 messages. Message memory or pre-programmed displays shall not be lost as a result of power failures to the on-board computer. The sign legend shall be capable of being changed in the field. Three-line presentation formats with up to six message phases shall be supported. PCMS format shall permit the complete message for each phase to be read at least twice.

The PCMS shall contain an accurate clock and programming logic which will allow the sign to be activated, deactivated or messages changed automatically at different times of the day for different days of the week.

The PCMS unit shall be maintained in good working order by the Contractor in accordance with the provisions of C&MS 614.07. The Contractor shall, prior to activating the unit, make arrangements, with an authorized service agent for the PCMS, to assure prompt service in the event of failure. Any failure shall not result in the sign being out of service for more than 12 hours, including weekends. Failure to comply may result in an order to stop work and open all traffic lanes and/or in the Department taking appropriate action to safely control traffic. The entire cost to control traffic, accrued by the Department due to the Contractor’s noncompliance, will be deducted from moneys due, or to become due the Contractor on his contract.

The Contractor shall be responsible for 24-hour-per-day operation and maintenance of these signs on the project for the duration of the phases when the plan requires their use.

Payment for the above described item shall be at the contract unit price. Payment shall include all labor, materials, equipment, fuels, lubricating oils, software, hardware and incidentals to perform the above described work.

Item 614, Portable Changeable Message Sign, as per plan 2 SIGN MONTH

Assuming 2 PCMS Sign(s) for 1 Month(s)

Dust Control

The Contractor shall furnish and apply water for dust control as directed by the Engineer. The following estimated quantities have been included for dust control purposes:

ITEM 616, WATER 1 M. GAL.

Maintenance of Traffic Signal/Flasher Installation

IT IS ANTICIPATED THAT THE FOLLOWING SIGNALIZED INTERSECTIONS WILL BE IMPACTED BY LOCAL DETOUR TRAFFIC:

SR-91 AND VETERANS WAY

SR-303 AND MILFORD ROAD/ATTERBURY BLVD

SR-91 and SR 303

SR-303 AND LIBRARY STREET

THE CONTRACTOR IS TO ANALYZE AND ADJUST SIGNAL TIMINGS AT THESE INTERSECTIONS DURING THE ROAD CLOSURE AS DIRECTED BY THE ENGINEER. ALL SIGNAL TIMINGS CHANGES ARE TO BE SUBMITTED TO THE CITY OF HUDSON FOR REVIEW AND APPROVAL PRIOR TO IMPLEMENTATION.

THE CONTRACTOR SHALL provide minimum 48 hour notice for city review and approval. a city of hudson represntative must be on site during the signal timing modifications.

The Contractor shall be responsible for maintaining traffic signal/flasher installations within the project under the following conditions:

1. Existing signal/flasher installations which the plans require the Contractor to adjust, modify, add onto or remove, or which the Contractor actually adjusts, modifies or otherwise disturbs. The Contractor shall be responsible for the entire installation (at an intersection) from the time his operations first disturb the installation until the installation has been subsequently removed or modified and the work is accepted.

2. New or reused signal/flasher installations or devices, installed by the Contractor. The

Contractor shall be responsible for maintenance of these from the time of installation until

the work is accepted.

The Contractor shall correct as quickly as possible all outages or malfunctions. He shall provide the maintaining agency and the Engineer such addresses and phone numbers where his

maintenance forces can be contacted. The Contractor shall provide one or more persons to receive all calls and dispatch the necessary maintenance forces to correct outages. Such a

person or persons may be used to perform other duties as long as prompt attention is given to

these calls and a person is readily available continuously 24 hours a day, 7 days a week. All

lamp outages, cable out 106136 MOT GEN NOTESages, electrical failures, equipment malfunctions and misaligned signal

heads shall be corrected to the satisfaction of the Engineer with the signal back to service

within four hours after the Contractor has been notified of the outage.

In the event new signals are damaged prior to acceptance, all damaged equipment except

poles and control equipment shall be replaced by the Contractor to the satisfaction of the

Engineer with the signal back in service within 8 hours after the Contractor's notification of the

outage. The Contractor shall arrange for full traffic control until the signal is back in operation. If poles and/or control equipment are damaged and must be replaced, the Contractor shall make temporary repairs as necessary to bring the signal back into full operation within the allowed 8-hour period, and shall make permanent repairs or replacement as soon thereafter as possible.

None of the above shall be construed as collective or consecutive outage time periods at any one location. That is, where more than one outage occurs at any one location then the allotted time limit shall be for the worst single outage.

Where outages are the direct result of a vehicle accident the response of the Contractor shall

be as outlined above. The Contractor shall be responsible for collection of any compensation

for this work from those parties responsible for the damage.

Where the Contractor has failed to, or cannot respond to, an outage or signal equipment

malfunction, at these locations within his responsibility, within periods as specified above, the Engineer may invoke the provisions of Section 105.15 and any subsequent billings to the State or the City of HUDSON for Police Services and maintenance services by City forces shall be deducted from monies due or to become due the contractor in accordance with provisions

of Section 105.15.

The Contractor shall provide the maintenance service entirely with his forces or he may choose to enter into a cooperative understanding with the local maintaining agency to provide the maintenance. The Contractor shall inform the Engineer, in writing, of the maintenance method selected.

The Contractor shall be responsible for any damage to any traffic signal components required to be handled during the relocation of poles and revisions to the signal system. When a traffic signal must be taken out of service by the Contractor, due to construction procedures, this outage shall not exceed 2 hours and shall not include the hours of 6 AM TO 9 AM AND 3 PM TO 6 PM. Any signalized intersection, where the signal is out of service due to construction procedures, or due to an outage or malfunction of equipment as described above, shall be protected, by the Contractor, by the installation of temporary "STOP" signs, except for the following intersections which shall be protected by off-duty City of HUDSON Police, hired by the Contractor:

1. SR-91 AND VETERANS WAY.

2. SR-303 AND MILFORD ROAD/ATTERBURY BLVD.

Any vehicular traffic signal head, either new or existing which will be out of operation shall be

covered in the manner described in 632.25.

The Contractor shall maintain complete records of malfunctions including:

1. Time of notification of malfunction;

2. Time of work crews arrival to correct the malfunction;

3. Actions taken to correct the malfunction, including a list of parts repaired or replaced;

4. A diagnosis of reason for the malfunction and probability of reoccurrence;

5. Time of completion of the repair and system restored to full service.

A copy of these records shall be provided to the Engineer within three (3) working days

following completion of each repair.

All costs resulting from the above requirements shall be considered to be included in the lump

sum price bid for Item 614, Maintaining Traffic.

Notification of Traffic Restrictions

Throughout the duration of the project, the Contractor shall notify the project engineer in writing of all traffic restrictions and upcoming maintenance of traffic changes. The Contractor shall ensure the written notification is submitted in a timely manner to allow the project engineer to meet the required time frames set forth in the table below to inform the Special Hauling Permits Section

(Hauling.Permits@dot.ohio.gov) and the District Public Information Office (PIO). This notification shall be received by the project engineer prior to the physical setup of any applicable signs or message boards.

Information should include, but is not limited to, all construction activities that impact or interfere with traffic and shall list the specific location, type of work, road status, date and time of restriction, duration of restriction, number of lanes maintained, number of lanes closed, minimum vertical clearance, minimum width of drivable pavement, detour routes, if applicable, and any other information requested by the project engineer.

Notification OF TRAFFIC RESTRICTIONS Time Table

| ITEM | DURATION OF CLOSURE | NOTICE DUE TO PERMITS & PIO |
| --- | --- | --- |
| RAMP & ROAD CLOSURES | ≥ 2 WEEKS | 21 CALENDAR DAYS PRIOR TO CLOSURE |
|  | > 12 HOURS & < 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE |
|  | ≤ 12 HOURS | 4 business days prior to closurE |
| LANE CLOSURES & RESTRICTIONS | ≥ 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE |
|  | < 2 WEEKS | 5 BUSINESS DAYS PRIOR TO CLOSURE |
| START OF CONSTRUCTION & TRAFFIC PATTERN CHANGES | N/A | 14 CALENDAR DAYS PRIOR TO IMPLEMENTATION |

Any unforeseen conditions not specified in the plans requiring traffic restrictions shall also be reported to the project engineer using the Notification Time Table.

COOPERATION BETWEEN CONTRACTORS

THE CONTRACTOR SHALL BE ADVISED THAT PROJECT (PID 106445) MAY BE ONGOING IN AN AREA IMMEDIATELY ADJACENT TO AND WITHIN THE PROJECT LIMITS OF THIS

PROJECT. THE CONTRACTOR SHALL SCHEDULE HIS WORK SO AS TO CAUSE A MINIMUM OF DELAY OR CONFLICT WITH THE OTHER PROJECTS. IN ACCORDANCE WITH

105.08, THE CONTRACTOR SHALL ARRANGE WITH THE OTHER CONTRACTORS APPROVAL OF THE ENGINEER. THE CONTRACTOR SHALL RECEIVE DAILY APPROVALS

FROM THE ENGINEER PRIOR TO COMMENCING ANY OPERATIONS. ANY CONFLICT BETWEEN CONTRACTORS INVOLVING WORK SCHEDULES, WORK AREA, OR

COOPERATION SHALL BE RESOLVED BY THE ENGINEER. COMPENSATION FOR THE ABOVE COOPERATION SHALL BE INCIDENTAL TO THE VARIOUS PAY ITEMS INCLUDED

WITHIN THIS PROJECT.

Item 614, Business Entrance (M4-H15) Sign, As Per Plan

The Business Entrance (M4-H15) sign should be provided at each temporarily relocated commercial Driveway for which the relocation is not obvious to the motorist. The project Engineer shall determine whether or not the driveway relocation is, or is not, obvious and whether or not a sign should be provided. Only one sign per Business shall be permitted. The sign shall be 36 inch X 48 inch in size with Type G or Type H orange retroreflective sheeting. The sign legend shall be placed on both sides of the sign (back to back). The sign shall have the standard M4-H15 legend with the word “BUSINESS” on the top line, except under unusual circumstances where it may not be intuitive that a driveway serves a specific business. In such unusual cases, the actual business name may be substituted for the word “BUSINESS”.

The sign shall be mounted on two #3 posts or on temporary posts in accordance with SCD MT-105.10 and in accordance with the Ohio Manual of Uniform Traffic Control Devices, latest edition. The sign shall be clearly visible and shall clearly identify the location of the driveway. The sign should be positioned at 90° to the direction of traffic. The sign may need to be moved for each Phase of the Maintenance of Traffic operations.

Payment for all costs associated with manufacturing, mounting, relocating, and removing the sign, including all labor, materials and equipment shall be included in the contract price per Each for Item 614-Business Entrance sign.

The following estimated quantity has been carried to the general summary for this item.

Item 614, Business Entrance Sign 1 Each