## WEST APP ROAD
Revision Date:
2010-04-12
WB MAINLINE WEST APPROACH ROADWAY FROM I-71 / I-90 SPLIT TO KENILWORTH
The facilities tabulated below are located inside the existing I-90 aerial ROW.
Starkweather Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Wire tie-ins | Active | Across | 102 + 00 | CPP | PUBLIC | City | City | MAYBE | CONTRACT | LOW | YES | DBT
Freeway Lighting | Active | Parallel | West | ODOT | PUBLIC | ODOT | ODOT | MAYBE | CONTRACT | LOW | YES | DBT
Wire tie-ins | Active | Parallel | West | CPP | PUBLIC | City | City | MAYBE | CONTRACT | LOW | YES | DBT
Other potential aerial conflicts may be encountered due to bridge deck reconstruction include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## WEST APP WALL
Revision Date:
2010-04-12
WB MAINLINE WEST APPROACH RETAINING WALLS BETWEEN KENILWORTH AND FAIRFIELD
No immediately identified aerial utility conflicts, however, potential conflicts may include overhead power and lighting lines; utility service connections and other above and underground facilities.

## KENILWORTH
Revision Date:
2010-04-12
WB MAINLINE OVER KENILWORTH BRIDGE WIDENING
The facilities tabulated below are located inside the existing Kenilworth Avenue aerial ROW.
Kenilworth Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Freeway Lighting | Active | Across | 110 + 00 | ODOT | PUBLIC | ODOT | ODOT | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Other potential aerial conflicts may be encountered due to bridge deck reconstruction include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## FAIRFIELD
Revision Date:
2010-04-12
WB MAINLINE OVER FAIRFIELD BRIDGE
Fairfield Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Across | 119 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 119 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 119 + 75 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
West 16th Place
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | CL | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 17 + 50 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 18 + 50 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
West 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## RAMP A6
Revision Date:
2010-04-12
RAMP A6 CONSTRUCTION (WB MAINLINE TO ABBEY / W 14TH)
W 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## WEST BANK
Revision Date:
2010-04-12
WEST BANK SLOPE UNLOADING
University Road - West
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 131 + 00 | UNKNOWN | PRIVATE | City | ODOT | MAYBE |  | NEUTRAL | YES | DBT
AD Lights | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Across | 131 + 50 | UNKNOWN | PRIVATE | City | ODOT | MAYBE |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | South |  | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | South |  | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
University Road - East
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Across | 130 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Across | 130 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
West 13th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Across | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Across | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Across | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW |  | DBT
Crown Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 128 + 75 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | North | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | South | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 129 + 00 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
W 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 813 + 00 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 813 + 00 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
W 14th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | South |  | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | South |  | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## SUBSTRUCTURE
Revision Date:
2010-04-12
I-90 VIADUCT SUBSTRUCTURE UNITS (W 14TH STREET EXTENSION TO ONTARIO STREET)
DBT TO PROVIDE SUBSTRUCTURE UNIT LOCATIONS AND COMPLETE TABLES
DBT to add tables as necessary for each additional substructure unit. DBT to add rows to tables as necessary to account for each identified impact.
REAR ABUTMENT STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN
WEST APPROACH PIER "N" STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN
FORWARD ABUTMENT STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Utility facilities being abandoned or relocated as part of West Bank Slope Unloading within the proposed Right of Way from Abbey Avenue to the Cuyahoga River.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## VALLEY
Revision Date:
2010-04-12
VALLEY AREA
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | Private | ODOT | YES |  | HIGH | YES | DBT
West 4th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 150 + 00 | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | ODOT | YES |  | HIGH | YES | DBT
West 3rd Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 153 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 153 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | CL | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | CL | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Billboard Lights | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## ONTARIO
Revision Date:
2010-04-12
RAMP A4 AND WB MAINLINE OVER ONTARIO BRIDGE
The facilities tabulated below are located inside the existing Ontario Street aerial ROW.
Ontario Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
| Active |  |  | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## EAST APP ROAD
Revision Date:
2010-04-12
WB MAINLINE EAST APPROACH ROADWAY
Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 157 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 158 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | NO |  | LOW | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | CL | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 157 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 157 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 160 + 75 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | CL | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 160 + 75 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Central Viaduct
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 159 + 25 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Across | 160 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Parking Lot
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 164 + 25 | UNKNOWN | PRIVATE | Private | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 164 + 25 | UNKNOWN | PRIVATE | Private | City | YES |  | HIGH | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## RAMP A4 WALL
Revision Date:
2010-04-12
RAMP A4 RETAINING WALL (Adjacent to CCC)
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## E 9TH
Revision Date:
2010-04-12
RAMP A3 OVER E 9TH BRIDGE
The facilities tabulated below are located inside the existing E 9th Street aerial ROW.
E 9th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Across | 511 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Across | 512 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | HIGH | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## RAMP A3 ROAD
Revision Date:
2010-04-12
RAMP A3 ROADWAY (Adjacent to Hilton)
Webster Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## RAMP A3 WALL
Revision Date:
2010-04-12
RAMP A3 RETAINING WALL (Adjacent to Hilton Hotel)
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.