## E 9TH STREET
Revision Date:
2026-08-06
EAST 9TH STREET STORM SEWER OUTFALL AREA
Along Broadway Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Railroad Crossing | Active | Across | 102 + 50 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO
Along East 9th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Railroad Crossing | Active | Across | 109 + 40 | GCRTA | PRIVATE | Private | GCRTA | NO | CONTRACT | NEUTRAL | NO
Railroad Crossing | Active | Across | 109 + 60 | GCRTA | PRIVATE | Private | GCRTA | NO | CONTRACT | NEUTRAL | NO
8” Water | Active | Across | 112 + 40 | CWD | PUBLIC | Private | City | YES | CONTRACT | HIGH | YES | DBT
Communications | Abandoned | Across | 115 + 30 | SPRINT | PRIVATE | Private | City | YES | YES | LOW | YES | SPRINT
Electric conduit | Active | Across | 118 + 45 | CEI | PRIVATE | City | City | YES | NO | HIGH | YES | CEI
12" Water | Active | Across | 118 + 70 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
8" Gas | Active | Across | 122 + 50 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
6” Gas | Active | Across | 122 + 55 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
Communications | Active | Across | 122 + 75 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT
Unidentified Facility | Active | Across | 122 + 75 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN
24" Combined Sewer | Active | Across | 122 + 80 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
6” Water | Active | Across | 122 + 95 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Along Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Unidentified Facility | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Unidentified Facility | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
8" Gas*** | Active | Parallel | North | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6" Gas*** | Active | Parallel | North | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Electric conduit | Active | Parallel | North | CPP | PUBLIC | City | City | NO | YES | HIGH | NO | NOT ALLOW
128 KV Conductor**** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
128 KV Conductor**** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
Communications*** | Active | Parallel | North | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
12" Water*** | Active | CL |  | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications*** | Active | Across | 17 + 75 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
128 KV Conductor**** | Active | Across | 16 + 45 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
Communications*** | Active | Across | 16 + 45 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
128 KV Conductor**** | Active | Across | 16 + 10 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
12" Water*** | Active | Across | 15 + 00 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications*** | Active | Across | 14 + 60 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
36" Combined Sewer*** | Active | Across | 14 + 60 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Unidentified Facility*** | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
8" Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6” Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Horizon Tunnel**** | Active | Across | 13 + 40 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW
Unidentified Facility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
6” Water | Active | Parallel | West | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Along Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
6” Water | Active | Across | 123 + 40 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Communications | Active | Across | 123 + 50 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT
24" Combined Sewer | Active | Across | 123 + 60 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
8" Gas | Active | Across | 124 + 05 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
6” Gas | Active | Across | 124 + 10 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
12" Combined Sewer | Active | Across | 125 + 40 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
10” Water | Active | Across | 125 + 55 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Along 40' Storm Easement
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Communications | Abandoned | Across | 126 + 15 | SPRINT | PRIVATE | City | City | NO | YES | LOW | YES | SPRINT
Railroad Crossing | Active | Across | 126 + 25 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO
Railroad Crossing | Active | Across | 126 + 40 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO
Railroad Crossing | Active | Across | 127 + 00 | CSX | PRIVATE | Private | CSX | NO | CONTRACT | NEUTRAL | NO
Communications | Active | Across | 127 + 05 | ATT | PRIVATE | City | City | MAYBE | NO | HIGH | YES | ATT
* Stationing is taken from the Storm Sewer alignment. See Appendix DR-02 Conceptual Drainage Evaluation, "Commercial Road Region Drainage - BMP View".
** Stationing is taken from proposed Commercial Road alignment.
*** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
**** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## EAST BANK
Revision Date:
2026-08-06
EAST BANK STORM SEWER OUTFALL AREA
Central Viaduct Way
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station**** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric conduit* | Active | Across | 100 + 95 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Communications* | Active | Across | 101 + 00 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
128 KV Conductor** | Active | Across | 101 + 25 | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
128 KV Conductor** | Active | Across | 101 + 60 | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
4" Gas* | Active | Across | 102 + 20 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Communications* | Active | Across | 103 + 05 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
12" Water* | Active | Across | 103 + 20 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station**** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Horizon Tunnel** | Active | Across | 106 + 40 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW
6” Water*** | Active | Across | 106 + 10 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications*** | Active | Across | 106 + 15 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
24" Combined Sewer*** | Active | Across | 106 + 25 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
8" Gas*** | Active | Across | 107 + 45 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
4” Gas*** | Active | Across | 107 + 50 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
Railroad Crossing | Active | Across | 109 + 00 | CSX | PRIVATE | Private | CSX | YES | CONTRACT | HIGH
Railroad Crossing | Active | Across | 109 + 20 | CSX | PRIVATE | Private | CSX | YES | CONTRACT | HIGH
Communications*** | Active | Across | 109 + 40 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
West 3rd Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station**** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
15" Combined Sewer | Active | Across | 111 + 45 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
6” Water | Active | Across | 111 + 55 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
10” Water | Active | Across | 111 + 70 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
4” Gas | Active | Across | 111 + 90 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
Industrial Flats Driveway
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station**** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
2” Water | Active | Across | 115 + 00 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
2” Water | Active | Across | 117 + 50 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Electric conduit | Active | Across | 122 + 45 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Railroad Crossing | Active | Across | 123 + 60 | NS | PRIVATE | Private | NS | YES | CONTRACT | HIGH
Communications | Active | Across | 123 + 70 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Railroad Crossing | Active | Across | 123 +85 | NS | PRIVATE | Private | NS | YES | CONTRACT | HIGH
* Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
*** Utility facilities located under existing Canal Road. Facility position varies with actual location on Canal Road.
**** Stationing is taken from the Storm Sewer alignment. See Appendix DR-02 Conceptual Drainage Evaluation, "East Bank Drainage BMP Plan View".
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## WEST BANK - EAST of I90
Revision Date:
2026-08-06
WEST BANK STORM SEWER OUTFALL AREA
EAST OF I90
West 15th Street (old ROW)
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Unidentified Facility | Active | Across | 100 + 25 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN
1.5" Water | Active | Across | 100 + 60 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
15" Combined Sewer | Active | Across | 101 + 45 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Fairfield Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
8” Gas | Active | Across | 102 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
12" Combined Sewer | Active | Across | 102 + 30 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
10" Water | Active | Across | 102 + 40 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer | Active | Across | 102 + 55 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Electric conduit | Active | Across | 102 + 60 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
8” Gas | Active | Across | 102 + 70 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric conduit | Active | Across | 110+ 00 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Electric conduit | Active | Across | 110 + 35 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
6” Water | Active | Across | 110 + 60 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
16” Water | Active | Across | 111 + 10 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
12" Combined Sewer | Active | Across | 111 + 40 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
University Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
60" Combined Sewer | Active | Across | 112 + 90 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
2” Gas | Active | Across | 113 + 00 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Electric conduit | Active | Across | 113 + 60 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Communications | Active | Across | 113 + 75 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Electric conduit | Active | Across | 113 + 75 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
21" Combined Sewer | Active | Across | 113 + 75 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer | Active | Across | 114 + 35 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
6” Gas | Active | Across | 114 + 40 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
24" Combined Sewer | Active | Across | 115 + 10 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
* Stationing is taken from the Storm Sewer alignment. See Appendix DR-02 Conceptual Drainage Evaluation, "West Bank Drainage - BMP View".
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## WEST BANK - WEST of I90
Revision Date:
2026-08-06
WEST BANK STORM SEWER OUTFALL AREA
WEST OF I90
West 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
15" Combined Sewer | Active | Across | 100 + 20 | NEORSD | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | NEORSD | Advance | 2010-03-19 | 17.5 | 2011-08-26
6” Water | Active | Across | 100 + 30 | CWD | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | DBT
8” Gas | Active | Across | 100 + 45 | DEOG | PRIVATE | City | ODOT | MAYBE | NO | HIGH | YES | DEOG
Abbey Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric conduit | Active | Across | 103 + 40 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Unidentified Facility | Active | Across | 103 + 50 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN
6” Water | Active | Across | 103 + 60 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
6" Gas | Active | Across | 103 + 95 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
Crown Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
6" Water | Active | Across | 104 + 70 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT
18" Combined Sewer | Active | Across | 104 + 80 | CWPC | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD
Cold Storage Drive
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric conduit | Active | Across | 107 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Electric conduit | Active | Across | 107 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
University Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
16” Water | Active | Across | 107 + 90 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT
Electric conduit | Active | Across | 107 + 95 | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN
24" Combined Sewer | Active | Across | 108 + 05 | NEORSD | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD
Electric conduit | Active | Across | 108 + 10 | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN
Communications | Active | Across | 108 + 20 | ATT | PRIVATE | City | ODOT | YES | NO | HIGH | YES | ATT
6” Gas | Active | Across | 108 + 25 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG
* Stationing is taken from the Storm Sewer alignment. See Appendix DR-02 Conceptual Drainage Evaluation, "West Bank Drainage - BMP View".
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
VERIZON
SPRINT
NOT ALLOW
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.